## ADDITIONAL DOCUMENT 3

Table 3.1. Set of strategies conducted in phases 1, 2, and 3 of the multiphase RT implementation

| Project Phase | Strategy | Define strategy | Actor | Actions |
| --- | --- | --- | --- | --- |
| P1 | Identify early adopters | Identify early adopters at the local site to learn from their experiences with the practice innovation | Human and animal health providers, health care administrators, bureaucrats at the regional and local level, local elected officials | Social network interviews |
| P1, P2, P3 | Cultivate relationships with animal, human and enviroment stakeholders | Recruit and cultivate relationships with leaders of health care centers, community, and animal and environmental health | Idem | Meetings introduced the RT protocol and reviewed the activities needed to improve community-engaged surveillance for T.Solium. Interviews |
| P1 | Obtain formal commitments | Obtain written commitments from key partners that state what they will do to implement the innovation | The head of each health care facility in the district, as well as representatives of regional human and animal governmental systems | Meetings |
| P2, P3 | Conduct participatory educational meetings and community outreach meetings | Hold targeted meetings for different stakeholder groups to teach them about the innovation. | The head of each health care facility in the district, as well as representatives of human and animal governmental systems, such as human health zoonosis coordinators and chief of agricultural health services, and local governors and municipality workers in charge of animal health services. | Meetings introduced the RT protocol and reviewed the activities needed to improve community-engaged surveillance for T.Solium. Staff conducted a brief needs assessment and reviewed the health systems surveillance forms and study data collection instruments. We provided a 4-hour participatory workshop in each village to describe the T. Solium transmission cycle. Participants were taught the technique for examining a pig with cysticercosis using a tongue examination to confirm the disease, as well as visualizing a cyst in infected meat. The session also included an introduction to the RT intervention and promoted surveillance and reporting of infected pigs or meat. Seven training sessions lasting 2 hours each were also held for health care personnel and community health workers, covering topics such as T. Solium transmission, the epidemiological surveillance system, the administration of antiparasitic drugs (e.g., niclosamide or praziquantel), and the use of records and instruments. |
| P2, P3 | Involve and train the community health workers and community leaders in implementation efforts | Train community health workers and local leaders in community-surveillance systems | Community members, local authorities, and representatives from animal and human health systems | Community health workers (CHWs) served as key players and links between the community and human and animal health systems in the epidemiological surveillance system for taeniasis. CHW received reports and participated in inspections of meat or in the slaughter of pigs. They actively conducted outreach activities, providing educational materials and information to communities, and identified cases of porcine cysticercosis, as well as proposed ideas for case reporting. |
| P2, P3 | Alter community incentive structure | Work to incentivize the reach by introducing payment approaches using other community payment/animal cost replacement schemes | Community health workers, elected mayor, and local environmental health municipal workers | Instituted the provision of a food basket in restitution for a report of a pig or meat |
| P2, P3 | Alter surveillance system's structure | Developing new tools and adapting systems to incentivize reporting and surveillance of infected animals or meat in human health surveillance systems | Community health workers and responsible for epidemiology |  |
| P1 | Assess for readiness and identify barriers and facilitators | Assess various aspects of an organization to determine its degree of readiness to implement, barriers that may impede implementation, and strengths that can be used in the implementation effort | Human and animal health providers, health care administrators, bureaucrats at the regional and local level, and local elected officials |  |
| P1, P2, P3 | Stage implementation scale up | Phase implementation efforts by starting with small pilots or demonstrations projects and gradually move to a system-wide rollout | Local and regional human and animal health providers and administrators, policy makers, community health workers, and elected officials |  |
| P2, P3 | Provide consultation for the development of regulatory documents, directives or ordinances | Regional directives and local ordinances informed by RT protocol for community- engaged surveillance | Regional and local policy makers |  |
| P2, P3 | Provide ongoing consultation to human and animals systems | Provide ongoing consultation with one or more experts in the strategies used to support implementing the innovation | Human and animal health providers, health care administrators, community health care workers | A training program led by a veterinarian from the Peruvian National Agrarian Health Service was conducted (July - August, 2024), training 12 community slaughterers and 16 CHWs to recognize cysticercosis cysts in pork. This activity was carried out in each participating locality. Educational materials such as posters, brochures, calendars, and videos were also developed by health personnel with the support of the research team. Also, key messages on the transmission and prevention of taeniasis/cysticercosis were broadcast on village radio stations. |
| P2, P3 | Capture share local knowledge | Capture local knowledge for adaptations that could work better in their setting | Clinicians and community health workers | Meetings and interviews |
| P2, P3 | Top-down approach | Engagement and dissemination with regional, national, and global health leaders | Zoonoses representatives of the Panamerican Health Organization, national and regional zoonoses from the Ministry of Health | Dissemination meetings |
| P2, P3 | Promote network weaving | Identify and build on existing high-quality working relationships and networks within and outside the organization, organizational units, teams, etc. to promote information sharing, collaborative problem-solving, and a shared vision/goal related to implementing the innovation | Zoonoses representatives of the Panamerican Health Organization, national and regional zoonoses from the Ministry of Health and Agriculture | Dissemination meetings and policy research |