# Implementation Failure Assessment Guide

Questions researchers and implementation teams can ask before, during, and after implementation — organized around four concepts contextual conditions, types of failure, power & equity, and responses/learning.

| Theme | Before | During | After |
| --- | --- | --- | --- |
| 1. Context & Recurring Determinants — Under what conditions? At what system/organizational level? |  |  |  |
| Structural & systemic foundations | ☐ Do staffing, workflows & technical infrastructure allow this without overburdening frontline teams? ☐ Does the policy mandate include clear, specific milestones? ☐ Is decision-making authority clearly assigned between funders/system actors and the implementing organization? | ☐ Is frontline capacity (staffing, workload, turnover) holding up as conditions change? ☐ Are outer-setting policies and inner-setting resources still aligned? | ☐ Did staffing instability, restricted autonomy, vague mandates, or underfunding contribute to the shortfall? ☐ At which level — inner, outer, or the misalignment between them — did it originate? |
| Gaps in implementation planning | ☐ Has a needs assessment and contextual analysis been done? ☐ Are roles, responsibilities & milestones defined? ☐ Have those affected by (or delivering) the innovation been engaged in shaping it? ☐ Is a facilitation/coaching plan in place? ☐ Has this initiative's priority relative to competing demands been assessed honestly? | ☐ Are engagement and facilitation actually happening as planned? ☐ Has the initiative slipped down the priority list? | ☐ Which planning gap — missed assessment, weak engagement, thin facilitation, competing priorities — best explains what happened? |
| Individual capability, opportunity & motivation | ☐ Do implementers have the needed skills? ☐ Do they have the time, authority & supervisory support to act? ☐ Do frontline staff even know the initiative exists? | ☐ Is motivation holding, or is the innovation experienced as an administrative burden? ☐ Are people getting the information/training they need as new demands arise? | ☐ Which COM-B element — capability, opportunity, or motivation — broke down, and for which group of implementers? |
| Innovation–context fit | ☐ Does the innovation address local priorities? ☐ Were recipients engaged in adapting its design? ☐ Is its complexity manageable for the roles that must deliver it? | ☐ Where is the innovation clashing with existing workflows, culture, or recipient needs as they evolve? | ☐ Did a mismatch between the innovation, recipients & context drive the outcome? ☐ Was there room for legitimate adaptation, or was fidelity enforced too rigidly (or too loosely)? |
| Temporal phase transitions (Exploration → Sustainment) | ☐ Exploration: is the environment actually ready to receive this, or is there a “wall” of hesitancy despite stated enthusiasm? ☐ Preparation: has assessment and stakeholder engagement genuinely happened before adoption, not just been assumed? | ☐ Implementation: is there a defensible balance between fidelity and adaptation? ☐ Are chosen strategies being deployed as intended? | ☐ Sustainment: are structures and monitoring in place to prevent reversion once formal support ends? |
| 2. Types & Manifestations of Failure — What — and for whom? |  |  |  |
| Implementation vs. innovation failure | ☐ How will we distinguish implementation failure from innovation/intervention failure? ☐ Will process measures (fidelity, reach) be tracked separately from clinical/programmatic outcomes? | ☐ Are process and outcome data both being collected, so either type of failure would be visible? | ☐ Was this an innovation failure, an implementation failure, or both? ☐ What evidence separates the two? |
| Manifestations (mis-implementation, unanticipated impacts, pseudo-compliance) | ☐ What would mis-implementation, unanticipated harm, or pseudo-compliance look like here? ☐ How would each be detected if it occurred? | ☐ Are we continuing something ineffective, or terminating something that was working (mis-implementation)? ☐ Are ripple effects emerging — burnout, stigmatization, loss of autonomy, eroded trust? ☐ Is there outward compliance masking covert workarounds (shadow systems, quiet resistance)? | ☐ For whom did it fail — which recipients or communities bore the cost? ☐ Which specific type of failure occurred, and what distinguishes it from ordinary, appropriate adaptation? |
| 3. Power & Equity — According to whom? |  |  |  |
| Whose definitions & authority | ☐ Whose definition of “success” is guiding this work? ☐ Who holds the structural authority to decide which adaptations are acceptable? | ☐ Who currently holds the power to approve, halt, or redirect adaptations? | ☐ Who decided this was (or wasn't) a failure, and from what vantage point? |
| Voice, safety & whose knowledge counts | ☐ Have recipient and frontline voices been included in defining what “working” means? | ☐ Can staff or recipients raise concerns without fear of surveillance or punishment? ☐ Whose knowledge is being privileged when adaptation decisions get made? | ☐ Whose knowledge counted when this was evaluated — and whose was missing? |
| Distribution of benefits & burden | ☐ Could this disproportionately burden or exclude historically marginalized groups? | ☐ Are benefits and burdens being distributed evenly across sites, roles, or populations? | ☐ Were benefits and burdens distributed equitably? ☐ Could this be read as a rights issue — a population deprived of benefits it was entitled to share in? |
| 4. Responses & Learning — So what? |  |  |  |
| Proactive preparation for learning | ☐ Has a premortem, predictive process evaluation, or FMEA been used to anticipate failure points? ☐ Are implementation strategies specified up front (e.g., via ERIC) so limitations are traceable later?(1) ☐ Is there a plan to report implementation outcomes (Proctor taxonomy) separately from clinical outcomes?(2) | ☐ Are early warning signs being tracked against the anticipated failure points? | ☐ Did the premortem/predictive work anticipate what actually happened? What would we add next time? |
| Cultural safety & determinant tracking | ☐ Is there a plan for staff to report problems without it being read as personal failure? | ☐ Is there cultural safety for staff to report emerging problems as they arise? ☐ Are we tracking multi-level determinants rather than defaulting to individual blame? | ☐ Did the team feel safe naming what went wrong, or was blame individualized? |
| Structured learning & reporting | ☐ Is equity built in as an explicit outcome to be assessed, not an afterthought? | ☐ Is learning being captured as it happens, not deferred entirely to a final report? | ☐ What structured learning process follows — something more than a tokenistic “lessons learned”? ☐ Should this be reimplemented — and if so, because of a failed initial attempt, a need for modification, or a sustainment failure? ☐ Will this be reported in a way journals/funders will accept, including null or negative findings? |

1.	Proctor EK, Powell BJ, McMillen JC. Implementation strategies: recommendations for specifying and reporting. Implement Sci. 2013;8:139.

2.	Proctor E, Silmere H, Raghavan R, Hovmand P, Aarons G, Bunger A, et al. Outcomes for Implementation Research: Conceptual Distinctions, Measurement Challenges, and Research Agenda. Administration & Policy in Mental Health & Mental Health Services Research. 2011;38(2):65-76.