Table 2. Key Quantitative Data Extracted from Documentary Sources

| Data Point | Value | Source(s) |
| --- | --- | --- |
| HWA establishment | 15 April 1974 | HWA (n.d.); Wikipedia (2024) |
| HWA workforce | 629 employees | Wikipedia (2026) |
| HWA annual budget | USD 6.2 million | Wikipedia (2026) |
| Fuel share of HWA budget | 50% | EY/WSP (2014); Farah (2015) |
| Pre-project water production | 9 million liters/day | UN-Habitat (2014); SDF (2014) |
| Post-HUWSUP design capacity | 14.5–20 million liters/day | UN-Habitat (2015) |
| Population with piped water access | 35% | SDF (2014); Farah (2015) |
| Population relying on water trucking | 65% | SDF (2014); Farah (2015) |
| Production vs. WHO minimum standard | 47% below | UNICEF (2012); Farah (2015) |
| Geed Deeble boreholes | 13 | UHL & Associates (2012); Farah (2015) |
| Original pipeline specifications | Twin 300mm, 20km | Farah (2015); UN-Habitat (2014) |
| HUWSUP pipeline length | 23 km | UN-Habitat (2015) |
| HUWSUP EU funding | EUR 15 million | UN-Habitat (2015) |
| HUWSUP SDF1 funding | USD 8.6 million | SDF (2014) |
| HUWSUP planned completion | 2017 | UN-Habitat (2015) |
| HUWSUP actual completion | 2022 | EU Delegation (2022) |
| HUWSUP delay duration | ~5 years | Calculated from above |
| HWSBSP KfW/BMZ funding | EUR 33 million | KfW (n.d.); GTAI (2023) |
| HWSBSP additional 2025 pledge | EUR 18 million | HWA (2025) |
| Ludwig Pfeiffer insolvency date | Mid-December 2021 | HWA (2025) |
| HWSBSP original completion | Jan 2023–Jan 2024 | GTAI (2023) |
| HWSBSP extended deadline | January 2025 | HWA (2025) |
| HWSBSP revised completion (direct impl.) | Before October 2025 | HWA (2025) |
| HWSBSP delay duration (as of 2025) | 4+ years | Calculated from above |
| HWSBSP scope: reservoirs | 4 RC, 7,600 m³ | GTAI (2023) |
| HWSBSP scope: transmission mains | 4 lines, 14 km | GTAI (2023) |
| HWSBSP scope: distribution networks | 6 networks, 157 km PE | GTAI (2023) |
| Hargeisa population (est.) | 1 million+ | Farah (2015); UNITAC (n.d.) |
| Annual population growth rate | 5–7% | Farah (2015); Hargeisa Municipality |
| IDP population | 111,000+ | UNITAC (n.d.) |
| Piped water price | USD 1.50/m³ | SIDA (2014); Farah (2015) |
| Trucked water price | Up to USD 7.50/m³ | SIDA (2014); Farah (2015) |
| Water price per barrel (piped) | ~USD 0.03 | UNITAC (n.d.) |
| Water price per barrel (trucked) | ~USD 2.50 | UNITAC (n.d.) |
| Kalqoray Dam capacity | 1.4 million m³ (1.8M with check-dam) | HWA (2025b) |
| Cumulative investment (by 2018) | ~EUR 53.2 million | Somaliland Economic (2018) |
| SDF1 allocation (boreholes/network) | USD 1.76 million | SDF (2014) |