Supplementary materials 2 - RELAX Patient and Public Involvement and Engagement Advisory Group meetings and related activities

| Public involvement (PPI) in phases of the study | Months duration | Budget available | PPI lead involvement | Key PPI events (32 in total) PPI and Engagement Advisory Group (PPIE-AG | Dates of PPI events | Processes and purpose: Topics discussed and presentations, decisions taken. PPIE-AG meetings were usually attended by the clinical trial coordinator (CTC), principal investigator (PI), PPI lead, and research assistant (RA). (In brackets, 13 individual PPI advisers are named, plus one other lived-experience video interviewee.) |
| --- | --- | --- | --- | --- | --- | --- |
| Pre-funding | 24 | No/low budget |  | King’s MNVP meetings (x3) Parent Action, ARC PPI: meetings | 2019/2020 2019 | PI advised by midwife, Laura Brindle. Meetings were held to discuss: Aims of the RCT, proposed eligibility. What do women want? Best timing in pregnancy/after birth for training. PPI co-investigator and PPI lead recruited. |
| Set-up Oct 2021-May 2023 | 20 | Yes/part | Contract from: 1st Feb 2022 | Lived experience workshops (x2) Parent Action community lunch PPIE-AG meeting 1 PPIE-AG meeting 2 PPIE-AG meeting 3 | 2022 Mar 2022 April 2022 May 2022 Nov 2023 Apr | Held online to discuss lived experiences; proposed study aims; eligibility; timing; interest in a PPI advisory role. Lived experiences; proposed study aims; eligibility; timing; interest in a PPI advisory role (Omar & Michele) Welcome and introductions, anxiety presentation; study logo and platform visuals; PPIE-AG terms of reference; PPIE plan; non-NHS recruitment, social media; training scenarios; any training needs; PPI payments. Welcome, introductions; study progress; PPI ‘usability testing’ of platform; PPI WhatsApp group; PPI in research training; NIHR ARC Involvement Learning Network event; Introduction of East of England Researcher feedback. Welcome and introductions, update on study progress; community recruitment (social media; mugs, pens, posters, business cards); NHS recruitment (small group work); PPI feedback (‘How is it for you?’ Shall we write a PPI blog? Co-create a newsletter?) A 30-min informal chat with the PPI lead after formal meeting introduced. |
| Recruitment to RCT June 2023-July 2024 | 13 | Yes |  | PPIE-AG meeting 4 PPIE-AG meeting 5 PPIE-AG meeting 6 PPIE-AG meeting 7 PPIE-AG meeting 8 | 2023 July 2023 Sept 2023 Nov 2024 Mar 2024 Jun | Welcome and introductions; update on study (recruitment started 8th June); community and NHS recruitment (detailed social media co-planning; Chrissy & Ophilia video, Abi video); planning newsletter 1; PPI feedback. Welcome and introductions, update on study progress; community and NHS recruitment; planning for a social media campaign (Sam video); reflections lessons learned; PPI blog update; planning newsletter 2; PPI feedback. Welcome and introductions; update on study: community and NHS recruitment; Change to worry score threshold (32>28); PPI advisors’ views and insights; PPI blog published; feedback on PPI training. Welcome and introductions; update on study: community and NHS recruitment; two new NHS sites; guest presentation on inclusivity; guest presentation on perinatal education; PPI and researcher feedback exchanged. Welcome, update on study: recruitment – almost complete! Conference poster featuring public advisers; presentation by PPI lead on peer researchers; intro of telephone interviews and framework analysis. |
| Data collection - non-PPI Aug 2024-May 2025 PPI activities: involvement in developing interview guide, PPI survey, EDI presentations, framework analysis | 10 | Yes |  | PPIE-AG meeting 9 PPI-led EDI meeting PPIE-AG meeting 10 Co-design PPI survey meeting PPIE-AG meeting 11 | 2024 Oct 2025 Jan 2025 Feb 2025 Mar 2025 Mar | Progress update, inc (T3) scoping questions; presentation: trial coordinator on framework analysis/enhanced PPI roles; PPI views sought on new study (Anchor), extension funding request & letter to NIHR; newsletter planning. Online planning meeting for PPI lead and two PPI speakers (experience of areas of deprivation in South London and Blackpool; Black and white ethnicity) to present at a research unit training event on inclusion. Welcome; update on study progress; proposed extension update / letter of support to funder re extension; Shortlisting: Black Maternal Health Awards 2025; feedback discussion on PPI-led inclusion presentations. Online planning meeting for seven PPI advisers and PPI lead to co-design PPI advisers’ reflections survey, working with RA on application for ethics approval. Welcome and introductions; updates; presentation on planning stakeholder workshop and discussion; plus presentation on PPI in RELAX/research on PPI, by PPI lead. Framework analysis and PPI feedback (Tania & Dylan). |
| Analysis and writing up June-Nov 2025 [end of project funding] NB: public engagement, the sharing of results, was planned and started during this phase. | 6 | Yes | To 31st July 2025. Plus four months to 31st Nov for study extension | Framework Analysis meetings (4) Stakeholder workshop planning PPIE-AG meeting 12 Stakeholder workshop PPI impact meetings (x2) PPIE-AG meeting 13 PPIE-AG meeting 14 (with lunch) Parent Action community lunch | 2025 2025 June 2025 July 2025 Sept 2025 Oct 2025 Sept 2025 Sept 2025 Oct | Small group discussion (Dylan, Tania, CTC, RA) to create and revise coding categories from the interview data. Small group discussion (Lola, Tanjida, Michelle, Siobhean, RA, PPI lead) & Harriet Boulding of KCL Policy Institute. Welcome; presentation by CTC: results of the RCT & interviews/framework analysis on acceptability; messages. Participative small group work 24 stakeholders. Four PPI advisers invited: Omar, Abigail, Siobhean, Simi. One lunchtime and one evening meeting for PPI advisers to discuss their views on PPI impact (11 attended). Welcome; feedback on stakeholder workshop; planning publications on RCT, acceptability and PPI articles. Welcome, to first face-to-face meeting! Presentations, sharing experiences, next steps opportunities and plans. Welcome and intros, ‘you said, we did’; results of study; stakeholders’ ideas; PPI in publications (Michele). |