## ASSY BOP V1
Process Planning Rule Matrix Type ">" if the process in row 4 has to be done after the process listed in column F ; Type ">=" if the process in row 4 is the follwing step of the process listed in column F; Type "<" if the process in row 4 has to be done before the process listed in column F ; |  | type |  |  |  | A | A | A | A | M | M | M | M | M | M | M | M | M | M | M | A | M | M | M | M | A | A | A | M | A | A | M | M | M | M | A | A | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | A | M | M | M | M | M | M | M | M | A | A | M | M | M | M | M | M | A | A | M | M | M | M | M | A | A | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | A | A | M | M | M | M | M | M | M | M | M | A | A | M | M | M | A | A | M | M | M | M | M | M | M | M | M | M | M | A | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | A | M | M | M | M | M | M | A | M | M | M | M | M | M | M | M | A | A | M | M | M | M | M | M | M | M | M | M | M | M | M | M | A | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | A | A | A | A | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | A | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | A | M | M | M | M | M | M | M | M
|  | Process |  |  |  | Load BLOCK ASM-ENG Press PIN-CR/SHF RR OIL SEAL HSG LOC Press PIN-CYL HD LOC Press PIN-ENG FRT CVR LOC Press PIN-STRTR LOC | Stamp BLOCK ASM-ENG Rotate BLOCK ASM-ENG | Loosen BOLT/SCREW-CR/SHF BRG CAP Separate CAP-CR/SHF BRG Lay CAP-CR/SHF BRG to kit tray | Vacuum to clean the BLOCK ASM-ENG bearing hole | Scan BLOCK ASM-ENG level code | Lubricate VALVE ASM-OIL FLOW CHK | Install VALVE ASM-OIL FLOW CHK | Install NOZZLE ASM-PSTN OIL | Pre-tighten NOZZLE ASM-PSTN OIL | Tighten NOZZLE ASM-PSTN OIL | Install BEARING-CR/SHF UPR | Lubricate BEARING-CR/SHF UPR | Load CRANKSHAFT-(MCHG) | Scan CRANKSHAFT-(MCHG) 2D code | Scan CRANKSHAFT-(MCHG) level code | Lubricate CRANKSHAFT-(MCHG) | Install BEARING-CR/SHF LWR | Install BEARING-CR/SHF THR | Install CAP-CR/SHF BRG | Pre-tighten BOLT/SCREW-CR/SHF BRG CAP | Tighten BOLT/SCREW-CR/SHF BRG CAP | TTT 1 | lubricate BLOCK ASM-ENG bore Scan PISTON ASM-(W/ CONN ROD) 2D code check the orientation of PISTON ASM-(W/ CONN ROD) | Install PISTON ASM-(W/ CONN ROD) | Tighten the BOLT/SCREW-CONN ROD | TTT 2 | Wipping EXTENSION ASM-LWR C/CASE | Scan EXTENSION ASM-LWR C/CASE 2D code | Load EXTENSION ASM-LWR C/CASE | Install BOLT/SCREW-LWR C/CASE EXTN | Press PIN-LWR C/CASE EXTN Press PIN-LWR C/CASE LOC Plasma EXTENSION ASM-LWR C/CASE RTV SEALER-LWR C/CASE EXTN Plasma BLOCK ASM-ENG（LCE surface） Install EXTENSION ASM-LWR C/CASE | Tighten BOLT/SCREW-LWR C/CASE EXTN | Install PIN-BALR SHF HSG LOC | Install SPROCKET-BALR SHF | Install CHAIN ASM-BALR | Install BOLT/SCREW-BALR SHF SPKT | Install GUIDE-BALR CHAIN | Pre-tighten BOLT/SCREW-BALR CHAIN GDE | Install TENSIONER ASM-BALR CHAIN | Pre-tighten BOLT/SCREW-BALR CHAIN TENSR | Tighten BOLT/SCREW-BALR CHAIN GDE | Tighten BOLT/SCREW-BALR CHAIN TENSR | Remove the lock pin of the tensioner | Remove PIN-BALR SHF HSG LOC | Install SCREEN ASM-O/PMP (W/ SUC PIPE) | Pre-tighten BOLT/SCREW-O/PMP SUC PIPE | Tighten BOLT/SCREW-O/PMP SUC PIPE | Install BRACKET-AUX W/PMP | Pre-tighten BOLT/SCREW-AUX W/PMP BRKT | Tighten BOLT/SCREW-AUX W/PMP BRKT | Plasma PAN ASM-LWR OIL RTV PAN ASM-LWR OIL Plasma EXTENSION ASM-LWR C/CASE（oil pan surface） | Load PAN ASM-LWR OIL | Install guide tool of PAN ASM-LWR OIL | Install PAN ASM-LWR OIL on to engine | Install BOLT/SCREW-OIL PAN | Remove guide tool of PAN ASM-LWR OIL | Pre-tighten BOLT/SCREW-OIL PAN | Install COOLER ASM-ENG OIL | Pre-tighten BOLT/SCREW-ENG OIL CLR | Tighten BOLT/SCREW-OIL PAN | Plasma COVER ASM-PCV OIL SEP RTV COVER ASM-PCV OIL SEP Plasma BLOCK ASM-ENG（oil seperator surface） | Load COVER ASM-PCV OIL SEP | Install guide tool of COVER ASM-PCV OIL SEP | Install COVER ASM-PCV OIL SEP | Remove guide tool of COVER ASM-PCV OIL SEP | Pre-tighten BOLT/SCREW-PCV OIL SEP CVR | Install VALVE ASM-OIL FLTR BYPASS | Tighten BOLT/SCREW-PCV OIL SEP CVR Tighten BOLT/SCREW-BALR SHF SPKT | RTV HOUSING ASM-CR/SHF RR OIL SEAL Plasma BLOCK ASM-ENG（Rear seal surface） | Load HOUSING ASM-CR/SHF RR OIL SEAL | Install guide tool of HOUSING ASM-CR/SHF RR OIL SEAL | Install HOUSING ASM-CR/SHF RR OIL SEAL | Remove guide tool of HOUSING ASM-CR/SHF RR OIL SEAL | Pre-tighten BOLT/SCREW-CR/SHF RR OIL SEAL HSG | Tighten BOLT/SCREW-CR/SHF RR OIL SEAL HSG | Real seal Leak Test | Scan PUMP ASM-WAT 2D Code | Install PUMP ASM-WAT | Pre-tighten BOLT/SCREW-W/PMP | Tighten BOLT/SCREW-W/PMP | Tighten VALVE ASM-OIL FLTR BYPASS | Install COVER-W/PMP | Pre-tighten BOLT/SCREW-W/PMP CVR | Tighten BOLT/SCREW-W/PMP CVR | Install SENSOR ASM-CR/SHF POSN | Tighten BOLT/SCREW-CR/SHF POSN SEN | Tighten BOLT/SCREW-ENG OIL CLR | Install GASKET-WAT INL | Install PIPE ASM-ENG COOL THERM HSG INL | Pre-tighten BOLT/SCREW-ENG COOL THERM HSG | Pre-tighten BOLT/SCREW-ENG COOL THERM HSG BRKT | Remove CLAMP ASM-W/PMP OTLT HOSE | Install FILTER ASM-OIL | Press PIN-FLYWHL LOC | Install RING-CR/SHF POSN SEN INR EXCITER | Install PLATE ASM-A/TRNS FLEX | Pre-tighten BOLT/SCREW-A/TRNS FLEX PLT | Tighten BOLT/SCREW-A/TRNS FLEX PLT Tighten FILTER ASM-OIL | Rotate BLOCK ASM-ENG 180deg | Install GASKET-CYL HD | Scan HEAD ASM-CYL (W/ VLV) 2D code | Install HEAD ASM-CYL (W/ VLV) | Install BOLT/SCREW-CYL HD | Rub engine stamp | Install SENSOR ASM-ENG OIL TEMP | Tighten SENSOR ASM-ENG OIL TEMP | Tighten BOLT/SCREW-ENG COOL THERM HSG | Tighten BOLT/SCREW-ENG COOL THERM HSG BRKT | Tighten BOLT/SCREW-CYL HD（Inner） Tighten BOLT/SCREW-CYL HD（outer） | Static Spark Plug Test | Install ADJUSTER-HYD VLV LASH | Lubricte ADJUSTER-HYD VLV LASH | Install ARM ASM-VLV RKR | Lubricate ARM ASM-VLV RKR | Plasma CARRIER-CM/SHF Plasma GASKET-CM/SHF CVR T-joint Plasma BLOCK ASM-ENG T-joint RTV GASKET-CM/SHF CVR T-joint | Load CARRIER-CM/SHF | Scan CARRIER-CM/SHF 2D code | Load GASKET-CM/SHF CVR | Install GASKET-CM/SHF CVR | Install Lock tool of camshaft | Install guide tool of CARRIER-CM/SHF | Install CARRIER-CM/SHF | Remove guide tool of CARRIER-CM/SHF | Install Lock tool of crankshaft | Install BOLT/SCREW-CM/SHF CVR | Install STUD-CM/SHF CVR | Tighten BOLT/SCREW-CM/SHF CVR Tighten STUD-CM/SHF CVR | Remove the extra RTV | Install SEAL-CR/SHF FRT (O RING) | Install TENSIONER ASM-TMG CHAIN | Pre-tighten BOLT/SCREW-TMG CHAIN TENSR | Tighten BOLT/SCREW-TMG CHAIN TENSR | Install GUIDE ASM-TMG CHAIN(left) | Pre-tighten BOLT/SCREW-TMG CHAIN GDE(left) | Tighten BOLT/SCREW-TMG CHAIN GDE(left) | Install GUIDE ASM-TMG CHAIN(right) | Pre-tighten BOLT/SCREW-TMG CHAIN GDE(right) | Tighten BOLT/SCREW-TMG CHAIN GDE(right) | Install SPROCKET-CR/SHF | Install SPROCKET ASM-CM/SHF EXH (W/CM/SHF POSN ACTR) | Pre-tighten BOLT/SCREW-CM/SHF SPKT (W/ ACTR VLV) | Install CHAIN ASM-TMG | Install SPROCKET ASM-CM/SHF INT (W/CM/SHF POSN ACTR) | Pre-tighten BOLT/SCREW-CM/SHF SPKT (W/ ACTR VLV) | Install GUIDE ASM-TMG CHAIN | Release the lock pin of TENSIONER ASM-TMG CHAIN | Tighten BOLT/SCREW-CM/SHF SPKT (W/ ACTR VLV) | Remove Lock tool of camshaft | Remove Lock tool of crankshaft | Install PLUG-CM/SHF CVR OPG | Tighten PLUG-CM/SHF CVR OPG | Install SEPARATOR ASM-PCV OIL | Pre-tighten BOLT/SCREW-PCV OIL SEP | Plasma BLOCK ASM-ENG （Front cover surface） RTV COVER ASM-ENG FRT | Load COVER ASM-ENG FRT | Install COVER ASM-ENG FRT | Pre-tighten BOLT/SCREW-ENG FRT CVR | Scan COVER ASM-TMG BELT UPR FRT 2D code | Install COVER ASM-TMG BELT UPR FRT | Pre-tighten BOLT/SCREW-TMG BELT UPR CVR | Install SOLENOID ASM-CM/SHF POSN ACTR VLV | Pre-tighten BOLT/SCREW-CM/SHF POSN ACTR VLV SOL | Tighten BOLT/SCREW-ENG FRT CVR Tighten BOLT/SCREW-TMG BELT UPR CVR Tighten BOLT/SCREW-PCV OIL SEP | Lubricate LUBRICANT-VALVE LIFTER BORE | Install FOLLOWER ASM-VLV LFTR | Scan PUMP ASM-FUEL 2D code | Install PUMP ASM-FUEL | Pre-tighten BOLT/SCREW-F/PMP | Scan RAIL ASM-DIR F/INJN FUEL W/ F/INJN WRG HARN 2D code | Install RAIL ASM-DIR F/INJN FUEL W/ F/INJN WRG HARN | Pre-tighten BOLT/SCREW-F/INJN FUEL RL | Tighten BOLT/SCREW-CM/SHF POSN ACTR VLV SOL | Scan BALANCER ASM-CR/SHF 2D code | Install BALANCER ASM-CR/SHF | Pre-tighten BOLT/SCREW-CR/SHF BALR | Install SENSOR ASM-KNOCK | Tighten BOLT/SCREW-KNOCK SEN | Connect the harness of Knock Sensor | Tighten BOLT/SCREW-CR/SHF BALR Tighten BOLT/SCREW-F/PMP Press RAIL ASM-DIR F/INJN FUEL W/ F/INJN WRG HARN Tighten BOLT/SCREW-F/INJN FUEL RL | Scan PIPE ASM-FUEL FEED INTER 2D code | Install PIPE ASM-FUEL FEED INTER | Tighten PIPE ASM-FUEL FEED INTER | Tighten BOLT/SCREW-F/INJN FUEL FEED PIPE | Install COIL ASM-IGN | Pre-tighten BOLT/SCREW-IGN COIL | Tighten BOLT/SCREW-IGN COIL | Install BRACKET-ENG LIFT RR(2) | Pre-tighten BOLT/SCREW-ENG LIFT BRKT | Tighten BOLT/SCREW-ENG LIFT BRKT | Install SENSOR ASM-ENG COOL TEMP | Tighten SENSOR ASM-ENG COOL TEMP | Conect harness of SENSOR ASM-ENG COOL TEMP | Install hansen fitting | Install process seal | Tighten Hasen fitting | Tighten Process seal bolt | Install SENSOR ASM-ENG OIL PRESS | Tighten SENSOR ASM-ENG OIL PRESS | Re-tighten PIPE ASM-FUEL FEED INTER | Heliem Test | Long block leak test | Oil filling | Cold Test | Install INSULATOR-F/INJN FUEL RL | Scan VALVE ASM-ENG COOL FLOW CONT 2D code | Install VALVE ASM-ENG COOL FLOW CONT | Pre-tighten BOLT/SCREW-ENG COOL FLOW CONT VLV | Install GASKET-TURBO OIL FEED PIPE | Install PIPE ASM-ENG COOL AIR BL | Pre-tighten BOLT/SCREW-ENG COOL AIR BL PIPE | Tighten BOLT/SCREW-ENG COOL FLOW CONT VLV | Tighten BOLT/SCREW-ENG COOL AIR BL PIPE | Scan PIPE ASM-ENG COOL HTR EXH 2D code | Install GASKET-ENG COOL MANIF | Install PIPE ASM-ENG COOL HTR EXH | Pre-tighten BOLT/SCREW-ENG COOL HTR EXH PIPE | Tighten BOLT/SCREW-ENG COOL HTR EXH PIPE | Install HOSE ASM-THERM BYPASS | Pre-tighten BOLT/SCREW-THERM BYPASS PIPE | Tighten BOLT/SCREW-THERM BYPASS PIPE | Install BOLT/SCREW-ENG COOL AIR BL PIPE | Tighten BOLT/SCREW-ENG COOL AIR BL PIPE | Install BOLT/SCREW-ENG COOL HTR EXH PIPE BRKT | Tighten BOLT/SCREW-ENG COOL HTR EXH PIPE BRKT | Scan MANIFOLD ASM-INT (W/ THROT BODY) 2D code | Scan BODY ASM-THROT (W/ SEN) 2D code | Scan ADAPTER ASM-THROT BODY 2D code | Install MANIFOLD ASM-INT (W/ THROT BODY) | Pre-tighten BOLT/SCREW-INT MANIF | Connect PIPE ASM-ENG COOL AIR BL & PIPE ASM-ENG COOL HTR EXH to cooler controler | Connect HOSE ASM-THERM BYPASS to cooler controler | Remove the clamps | Lubricate INDICATOR ASM-OIL LVL (W/ IND TUBE) | Install INDICATOR ASM-OIL LVL (W/ IND TUBE) | Pre-tighten BOLT/SCREW-OIL LVL IND TUBE BRKT | Blow by the hansen fitting | Remove the hansen fitting | Remove the seal | Install SENSOR ASM-ENG OIL PRESS | Tighten SENSOR ASM-ENG OIL PRESS | Install CAP ASM-OIL FIL | Install guide tool of turbo | Install SHIELD ASM-TURBO HT | Pre-tighten BOLT/SCREW-TURBO H/SHLD | Scan TURBOCHARGER ASM-CMPR AIR INT 2D code | Install TURBOCHARGER ASM-CMPR AIR INT | Pre-tighten BOLT/SCREW-TURBO | Remove guide tool of turbo | Install GASKET-TURBO OIL FEED PIPE | Pre-tighten BOLT/SCREW-TURBO OIL FEED PIPE | Install SHIELD-CM/SHF CVR HT | Pre-tighten BOLT/SCREW-CM/SHF CVR HT SHLD | Tighten BOLT/SCREW-TURBO H/SHLD | Install HARNESS ASM-ENG WRG | Tighten BOLT/SCREW-TURBO Tighten BOLT/SCREW-INT MANIF | Install GASKET-TURBO COOL FEED & RTN PIPE | Lubricate PIPE ASM-TURBO COOL FEED & RTN | Install PIPE ASM-TURBO COOL FEED & RTN | Pre-tighten BOLT/SCREW-TURBO COOL FEED & RTN PIPE | Pre-tighten BOLT/SCREW-TURBO COOL FEED PIPE BRKT | Remove the clamp of the pipe | Pre-tighten STUD-TURBO H/SHLD | Tighten STUD-TURBO H/SHLD | Install HOSE-PCV | Pre-tighten BOLT/SCREW-PCV HOSE CONN | Tighten BOLT/SCREW-PCV HOSE CONN | Install ADAPTER-CHRG AIR CLR INL AIR HOSE | Pre-tighten BOLT/SCREW-CHRG AIR CLR INL AIR HOSE | Tighten BOLT/SCREW-CHRG AIR CLR INL AIR HOSE | Scan PUMP ASM-EVAP EMIS CNSTR PURGE 2D code | Install PUMP ASM-EVAP EMIS CNSTR PURGE | Pre-tighten BOLT/SCREW-EVAP EMIS CNSTR PURGE PUMP | Tighten BOLT/SCREW-EVAP EMIS CNSTR PURGE PUMP | Install INSULATOR-F/PMP | Install BRACKET-ENG WRG HARN | Pre-tighten NUT-ENG WRG HARN BRKT | Tighten BOLT/SCREW-OIL LVL IND TUBE BRKT | Install COVER-F/PMP | Pre-tighten BOLT/SCREW-F/PMP SHLD | Tighten BOLT/SCREW-F/PMP SHLD | Tighten BOLT/SCREW-TURBO COOL FEED & RTN PIPE | Tighten BOLT/SCREW-TURBO COOL FEED PIPE BRKT | Final water cavity leak test | Print LABEL-ENG TRACEABILITY | Scan LABEL-ENG TRACEABILITY | Paste LABEL-ENG TRACEABILITY | Print LABEL-ENG MFG ORIGIN | Paste LABEL-ENG MFG ORIGIN | care | loosen adapter bolts | Unload ENGINE ASM-GASOLINE
type | Process | Orient | Orient | CT
A | Load BLOCK ASM-ENG Press PIN-CR/SHF RR OIL SEAL HSG LOC Press PIN-CYL HD LOC Press PIN-ENG FRT CVR LOC Press PIN-STRTR LOC | PRD-FRT | FRT | 66 | 1
A | Stamp BLOCK ASM-ENG Rotate BLOCK ASM-ENG | PRD-FRT | FRT | 66 | 2 | >
A | Loosen BOLT/SCREW-CR/SHF BRG CAP Separate CAP-CR/SHF BRG Lay CAP-CR/SHF BRG to kit tray | PRU-FRT | FRT | 66 | 3 |  | >
A | Vacuum to clean the BLOCK ASM-ENG bearing hole | PRU-FRT | FRT | 66 | 4 |  |  | >
M | Scan BLOCK ASM-ENG level code | PRU-FRT | FRT | 3 | 5 |  |  |  | >
M | Lubricate VALVE ASM-OIL FLOW CHK | PRU-INT | INT | 3 |  |  |  |  | >
M | Install VALVE ASM-OIL FLOW CHK | PRU-INT | INT | 5 | [6 empty] | >=
M | Install NOZZLE ASM-PSTN OIL | PRU-INT | INT | 15 |  |  |  |  | >
M | Pre-tighten NOZZLE ASM-PSTN OIL | PRU-INT | INT | 15 | [8 empty] | >=
M | Tighten NOZZLE ASM-PSTN OIL | PRU-INT | INT | 15 | [9 empty] | >
M | Install BEARING-CR/SHF UPR | PRU-INT | INT | 25 | 6 |  |  |  |  | >
M | Lubricate BEARING-CR/SHF UPR | PRU-INT | INT | 10 | [11 empty] | >
M | Load CRANKSHAFT-(MCHG) | PRU-INT | INT | 15 | [10 empty] | > |  | >
M | Scan CRANKSHAFT-(MCHG) 2D code | PRU-INT | INT | 3 | [13 empty] | >=
M | Scan CRANKSHAFT-(MCHG) level code | PRU-INT | INT | 3 | [14 empty] | >=
A | Lubricate CRANKSHAFT-(MCHG) | PRU-INT | INT | 66 | 7 | [13 empty] | > | >
M | Install BEARING-CR/SHF LWR | PRU-INT | INT | 25 | 8 | [15 empty] | >
M | Install BEARING-CR/SHF THR | PRU-INT | INT | 5 | [16 empty] | >
M | Install CAP-CR/SHF BRG | PRU-INT | INT | 15 | [17 empty] | > | >
M | Pre-tighten BOLT/SCREW-CR/SHF BRG CAP | PRU-INT | INT | 10 | [19 empty] | >
A | Tighten BOLT/SCREW-CR/SHF BRG CAP | PRU-FRT | FRT | 66 | 9 | [6 empty] | > | [12 empty] | >
A | TTT 1 | PRU-FRT | FRT | 66 | 10 | [20 empty] | >
A | lubricate BLOCK ASM-ENG bore Scan PISTON ASM-(W/ CONN ROD) 2D code check the orientation of PISTON ASM-(W/ CONN ROD) | PRU-FRT | FRT | 66 | 11 | [21 empty] | >
M | Install PISTON ASM-(W/ CONN ROD) | PRU-FRT | FRT | 63 | 12 | [22 empty] | >
A | Tighten the BOLT/SCREW-CONN ROD | PRU-FRT | FRT | 66 | 13 | [23 empty] | >
A | TTT 2 | PRU-FRT | FRT | 66 | 14 | [24 empty] | >
M | Wipping EXTENSION ASM-LWR C/CASE | PRU-FRT | FRT | 15 | 15 | [25 empty] | >
M | Scan EXTENSION ASM-LWR C/CASE 2D code | PRU-FRT | FRT | 3 | [27 empty] | >
M | Load EXTENSION ASM-LWR C/CASE | PRU-FRT | FRT | 20 | [28 empty] | >=
M | Install BOLT/SCREW-LWR C/CASE EXTN | PRU-FRT | FRT | 20 | [29 empty] | >=
A | Press PIN-LWR C/CASE EXTN Press PIN-LWR C/CASE LOC Plasma EXTENSION ASM-LWR C/CASE RTV SEALER-LWR C/CASE EXTN Plasma BLOCK ASM-ENG（LCE surface） Install EXTENSION ASM-LWR C/CASE | PRU-FRT | FRT | 66 | 16 | [29 empty] | >=
A | Tighten BOLT/SCREW-LWR C/CASE EXTN | PRU-FRT | FRT | 66 | 17 | [30 empty] | >
M | Install PIN-BALR SHF HSG LOC | PRU-REAR | REAR | 5 | 18 | [31 empty] | >
M | Install SPROCKET-BALR SHF | PRU-REAR | REAR | 8 | [33 empty] | >
M | Install CHAIN ASM-BALR | PRU-REAR | REAR | 10 | [34 empty] | >
M | Install BOLT/SCREW-BALR SHF SPKT | PRU-REAR | REAR | 5 | [34 empty] | >
M | Install GUIDE-BALR CHAIN | PRU-REAR | REAR | 10 | [35 empty] | >
M | Pre-tighten BOLT/SCREW-BALR CHAIN GDE | PRU-REAR | REAR | 5 | [37 empty] | >=
M | Install TENSIONER ASM-BALR CHAIN | PRU-REAR | REAR | 12 | [35 empty] | >
M | Pre-tighten BOLT/SCREW-BALR CHAIN TENSR | PRU-REAR | REAR | 5 | [39 empty] | >=
M | Tighten BOLT/SCREW-BALR CHAIN GDE | PRU-REAR | REAR | 6 | 19 | [37 empty] | >
M | Tighten BOLT/SCREW-BALR CHAIN TENSR | PRU-REAR | REAR | 6 | [40 empty] | >
M | Remove the lock pin of the tensioner | PRU-REAR | REAR | 3 | [36 empty] | > |  |  |  |  | > | >
M | Remove PIN-BALR SHF HSG LOC | PRU-REAR | REAR | 3 | [36 empty] | > |  |  |  |  | > | >
M | Install SCREEN ASM-O/PMP (W/ SUC PIPE) | PRU-REAR | REAR | 8 | [44 empty] | >
M | Pre-tighten BOLT/SCREW-O/PMP SUC PIPE | PRU-REAR | REAR | 5 | [45 empty] | >=
M | Tighten BOLT/SCREW-O/PMP SUC PIPE | PRU-REAR | REAR | 8 | [46 empty] | >
M | Install BRACKET-AUX W/PMP | PRU-INT | INT | 8 | [32 empty] | >
M | Pre-tighten BOLT/SCREW-AUX W/PMP BRKT | PRU-INT | INT | 5 | [48 empty] | >=
M | Tighten BOLT/SCREW-AUX W/PMP BRKT | PRU-INT | INT | 8 | [49 empty] | >
A | Plasma PAN ASM-LWR OIL RTV PAN ASM-LWR OIL Plasma EXTENSION ASM-LWR C/CASE（oil pan surface） | PRU-FRT | FRT | 66 | 20 | [42 empty] | > |  |  |  | >
M | Load PAN ASM-LWR OIL | PRU-INT | INT | 15 | 21 | [50 empty] | >=
M | Install guide tool of PAN ASM-LWR OIL | PRU-INT | INT | 5 | [52 empty] | >
M | Install PAN ASM-LWR OIL on to engine | PRU-INT | INT | 20 | [53 empty] | >
M | Install BOLT/SCREW-OIL PAN | PRU-INT | INT | 15 | [54 empty] | >
M | Remove guide tool of PAN ASM-LWR OIL | PRU-INT | INT | 5 | [55 empty] | >
M | Pre-tighten BOLT/SCREW-OIL PAN | PRU-INT | INT | 25 | 22 | [55 empty] | >
M | Install COOLER ASM-ENG OIL | PRU-INT | INT | 15 | [32 empty] | > | [14 empty] | >
M | Pre-tighten BOLT/SCREW-ENG OIL CLR | PRU-INT | INT | 15 | [58 empty] | >=
A | Tighten BOLT/SCREW-OIL PAN | PRU-FRT | FRT | 66 | 23 | [56 empty] | >
A | Plasma COVER ASM-PCV OIL SEP RTV COVER ASM-PCV OIL SEP Plasma BLOCK ASM-ENG（oil seperator surface） | PRU-FRT | FRT | 66 | 24 | [31 empty] | >
M | Load COVER ASM-PCV OIL SEP | PRU-INT | INT | 10 | 25 | [60 empty] | >=
M | Install guide tool of COVER ASM-PCV OIL SEP | PRU-INT | INT | 5 | [62 empty] | >
M | Install COVER ASM-PCV OIL SEP | PRU-INT | INT | 15 | [63 empty] | >
M | Remove guide tool of COVER ASM-PCV OIL SEP | PRU-INT | INT | 5 | [64 empty] | >
M | Pre-tighten BOLT/SCREW-PCV OIL SEP CVR | PRU-INT | INT | 10 | [65 empty] | >
M | Install VALVE ASM-OIL FLTR BYPASS | PRU-INT | INT | 15 | [32 empty] | >
A | Tighten BOLT/SCREW-PCV OIL SEP CVR Tighten BOLT/SCREW-BALR SHF SPKT | PRU-FRT | FRT | 66 | 26 | [35 empty] | > | [29 empty] | >
A | RTV HOUSING ASM-CR/SHF RR OIL SEAL Plasma BLOCK ASM-ENG（Rear seal surface） | PRU-FRT | FRT | 66 | 27 | [43 empty] | > | [23 empty] | >
M | Load HOUSING ASM-CR/SHF RR OIL SEAL | PRU-Rear | Rear | 11 | 28 | [68 empty] | >=
M | Install guide tool of HOUSING ASM-CR/SHF RR OIL SEAL | PRU-Rear | Rear | 8 | [70 empty] | >
M | Install HOUSING ASM-CR/SHF RR OIL SEAL | PRU-Rear | Rear | 15 | [71 empty] | >
M | Remove guide tool of HOUSING ASM-CR/SHF RR OIL SEAL | PRU-Rear | Rear | 3 | [72 empty] | >
M | Pre-tighten BOLT/SCREW-CR/SHF RR OIL SEAL HSG | PRU-Rear | Rear | 20 | [73 empty] | >
A | Tighten BOLT/SCREW-CR/SHF RR OIL SEAL HSG | PRU-FRT | FRT | 66 | 29 | [73 empty] | >
A | Real seal Leak Test | PRU-FRT | FRT | 66 | 30 | [74 empty] | >
M | Scan PUMP ASM-WAT 2D Code | PRU-INT | INT | 3 | 31 | [49 empty] | >
M | Install PUMP ASM-WAT | PRU-INT | INT | 10 | [77 empty] | >=
M | Pre-tighten BOLT/SCREW-W/PMP | PRU-INT | INT | 8 | [78 empty] | >=
M | Tighten BOLT/SCREW-W/PMP | PRU-INT | INT | 10 | [79 empty] | >
M | Tighten VALVE ASM-OIL FLTR BYPASS | PRU-INT | INT | 8 | [67 empty] | >
M | Install COVER-W/PMP | PRU-INT | INT | 8 | [80 empty] | >
M | Pre-tighten BOLT/SCREW-W/PMP CVR | PRU-INT | INT | 5 | [82 empty] | >=
M | Tighten BOLT/SCREW-W/PMP CVR | PRU-INT | INT | 8 | [83 empty] | >
M | Install SENSOR ASM-CR/SHF POSN | PRU-INT | INT | 8 | 32 |  |  |  |  | >
M | Tighten BOLT/SCREW-CR/SHF POSN SEN | PRU-INT | INT | 5 | [85 empty] | >
M | Tighten BOLT/SCREW-ENG OIL CLR | PRU-INT | INT | 15 | [59 empty] | >
M | Install GASKET-WAT INL | PRU-EXH | EXH | 5 | [60 empty] | > | [23 empty] | >
M | Install PIPE ASM-ENG COOL THERM HSG INL | PRU-EXH | EXH | 10 | [88 empty] | >
M | Pre-tighten BOLT/SCREW-ENG COOL THERM HSG | PRU-EXH | EXH | 5 | [89 empty] | >=
M | Pre-tighten BOLT/SCREW-ENG COOL THERM HSG BRKT | PRU-EXH | EXH | 3 | [90 empty] | >=
M | Remove CLAMP ASM-W/PMP OTLT HOSE | PRU-EXH | EXH | 5 | [90 empty] | > | >
M | Install FILTER ASM-OIL | PRU-INT | INT | 10 | 33 | [80 empty] | >
M | Press PIN-FLYWHL LOC | PRU-Rear | Rear | 5 | [76 empty] | >
M | Install RING-CR/SHF POSN SEN INR EXCITER | PRU-Rear | Rear | 3 | [94 empty] | >
M | Install PLATE ASM-A/TRNS FLEX | PRU-Rear | Rear | 20 | [95 empty] | >
M | Pre-tighten BOLT/SCREW-A/TRNS FLEX PLT | PRU-Rear | Rear | 20 | [96 empty] | >=
A | Tighten BOLT/SCREW-A/TRNS FLEX PLT Tighten FILTER ASM-OIL | PRU-FRT | FRT | 66 | 34 | [92 empty] | > |  |  |  | >
A | Rotate BLOCK ASM-ENG 180deg | PRD-FRT | FRT | 66 | 35 | [85 empty] | > | > |  |  |  |  | > | [5 empty] | >
M | Install GASKET-CYL HD | PRD-EXH | EXH | 5 | 36 | [98 empty] | >
M | Scan HEAD ASM-CYL (W/ VLV) 2D code | PRD-EXH | EXH | 3 | [100 empty] | >
M | Install HEAD ASM-CYL (W/ VLV) | PRD-EXH | EXH | 35 | [101 empty] | >=
M | Install BOLT/SCREW-CYL HD | PRD-EXH | EXH | 15 | [102 empty] | >
M | Rub engine stamp | PRD-EXH | EXH | 30 | 37 |  | > | [96 empty] | >
M | Install SENSOR ASM-ENG OIL TEMP | PRD-EXH | EXH | 10 | [99 empty] | >
M | Tighten SENSOR ASM-ENG OIL TEMP | PRD-EXH | EXH | 8 | [105 empty] | >
M | Tighten BOLT/SCREW-ENG COOL THERM HSG | PRD-EXH | EXH | 8 | [90 empty] | >
M | Tighten BOLT/SCREW-ENG COOL THERM HSG BRKT | PRD-EXH | EXH | 5 | [91 empty] | >
A | Tighten BOLT/SCREW-CYL HD（Inner） Tighten BOLT/SCREW-CYL HD（outer） | PRD-FRT | FRT | 66 | 38 | [102 empty] | >
A | Static Spark Plug Test | PRD-FRT | FRT | 66 | 39 | [108 empty] | >
M | Install ADJUSTER-HYD VLV LASH | PRD-EXH | EXH | 25 | 40 | [109 empty] | >
M | Lubricte ADJUSTER-HYD VLV LASH | PRD-EXH | EXH | 10 | [111 empty] | >
M | Install ARM ASM-VLV RKR | PRD-EXH | EXH | 25 | [112 empty] | >
M | Lubricate ARM ASM-VLV RKR | PRD-EXH | EXH | 63 | 41 | [112 empty] | >
A | Plasma CARRIER-CM/SHF Plasma GASKET-CM/SHF CVR T-joint Plasma BLOCK ASM-ENG T-joint RTV GASKET-CM/SHF CVR T-joint | PRD-FRT | FRT | 66 | 42 | [113 empty] | >
M | Load CARRIER-CM/SHF | PRD-INT | INT | 7 | 43 | [114 empty] | >=
M | Scan CARRIER-CM/SHF 2D code | PRD-INT | INT | 3 | [116 empty] | >=
M | Load GASKET-CM/SHF CVR | PRD-INT | INT | 3 | [117 empty] | >
M | Install GASKET-CM/SHF CVR | PRD-INT | INT | 8 | [118 empty] | >=
M | Install Lock tool of camshaft | PRD-INT | INT | 3 | [119 empty] | >
M | Install guide tool of CARRIER-CM/SHF | PRD-INT | INT | 3 | [120 empty] | >
M | Install CARRIER-CM/SHF | PRD-INT | INT | 9 | [121 empty] | >
M | Remove guide tool of CARRIER-CM/SHF | PRD-INT | INT | 3 | [122 empty] | >
M | Install Lock tool of crankshaft | PRD-INT | INT | 3 | [123 empty] | >
M | Install BOLT/SCREW-CM/SHF CVR | PRD-INT | INT | 12 | [124 empty] | >
M | Install STUD-CM/SHF CVR | PRD-INT | INT | 5 | [125 empty] | >
A | Tighten BOLT/SCREW-CM/SHF CVR Tighten STUD-CM/SHF CVR | PRD-FRT | FRT | 66 | 44 | [124 empty] | > | >
M | Remove the extra RTV | PRD-FRT | FRT | 3 | 45 | [126 empty] | >
M | Install SEAL-CR/SHF FRT (O RING) | PRD-FRT | FRT | 10 | [128 empty] | >
M | Install TENSIONER ASM-TMG CHAIN | PRD-FRT | FRT | 7 | [129 empty] | >
M | Pre-tighten BOLT/SCREW-TMG CHAIN TENSR | PRD-FRT | FRT | 6 | [130 empty] | >=
M | Tighten BOLT/SCREW-TMG CHAIN TENSR | PRD-FRT | FRT | 6 | [131 empty] | >
M | Install GUIDE ASM-TMG CHAIN(left) | PRD-FRT | FRT | 7 | [129 empty] | >
M | Pre-tighten BOLT/SCREW-TMG CHAIN GDE(left) | PRD-FRT | FRT | 4 | [133 empty] | >=
M | Tighten BOLT/SCREW-TMG CHAIN GDE(left) | PRD-FRT | FRT | 4 | [134 empty] | >
M | Install GUIDE ASM-TMG CHAIN(right) | PRD-FRT | FRT | 7 | [129 empty] | >
M | Pre-tighten BOLT/SCREW-TMG CHAIN GDE(right) | PRD-FRT | FRT | 4 | [136 empty] | >=
M | Tighten BOLT/SCREW-TMG CHAIN GDE(right) | PRD-FRT | FRT | 4 | [137 empty] | >
M | Install SPROCKET-CR/SHF | PRD-FRT | FRT | 8 | 46 | [128 empty] | >
M | Install SPROCKET ASM-CM/SHF EXH (W/CM/SHF POSN ACTR) | PRD-FRT | FRT | 8 | [129 empty] | >
M | Pre-tighten BOLT/SCREW-CM/SHF SPKT (W/ ACTR VLV) | PRD-FRT | FRT | 5 | [140 empty] | >=
M | Install CHAIN ASM-TMG | PRD-FRT | FRT | 15 | [131 empty] | > |  |  | > |  |  | > |  | > |  | >
M | Install SPROCKET ASM-CM/SHF INT (W/CM/SHF POSN ACTR) | PRD-FRT | FRT | 8 | [142 empty] | >
M | Pre-tighten BOLT/SCREW-CM/SHF SPKT (W/ ACTR VLV) | PRD-FRT | FRT | 5 | [143 empty] | >=
M | Install GUIDE ASM-TMG CHAIN | PRD-FRT | FRT | 8 | [144 empty] | >
M | Release the lock pin of TENSIONER ASM-TMG CHAIN | PRD-FRT | FRT | 5 | [145 empty] | >
A | Tighten BOLT/SCREW-CM/SHF SPKT (W/ ACTR VLV) | PRD-FRT | FRT | 66 | 47 | [143 empty] | >
M | Remove Lock tool of camshaft | PRD-FRT | FRT | 5 | 48 | [146 empty] | >
M | Remove Lock tool of crankshaft | PRD-EXH | EXH | 5 | [147 empty] | >
M | Install PLUG-CM/SHF CVR OPG | PRD-FRT | FRT | 10 | [148 empty] | > | >
M | Tighten PLUG-CM/SHF CVR OPG | PRD-FRT | FRT | 8 | [150 empty] | >
M | Install SEPARATOR ASM-PCV OIL | PRD-EXH | EXH | 20 | [127 empty] | >
M | Pre-tighten BOLT/SCREW-PCV OIL SEP | PRD-EXH | EXH | 12 | [152 empty] | >=
A | Plasma BLOCK ASM-ENG （Front cover surface） RTV COVER ASM-ENG FRT | PRD-FRT | FRT | 66 | 49 | [131 empty] | > |  |  | > |  |  | > | [7 empty] | > |  | > | >
M | Load COVER ASM-ENG FRT | PRD-FRT | FRT | 20 | 50 | [153 empty] | >=
M | Install COVER ASM-ENG FRT | PRD-FRT | FRT | 20 | [155 empty] | >=
M | Pre-tighten BOLT/SCREW-ENG FRT CVR | PRD-FRT | FRT | 20 | [156 empty] | >=
M | Scan COVER ASM-TMG BELT UPR FRT 2D code | PRD-FRT | FRT | 3 | 51 | [147 empty] | > | >
M | Install COVER ASM-TMG BELT UPR FRT | PRD-FRT | FRT | 18 | [158 empty] | >=
M | Pre-tighten BOLT/SCREW-TMG BELT UPR CVR | PRD-FRT | FRT | 20 | [159 empty] | >=
M | Install SOLENOID ASM-CM/SHF POSN ACTR VLV | PRD-FRT | FRT | 10 | [160 empty] | >
M | Pre-tighten BOLT/SCREW-CM/SHF POSN ACTR VLV SOL | PRD-FRT | FRT | 10 | [161 empty] | >=
A | Tighten BOLT/SCREW-ENG FRT CVR Tighten BOLT/SCREW-TMG BELT UPR CVR Tighten BOLT/SCREW-PCV OIL SEP | PRD-FRT | FRT | 66 | 52 | [152 empty] | > |  |  |  | > |  |  | >
A | Lubricate LUBRICANT-VALVE LIFTER BORE | PRD-FRT | FRT | 66 | 53 | [126 empty] | > | [35 empty] | >
M | Install FOLLOWER ASM-VLV LFTR | PRD-INT | INT | 8 | 54 | [163 empty] | >=
M | Scan PUMP ASM-FUEL 2D code | PRD-INT | INT | 3 | [165 empty] | >
M | Install PUMP ASM-FUEL | PRD-INT | INT | 12 | [166 empty] | >=
M | Pre-tighten BOLT/SCREW-F/PMP | PRD-INT | INT | 8 | [167 empty] | >=
M | Scan RAIL ASM-DIR F/INJN FUEL W/ F/INJN WRG HARN 2D code | PRD-INT | INT | 3 | [127 empty] | >
M | Install RAIL ASM-DIR F/INJN FUEL W/ F/INJN WRG HARN | PRD-INT | INT | 10 | [169 empty] | >=
M | Pre-tighten BOLT/SCREW-F/INJN FUEL RL | PRD-INT | INT | 8 | [170 empty] | >=
M | Tighten BOLT/SCREW-CM/SHF POSN ACTR VLV SOL | PRD-FRT | FRT | 8 | [162 empty] | >
M | Scan BALANCER ASM-CR/SHF 2D code | PRD-FRT | FRT | 3 | 55 | [162 empty] | >
M | Install BALANCER ASM-CR/SHF | PRD-FRT | FRT | 20 | [173 empty] | >=
M | Pre-tighten BOLT/SCREW-CR/SHF BALR | PRD-FRT | FRT | 10 | [174 empty] | >=
M | Install SENSOR ASM-KNOCK | PRD-INT | INT | 15 | [110 empty] | >
M | Tighten BOLT/SCREW-KNOCK SEN | PRD-INT | INT | 5 | [176 empty] | >
M | Connect the harness of Knock Sensor | PRD-INT | INT | 5 | [171 empty] | > | [5 empty] | >
A | Tighten BOLT/SCREW-CR/SHF BALR Tighten BOLT/SCREW-F/PMP Press RAIL ASM-DIR F/INJN FUEL W/ F/INJN WRG HARN Tighten BOLT/SCREW-F/INJN FUEL RL | PRD-FRT | FRT | 66 | 56 | [167 empty] | > |  |  | > |  |  |  | >
M | Scan PIPE ASM-FUEL FEED INTER 2D code | PRD-INT | INT | 3 | 57 | [178 empty] | >
M | Install PIPE ASM-FUEL FEED INTER | PRD-INT | INT | 20 | [180 empty] | >=
M | Tighten PIPE ASM-FUEL FEED INTER | PRD-INT | INT | 30 | [181 empty] | >
M | Tighten BOLT/SCREW-F/INJN FUEL FEED PIPE | PRD-INT | INT | 5 | [181 empty] | >
M | Install COIL ASM-IGN | PRD-INT | INT | 25 | 58 | [126 empty] | >
M | Pre-tighten BOLT/SCREW-IGN COIL | PRD-INT | INT | 20 | [184 empty] | >=
M | Tighten BOLT/SCREW-IGN COIL | PRD-INT | INT | 15 | [185 empty] | >
M | Install BRACKET-ENG LIFT RR(2) | PRD-FRT | FRT | 20 | 59 | [180 empty] | > | >
M | Pre-tighten BOLT/SCREW-ENG LIFT BRKT | PRD-FRT | FRT | 15 | [187 empty] | >=
M | Tighten BOLT/SCREW-ENG LIFT BRKT | PRD-FRT | FRT | 12 | [188 empty] | >
M | Install SENSOR ASM-ENG COOL TEMP | PRD-FRT | FRT | 5 | [163 empty] | >
M | Tighten SENSOR ASM-ENG COOL TEMP | PRD-FRT | FRT | 5 | [190 empty] | >
M | Conect harness of SENSOR ASM-ENG COOL TEMP | PRD-FRT | FRT | 5 | [191 empty] | >
M | Install hansen fitting | PRD-EXH | EXH | 8 | 60 | [162 empty] | >
M | Install process seal | PRD-EXH | EXH | 12 | [163 empty] | >
M | Tighten Hasen fitting | PRD-EXH | EXH | 5 | [193 empty] | >
M | Tighten Process seal bolt | PRD-EXH | EXH | 8 | [194 empty] | >
M | Install SENSOR ASM-ENG OIL PRESS | PRD-EXH | EXH | 6 | [110 empty] | >
M | Tighten SENSOR ASM-ENG OIL PRESS | PRD-EXH | EXH | 6 | [197 empty] | >
M | Re-tighten PIPE ASM-FUEL FEED INTER | PRD-INT | INT | 15 | [182 empty] | >
M | Heliem Test | PRD-INT | INT | 63 | 61 | [182 empty] | > | [15 empty] | >
A | Long block leak test | PRD-FRT | FRT | 66 | 62 | [103 empty] | > |  | > | > | > | [42 empty] | > | [11 empty] | > | [8 empty] | > |  |  |  |  | > |  | > | [6 empty] | > |  |  | > |  | > |  |  |  | > | > |  | > |  | >
A | Oil filling | PRD-FRT | FRT | 66 | 63 | [200 empty] | >
A | Cold Test | PRD-FRT | FRT | 66 | 64 | [177 empty] | > | [13 empty] | > | [9 empty] | >
M | Install INSULATOR-F/INJN FUEL RL | PRD-INT | INT | 5 | 65 | [202 empty] | >
M | Scan VALVE ASM-ENG COOL FLOW CONT 2D code | PRD-INT | INT | 3 | [203 empty] | >
M | Install VALVE ASM-ENG COOL FLOW CONT | PRD-INT | INT | 14 | [205 empty] | >=
M | Pre-tighten BOLT/SCREW-ENG COOL FLOW CONT VLV | PRD-INT | INT | 8 | [206 empty] | >=
M | Install GASKET-TURBO OIL FEED PIPE | PRD-EXH | EXH | 5 | [203 empty] | >
M | Install PIPE ASM-ENG COOL AIR BL | PRD-EXH | EXH | 15 | [208 empty] | >=
M | Pre-tighten BOLT/SCREW-ENG COOL AIR BL PIPE | PRD-EXH | EXH | 10 | [209 empty] | >=
M | Tighten BOLT/SCREW-ENG COOL FLOW CONT VLV | PRD-EXH | EXH | 6 | 66 | [206 empty] | >
M | Tighten BOLT/SCREW-ENG COOL AIR BL PIPE | PRD-EXH | EXH | 10 | [210 empty] | >
M | Scan PIPE ASM-ENG COOL HTR EXH 2D code | PRD-EXH | EXH | 3 | [212 empty] | >
M | Install GASKET-ENG COOL MANIF | PRD-EXH | EXH | 15 | [213 empty] | >=
M | Install PIPE ASM-ENG COOL HTR EXH | PRD-EXH | EXH | 15 | [214 empty] | >
M | Pre-tighten BOLT/SCREW-ENG COOL HTR EXH PIPE | PRD-EXH | EXH | 10 | [215 empty] | >=
M | Tighten BOLT/SCREW-ENG COOL HTR EXH PIPE | PRD-EXH | EXH | 8 | 67 | [215 empty] | >
M | Install HOSE ASM-THERM BYPASS | PRD-INT | INT | 10 | [211 empty] | >
M | Pre-tighten BOLT/SCREW-THERM BYPASS PIPE | PRD-INT | INT | 15 | [218 empty] | >=
M | Tighten BOLT/SCREW-THERM BYPASS PIPE | PRD-INT | INT | 5 | [219 empty] | >
M | Install BOLT/SCREW-ENG COOL AIR BL PIPE | PRD-FRT | FRT | 6 | [212 empty] | >
M | Tighten BOLT/SCREW-ENG COOL AIR BL PIPE | PRD-FRT | FRT | 5 | [221 empty] | >
M | Install BOLT/SCREW-ENG COOL HTR EXH PIPE BRKT | PRD-FRT | FRT | 6 | [218 empty] | >
M | Tighten BOLT/SCREW-ENG COOL HTR EXH PIPE BRKT | PRD-FRT | FRT | 5 | [223 empty] | >
M | Scan MANIFOLD ASM-INT (W/ THROT BODY) 2D code | PRD-INT | INT | 3 | 68 | [203 empty] | > | [15 empty] | >
M | Scan BODY ASM-THROT (W/ SEN) 2D code | PRD-INT | INT | 3 | [225 empty] | >=
M | Scan ADAPTER ASM-THROT BODY 2D code | PRD-INT | INT | 3 | [226 empty] | >=
M | Install MANIFOLD ASM-INT (W/ THROT BODY) | PRD-INT | INT | 20 | [227 empty] | >=
M | Pre-tighten BOLT/SCREW-INT MANIF | PRD-INT | INT | 10 | [228 empty] | >=
M | Connect PIPE ASM-ENG COOL AIR BL & PIPE ASM-ENG COOL HTR EXH to cooler controler | PRD-INT | INT | 8 | [222 empty] | > |  | >
M | Connect HOSE ASM-THERM BYPASS to cooler controler | PRD-INT | INT | 8 | [220 empty] | >
M | Remove the clamps | PRD-INT | INT | 6 | [230 empty] | > | >
M | Lubricate INDICATOR ASM-OIL LVL (W/ IND TUBE) | PRD-INT | INT | 5 | 69 | [228 empty] | >
M | Install INDICATOR ASM-OIL LVL (W/ IND TUBE) | PRD-INT | INT | 10 | [233 empty] | >=
M | Pre-tighten BOLT/SCREW-OIL LVL IND TUBE BRKT | PRD-INT | INT | 5 | [234 empty] | >=
M | Blow by the hansen fitting | PRD-EXH | EXH | 5 | [203 empty] | >
M | Remove the hansen fitting | PRD-EXH | EXH | 8 | [236 empty] | >
M | Remove the seal | PRD-EXH | EXH | 8 | [203 empty] | >
M | Install SENSOR ASM-ENG OIL PRESS | PRD-EXH | EXH | 7 | [237 empty] | > | >
M | Tighten SENSOR ASM-ENG OIL PRESS | PRD-EXH | EXH | 8 | [239 empty] | >
M | Install CAP ASM-OIL FIL | PRD-EXH | EXH | 5 | [203 empty] | >
M | Install guide tool of turbo | PRD-EXH | EXH | 5 | 70 | [229 empty] | > | >
M | Install SHIELD ASM-TURBO HT | PRD-EXH | EXH | 5 | [242 empty] | >
M | Pre-tighten BOLT/SCREW-TURBO H/SHLD | PRD-EXH | EXH | 5 | [243 empty] | >=
M | Scan TURBOCHARGER ASM-CMPR AIR INT 2D code | PRD-EXH | EXH | 3 | [244 empty] | >
M | Install TURBOCHARGER ASM-CMPR AIR INT | PRD-EXH | EXH | 24 | [245 empty] | >=
M | Pre-tighten BOLT/SCREW-TURBO | PRD-EXH | EXH | 15 | [246 empty] | >=
M | Remove guide tool of turbo | PRD-EXH | EXH | 5 | [247 empty] | >
M | Install GASKET-TURBO OIL FEED PIPE | PRD-EXH | EXH | 12 | 71 | [247 empty] | >
M | Pre-tighten BOLT/SCREW-TURBO OIL FEED PIPE | PRD-EXH | EXH | 10 | [249 empty] | >=
M | Install SHIELD-CM/SHF CVR HT | PRD-EXH | EXH | 10 | [224 empty] | >
M | Pre-tighten BOLT/SCREW-CM/SHF CVR HT SHLD | PRD-EXH | EXH | 10 | [251 empty] | >=
M | Tighten BOLT/SCREW-TURBO H/SHLD | PRD-EXH | EXH | 5 | [250 empty] | > |  | >
M | Install HARNESS ASM-ENG WRG | PRD-EXH | EXH | 15 | [253 empty] | >
A | Tighten BOLT/SCREW-TURBO Tighten BOLT/SCREW-INT MANIF | PRD-FRT | FRT | 66 | 72 | [228 empty] | > | [18 empty] | >
M | Install GASKET-TURBO COOL FEED & RTN PIPE | PRD-EXH | EXH | 15 | 73 | [254 empty] | >
M | Lubricate PIPE ASM-TURBO COOL FEED & RTN | PRD-EXH | EXH | 5 | [256 empty] | >
M | Install PIPE ASM-TURBO COOL FEED & RTN | PRD-EXH | EXH | 15 | [257 empty] | >=
M | Pre-tighten BOLT/SCREW-TURBO COOL FEED & RTN PIPE | PRD-EXH | EXH | 8 | [258 empty] | >=
M | Pre-tighten BOLT/SCREW-TURBO COOL FEED PIPE BRKT | PRD-EXH | EXH | 5 | [259 empty] | >=
M | Remove the clamp of the pipe | PRD-EXH | EXH | 5 | [259 empty] | > | >
M | Pre-tighten STUD-TURBO H/SHLD | PRD-EXH | EXH | 8 | [253 empty] | >
M | Tighten STUD-TURBO H/SHLD | PRD-EXH | EXH | 12 | 74 | [261 empty] | >
M | Install HOSE-PCV | PRD-Rear | REAR | 10 | [255 empty] | >
M | Pre-tighten BOLT/SCREW-PCV HOSE CONN | PRD-Rear | REAR | 8 | [264 empty] | >=
M | Tighten BOLT/SCREW-PCV HOSE CONN | PRD-Rear | REAR | 5 | [265 empty] | >
M | Install ADAPTER-CHRG AIR CLR INL AIR HOSE | PRD-Rear | REAR | 10 | [255 empty] | >
M | Pre-tighten BOLT/SCREW-CHRG AIR CLR INL AIR HOSE | PRD-Rear | REAR | 8 | [267 empty] | >=
M | Tighten BOLT/SCREW-CHRG AIR CLR INL AIR HOSE | PRD-Rear | REAR | 8 | [268 empty] | >
M | Scan PUMP ASM-EVAP EMIS CNSTR PURGE 2D code | PRD-Rear | REAR | 3 | 75 | [255 empty] | >
M | Install PUMP ASM-EVAP EMIS CNSTR PURGE | PRD-Rear | REAR | 15 | [270 empty] | >=
M | Pre-tighten BOLT/SCREW-EVAP EMIS CNSTR PURGE PUMP | PRD-Rear | REAR | 10 | [271 empty] | >=
M | Tighten BOLT/SCREW-EVAP EMIS CNSTR PURGE PUMP | PRD-Rear | REAR | 10 | [272 empty] | >
M | Install INSULATOR-F/PMP | PRD-INT | INT | 5 | [203 empty] | >
M | Install BRACKET-ENG WRG HARN | PRD-INT | INT | 10 | [254 empty] | >
M | Pre-tighten NUT-ENG WRG HARN BRKT | PRD-INT | INT | 5 | [275 empty] | >=
M | Tighten BOLT/SCREW-OIL LVL IND TUBE BRKT | PRD-INT | INT | 5 | [235 empty] | >
M | Install COVER-F/PMP | PRD-INT | INT | 15 | 76 | [273 empty] | >
M | Pre-tighten BOLT/SCREW-F/PMP SHLD | PRD-INT | INT | 10 | [278 empty] | >=
M | Tighten BOLT/SCREW-F/PMP SHLD | PRD-INT | INT | 8 | [279 empty] | >
M | Tighten BOLT/SCREW-TURBO COOL FEED & RTN PIPE | PRD-EXH | EXH | 12 | [259 empty] | >
M | Tighten BOLT/SCREW-TURBO COOL FEED PIPE BRKT | PRD-EXH | EXH | 12 | [260 empty] | >
A | Final water cavity leak test | PRD-FRT | FRT | 66 | 77 | [216 empty] | > | [14 empty] | > | [7 empty] | > | [20 empty] | > |  | > |  |  | > |  |  | > |  |  |  | > |  |  | > | > |  |  | > | > | >
M | Print LABEL-ENG TRACEABILITY | PRD-FRT | FRT | 10 | 78 | [282 empty] | >
M | Scan LABEL-ENG TRACEABILITY | PRD-FRT | FRT | 8 | [284 empty] | >
M | Paste LABEL-ENG TRACEABILITY | PRD-FRT | FRT | 15 | [285 empty] | >
M | Print LABEL-ENG MFG ORIGIN | PRD-FRT | FRT | 10 | [283 empty] | >
M | Paste LABEL-ENG MFG ORIGIN | PRD-FRT | FRT | 15 | [287 empty] | >
M | care | PRD-FRT | FRT | 60 | 79 | [240 empty] | > | [44 empty] | > |  | >
M | loosen adapter bolts | PRD-FRT | FRT | 20 | 80 | [288 empty] | >
M | Unload ENGINE ASM-GASOLINE | PRD-FRT | FRT | 40 | [290 empty] | >