Supplement 3.Table 1.  Trial Undergoing Modifications in Extenuating Circumstances

| MULTIPAP PLUS trial modified by covid-19 ( Spain) | Sample of conserve items |
| --- | --- |
| The outbreak of the covid-19 pandemic in March 2020 overwhelmed the capacity of the Spanish healthcare system, a state of alarm was declared in the country and containment measures were implemented. The health measures imposed have affected the incidence of acute and chronic pathologies in this healthcare setting differently and many trials have been suspended. The MULTIPAP PLUS trial had started recruitment at the end of 2019 and centers were being enrolled sequentially so that no more than 100 patients had been recruited at the start of the pandemic. From the initial stages of the pandemic, primary care in Spain was responsible for the screening and diagnosis of covid-19 patients and for the out-of-hospital treatment at home of most of the affected patients. The project had to be suspended. The epidemiological situation and the pressure of care in primary care, first for COVID-19 and then for non-COVID pathologies that were no longer being treated or were delayed, made it impossible to resume the study until May 2021. ClinicalTrials.gov NCT04147130 Registration :. Recruitment Status : Recruiting First Posted : October 31, 2019 Last Update Posted : February 28, 2020 Patients recruited before March 2020 who had already signed informed consent were reviewed and their status updated between May 2021 and December 2021. The randomization of the physicians to the intervention or control group will take place at the end of recruitment in December 2021 and the 6, 12 and 18 month visits will be counted from the time of physician randomization. In order to make the care work of the physicians in the study compatible with the pressure of care, the number of patients per physician has been reduced (from 8 to 5 patients per physician). This reduction in the size of the cluster has modified the final sample size. ClinicalTrials.gov NCT04147130 Registration : Estimated Enrollment :1234 participants. An average group size of eight patients per FP and an intraclass correlation coefficient of 0.02 [2] . The design effect (DE)=1.14 . Now, an average group size of five patients per FP, the design effect (DE)=1.08. Estimated Enrollment : 1063 patients. Assuming a loss rate of 8%, the final sample size required is 1148 patients (574 per group). | Extenuating circumstance: COVID-19 and its effects on primary care. Impacts: RCT had to be suspended in march 2020. Study began again in may 2021. Impacts: Stop recruitment, loss of some professionals and patients. Mitigating strategies: restart recruitment in May 2021 and increase period to December 2021, Changed in Clinical Trial Registration: Recruitment Status: Recruiting First Posted: October 31, 2019 Suspended recruitment: March 2020- May 2021 Last Update Posted: December , 2021 Patients recruited before March 2020 were reviewed and their status updated, the situation of the participating physicians was reviewed and new professionals were incorporated, the number of patients per physician has been reduced to 5. These are important modifications that had implications for study feasibility and the size of the cluster . |