Table 5. Mentorship visits, workplan development and implementation by intensive implementation and maintenance phases

|  | All facilities |  |  |  | Wave 1 |  |  |  |  | Wave 2 |  |  |  |  | Wave 3a |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mentorship and workplan indicators | Intensive | Maintenance |  |  |  | Intensive | Maintenance |  |  |  | Intensive | Maintenance |  |  |  | Intensive |  |
| Mentorship visits per facility-month (mean) | 1.10 | 1.00 |  |  |  | 1.17 | 1.00 |  |  |  | 1.09 | 1.00 |  |  |  | 1.05 |  |
| Facility staff participation per mentorship visit (mean) | 6.57 | 7.58 |  |  |  | 7.78 | 8.64 |  |  |  | 4.86 | 5.46 |  |  |  | 7.03 |  |
| Workplans created (total, 04/2018–03/2021) | 429 | 432 |  |  |  | 144 | 288 |  |  |  | 144 | 144 |  |  |  | 141 |  |
| per health facility (mean) | 11.9 | 12.0 |  |  |  | 12.0 | 24.0 |  |  |  | 12.0 | 12.0 |  |  |  | 11.8 |  |
| Micro-interventions proposed (total, 04/2018–03/2021) | 967 | 719 |  |  |  | 368 | 528 |  |  |  | 327 | 191 |  |  |  | 272 |  |
| per workplan (mean) | 2.3 | 1.7 |  |  |  | 2.6 | 1.8 |  |  |  | 2.3 | 1.3 |  |  |  | 1.9 |  |
| Workplan implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fully, n (%) | 237 (57%) | 221 (55%) |  |  |  | 78 (54%) | 143 (52%) |  |  |  | 83 (58%) | 78 (60%) |  |  |  | 76 (59%) |  |
| Partially, n (%) | 146 (35%) | 126 (31%) |  |  |  | 57 (40%) | 99 (36%) |  |  |  | 43 (30%) | 27 (21%) |  |  |  | 46 (36%) |  |
| No, n (%) | 34 (8%) | 57 (14%) |  |  |  | 9 (6%) | 33 (12%) |  |  |  | 18 (13%) | 24 (19%) |  |  |  | 7 (5%) |  |
| Micro-intervention adoption |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Adopted, n (%) | 222 (70%) | 246 (62%) |  |  |  | 19 (43%) | 153 (56%) |  |  |  | 102 (71%) | 93 (73%) |  |  |  | 101 (78%) |  |
| Adapted, n (%) | 88 (28%) | 113 (28%) |  |  |  | 24 (55%) | 82 (30%) |  |  |  | 37 (26%) | 31 (24%) |  |  |  | 27 (21%) |  |
| Abandoned, n (%) | 7 (2%) | 41 (10%) |  |  |  | 1 (2%) | 37 (14%) |  |  |  | 5 (3%) | 4 (3%) |  |  |  | 1 (1%) |  |
| Sector in which problems were identified |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Antenatal care, n (%) | 118 (24%) | 63 (14%) |  |  |  | 48 (27%) | 50 (17%) |  |  |  | 40 (23%) | 13 (9%) |  |  |  | 30 (20%) |  |
| Maternity, n (%) | 191 (38%) | 189 (42%) |  |  |  | 62 (35%) | 125 (42%) |  |  |  | 69 (40%) | 64 (44%) |  |  |  | 60 (40%) |  |
| Postpartum care, n (%) | 11 (2%) | 9 (2%) |  |  |  | 6 (3%) | 9 (3%) |  |  |  | 3 (2%) | 0 (0%) |  |  |  | 2 (1%) |  |
| At-risk child service, n (%) | 181 (36%) | 186 (42%) |  |  |  | 63 (35%) | 117 (39%) |  |  |  | 60 (35%) | 69 (47%) |  |  |  | 58 (39%) |  |
| Micro-intervention categorization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Service organizationb, n (%) | 327 (34%) | 267 (37%) |  |  |  | 118 (32%) | 231 (44%) |  |  |  | 104 (32%) | 36 (19%) |  |  |  | 105 (39%) |  |
| Patient educationc, n (%) | 472 (49%) | 335 (47%) |  |  |  | 179 (49%) | 211 (40%) |  |  |  | 159 (49%) | 124 (65%) |  |  |  | 134 (49%) |  |
| Staff communication improvement, n (%) | 42 (4%) | 32 (4%) |  |  |  | 22 (6%) | 30 (6%) |  |  |  | 15 (5%) | 2 (1%) |  |  |  | 5 (2%) |  |
| Data quality improvement and use to inform decision-making, n (%) | 237 (25%) | 174 (24%) |  |  |  | 96 (26%) | 130 (25%) |  |  |  | 71 (22%) | 44 (23%) |  |  |  | 70 (26%) |  |
| All facilities had a 12-month intensive phase. Wave 1 facilities began the intensive phase in April 2018 and had a 24-month maintenance phase. Wave 2 facilities began the intensive phase in April 2019 and had a 12-month maintenance phase. Wave 3 facilities began the intensive phase in April 2020 and had no maintenance phase during the study period. aWave 3 facilities had no maintenance phase due to the stepped-wedge study design, in which these facilities initiated the intensive phase 24 months later than wave 1 facilities. bservice organization includes reorganization, such as task-shifting. cpatient education includes calling new mothers to encourage retention in care. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |