Supplementary material 4: CHW community mobilization training with rapid PAR workshops (n=15)

| Week/ Workshop | Participants | Facilitator/s | Objectives/tools |
| --- | --- | --- | --- |
| Week 1 Workshop 1 (Introduction and Training 1.1) | - CHWs (9) - Community mentors (6) - Clinic nurses (3) - Clinic cttee (3) | VAPAR | Training in PAR tool 1 (ranking/rating) to support and orient of CHWs and community mentors to identify priority health issue. |
| Weeks 2-3 Workshop 2 (Training 1.2) | - CHWs (9) - Community mentors (6) | VAPAR | Training in PAR tool 2 (problem tree) to identify priority health related condition, facilitation and consensus building and community engagement - engaging active pax. selection and representation (n=3 for each CHW). Training in PAR tool 3 (photovoice) to convey lived experiences visually. Basic photography training given. Photographs showing topics as they exist physically taken and showcased in public discourses. Captions developed on what images convey. Baseline interviews. |
| Week 4 Workshop 3 Workshop 4 Workshop 5 (Problematising) | In each of 3 villages - CHWs (3) - Community mentors (2) - Community pax (9) | CHWs | Understand priority health issue from different perspectives, identifying cause-and-effect relationships, consequences, and other effects, building shared accounts. |
| Week 5 Workshop 6 (Training 2) | - CHWs (n=9) - Community mentors (n=6) | VAPAR | Reflect on Workshops 3-5. Training in PAR tool 3 (Venn diagram) to identify actors and organisations involved with the topic and how they relate to one another with regards to collaboration and contact. |
| Week 6 Workshop 7 Workshop 8 Workshop 9 (Actors and impacts) | In each of 3 villages - CHWs (3) - Community mentors (2) - Community pax (9) | CHWs | Understand impacts and actors. Collective account indicating relationships and interactions between various actors and institutions. |
| Week 7 Workshop 10 (Training 3) | - CHWs (9) - Community mentors (6) | VAPAR | Reflect on Workshops 7-9. Training in PAR tool 4 (Action planning) to collectively articulate overall goal(s) and develop series of interconnected steps and events to achieve these. |
| Week 8 Workshop 11 Workshop 12 Workshop 13 (Action planning) | In each of 3 villages - CHWs (3) - Community mentors (2) - Community pax (9) | CHWs | Agree overall goal(s) to address issues identified and develop stepwise actions to achieve these. Draws on problem tree and Venn diagram to collectively develop moving towards a desired goal via a series of interconnected steps and events |
| Week 9 Workshop 14 (Synthesis and agreeing process for engaging authorities) | - CHWs (9) - Community mentors (6) - Clinic nurses (3) - Clinic committee (3) | VAPAR | Reflect on Workshops 11-13 and codesign/plan taking local action plans to multisectoral fora for analysis and planning. Conduct end line interviews. |
| Week 10 Workshop 15 (Planning Step 2) | - CHWs (9) - Community mentors (6) - Clinic nurses (3) and - Clinic cttee (3) - Community pax (27) | CHWs | Present and finalise PAR data for 3 villages. Conduct end line interviews. |

N.B.: Shaded rows indicate community workshops; clear rows denote peer support workshops