Supplementary file 2_ Timeline tables
Supplementary table 1: Project timeline and deadlines
	Date
	Task

	24.10
	Intensive period starts: 
· Protocol completed and sent to internal peer review with deadline 26.10 kl 15:45. Not sent to external peer reviewers as subject specialists were involved in writing the project plan. 

	26.10
	Project plan back from peer review

	27.10
	Search run

	28.10
	Project plan completed and sent for approval. Systematic review protocol registered in Prospero. 

	31.10
	Screening and study selection start

	04.11
	Finalize including studies

	07.11- 09.11
	Data extraction

	10.11-18.11
	Analysis (GRADE)

	18.11
	GRADE and Risk of Bias completed

	21-30.11
	Report writing

	30.11
	Send to internal and external peer review with deadline 05.12

	05.12
	Report back from internal and external peer review

	07. 12
	Report completed and sent for leader approval

	13.12
	Report approved and ready for publication






Supplementary table 2: Project timeline and deadlines compared to actual work outputs for the systematic scoping review
	Task plan
	Scoping review actual work outputs

	24.10
	Protocol completed and sent to internal peer review 
	24.10

27.10*
	Protocol completed and sent to internal peer review 
Protocol sent to external review with a two-day deadline

	26.10
	Project plan back from peer review
	26.10

29.10

	Project plan back from internal peer review
Project plan back from external peer reveiw 

	27.10
	Search run
	25.10**
	Database searches run

	28.10
	Project plan completed and sent for approval. 
	31.10
	Project plan completed and sent for approval.

	31.10
	Screening and study selection start

	04.11
	Finalize included studies
	10.11

	We searched for relevant studies in grey literature and in OpenAlex parallell to data extraction from the included studies from the database searches

	07- 09.11
	Data extraction
	7- 18.11

	Data extraction and mapping of evidence base

	21-30.11
	Report writing

	30.11
	Send to internal and external peer review 

	05.12
	Report back from internal and external peer review

	07. 12
	Report completed and sent for leader approval

	13.12
	Report approved 
	14.12
	Report approved


*As we collaborated with a topic expert on the project plan we did not plan to send it to external review. The internal reviewer did however mean that this was necessary and we decided to send it to an external reviewer according her feedback. ** The search was run before feedback from reviewers as we needed an overview of the approximate number of search hits to plan our work. We planned to adapt the search strategy according to feedback from reviewers if necessary. 



Supplementary table 3: Project timeline and deadlines compared to actual work outputs for the systematic review
	Task plan
	Systematic Review actual work outputs

	24.10            Protocol completed and sent to internal peer review *

	26.10
	Project plan back from peer review
	25.10
	Protocol back from peer review

	27.10
	Search run

	28.10
	Project plan completed and sent for approval. 
Systematic review protocol registered in Prospero. 
	27.10
	Project plan sent to approval (approved on 31.10). 
Registration in PROSPERO completed

	31.10
	Screening and study selection start
	28.10
	Screening and study selection start

	04.11
	Finalize included studies
	03.11
	Screening completed. No included studies


	07- 09.11
	Data extraction
	04.11
	Meeting with commissioner to discuss further solutions (agreed on: a) finish deliverable 1 – empty systematic review, b) deliverable 2 – mapping include risk of bias-assessment of selected research excluded from systematic review***)

	10-18.11
	Analysis (GRADE)
	04.11-09.12
	Report writing (deliverables 1 and 2) 

	18.11
	GRADE and Risk of Bias completed
	14.11
	Report (deliverable 1) sent to internal and external peer review 

	21-30.11
	Report writing
	28.11
	Report (deliverable 1) back from last peer reviewer

	30.11
	Send to internal and external peer review 
	06.12
	Report (deliverable 1) complete and sent for leader approval

	05.12
	Back from peer review
	08.12

09.12
	Report (deliverable 1) approved and ready for publication
Report (deliverable 2) complete and sent to for leader approval

	07. 12
	Report completed and sent for leader approval
	12.12
	Report (deliverable 2) approved and ready for publication

	13.12
	Report approved and ready for publication
	
	


* Because a topic expert was involved on the commissioners’ side, no peer reviewers were involved in deliverable 2 (as per NIPHs quality assurance procedure for this product type).



