Table S1: Gantt chart timeline for Study 1

| Milestones |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Milestone 1: Logistic preparations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Development of electronic data abstraction form and data collection workflow. | X |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 | Training of research team members in data abstraction | X |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 2: Pre-post Data collection |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Sociodemographic, clinical, quality of care, services utilization and satisfaction secondary data collection. |  | X | X | X | X | X | X | X | X | X |  |  |
| Milestone 3: Qualitative data collection |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Key informant/examiner partner interviews and focus groups to collect patient experience and qualitative satisfaction data |  |  | X |  |  | X |  |  |  |  |  |  |
| Milestone 3: Data compilation, analysis and preparation of reports, publications and presentations for multi-scale dissemination |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Data compilation. |  |  |  | X | X | X | X | X | X | X | X | X |
| 4.2 | Data analysis. |  |  |  | X | X | X | X | X | X | X | X | X |
| 4.3 | Preparation of reports, publications and presentations. |  |  |  |  |  |  | X | X | X | X | X | X |