Appendix 1: A sample from the deliverable sheet created to keep track of all the tasks and deadlines under each phase.

Tasks

Phase one: Benchmarking

Develop a practical methodology for evaluating countries' experiences that considered the best practices

Develop the criteria for the initial selection and sort of countries' experiences that are considered best practices

Prepare a preliminary study of country experiences

Prepare an inclusive study that includes all external factors and influences (political, economic, social, legal, technological, etc.) and internal factors and influences (beneficiaries, suppliers, human and financial resources and capabilities, leadership, strategic vision, governance, etc.)

Document the initial selection and screening criteria

Document the study methodologies

Document the initial study of the country's experiences

Document the inclusive study of the country's experiences

Phase two: Review the current public health training situation (situational analysis).

List and classify all agencies that provide education and training services in general, and in particular education and training in the health fields

List and classify all relevant initiatives, plans, and strategies of external parties

List and classify all agencies regulating education and training in the health field and define the sector governance

List and classify the systems, regulations and legislations that are related to public and private education and training in the health fields

List all training, educational, technical, and administrative programs in the health fields

Classify comprehensive training and educational programs in the health fields that include topics, category of beneficiaries, number of beneficiaries, prices, means, obligation, accreditation, geographic coverage, number of hours, number of times per year, etc.

Identify and classify private and public suppliers of educational and training services and products in terms of hardware, operation, IT systems and services, Technical and management consultancy, support services, etc.

Document the methodologies and criteria used to study and analyse the current situation

Document the study and analysis for the current status of the training and health education sector

Phase three: Develop a strategy for setting up Public Health Academy

Prepare the vision and mission

Prepare the target value and basic principles of service

Develop a strategic and operational plan that aligns with the Kingdom's 2030 vision and the national and health transformation programs in developing national capabilities and derives from the strategy of the National Centre for Prevention from Diseases and their control

Set Quick Wins, medium-, and long-term targets

Examine the obstacles, risks, and current strengths of the facility

Create a SWOT analysis (strengths, weaknesses, opportunities, and threats) for the Public Health Academy

Examine the influencing external factors

Create a gap analysis between the current situation and the target vision

Design a Development Learning Model, identify the target groups, and analyse the training and knowledge needs

Align with the other related parties' initiatives, plans, and strategies

Prepare and classify the initiatives and recommendations to achieve the targets

Prepare the operating model according to the approved best practices, including the service description, the service's beneficiaries, the service, the price of the services, the service providers, the stakeholders, service delivery channels, etc.

Prepare a governance model

Prepare job descriptions of leaders, technicians, and administrators

Prepare the employment plan for leaders, technicians, and administrators

Prepare the operation and development plan and measuring performance template

Prepare a plan to target Healthcare Workers and Non-Healthcare Workers ( Marketing plan)

Prepare a (Phasing-out plan for non-health workers with public health workers in the areas of public health.

Prepare the academic, financial sustainability plan and financial planning for future programs

Prepare the marketing plan