## Adaptation
No. | Activity Name | Lifecycle stage |  |  | Project stage(s) | Description of Activity | Implemetation of Activity (general) | Implemetation of Activity (Energy specific)
|  | Planning | Delivery | Management
1 | Stakeholder Mapping and Engagement | TRUE | FALSE | FALSE | Project Preparation | Conducting an inclusive stakeholder mapping can identify all parties affected by the infrastructure project and its climate impacts. Identifying a broad spectrum of stakeholders is pivotal for contextualizing the project. This can lead to more informed decision-making and better project outcomes, including more effective climate adaptation strategies. Additionally, planners and project managers should undertake continuous engagement-building exercises among stakeholders to increase communication, collaboration, and trust, and facilitate wide acceptance of the project. This can lead to improved environmental and social sustainability. | - Identify the users of the infrastructure asset and its associated services. - Identify stakeholders who would be directly and indirectly affected by climate impacts related to the project, such as decision makers, local communities, and civil society organizations. - Understand which actors have the power to influence and make decisions regarding the local environment. - Consider the willingness and capacity of local stakeholders to participate in a project over the long term. - Identify the skills and resources that different stakeholders can provide that will be benificial to the project. - Understand the role of different stakeholders to minimize the risk of marginalizing or negatively impacting any particular group. | - Map stakeholders in the energy sector, including manufacturers, retailers, operators, local governments, local populations, landowners, energy users, and energy companies, to achieve effective energy projects that realize the full climate adaptation potential of the project. - Investigate potential land-use conflicts for some renewable energy projects, where stakeholder mapping should address interests in competing land-uses, especially for adaptation purposes. - In the stakeholder mapping, include communities and connected civil society organizations that live and use existing natural resources within the target area, and downstream of planned interventions where systemic impacts may occur.
2 | Inclusive Public Participation for Climate Justice | TRUE | FALSE | FALSE | Project Preparation | Local communities and civil society organizations should be included in the decision-making process. Engagement of marginalized groups of society, including women and indigenous people, should be prioritized to ensure that project process and outcomes support climate justice. Increased acceptance of the project, identification of goal conflicts, and trade-offs between environmental and social factors are all supported by inclusive public participation. | - Increase public participation and prioritize information distribution about the project to enhance the quality of decision-making, incentivized by the Aarhus Convention. - Conduct inclusive participatory stakeholder consultation with diverse participatory methods to understand how a climate risk will affect the different stakeholders. - Implement public participation in the EIA or SEA. - Conduct participatory pre-feasibility and feasibility studies to ensure uptake of social and environmental implications and trade-offs of the project. | - Public participation and inclusion of local citizens and civil society organizations are extra important for land-use decisions for renewable energy projects where spatial claims need to be made. - The transition towards a sustainable and renewable energy system benefits from involving the public, and strong democracies are important to support a political climate where society can influence the transition - In the transition towards a renewable energy system, take consideration of communities dependent on fossil fuel extraction with social and economic consequences.
3 | Use of Indigenous and Local Knowledge | TRUE | FALSE | FALSE | Project Preparation | Indigenous and local knowledege (ILK) are skills and information that has developed through historical observations of local surroundings and are a valuable asset for informed land-use decisions in an infrastructure project. ILK brings contextualisation of the natural surroundings to the site of intrest for exploatation and can provide valuable information of effective land use decisions and identification of long-term climate changes. When formal data collection is unavailable, ILK can be a complement to the scientific knowledge and should be used in the decision making process for more effective and context-specific adaptation measures, while also respecting and valuing the knowledge and perspectives of local communities. | - Use contextualized ILK in the decision-making process for better decision basis about the local area to complement the scientific data and project approaches in the project preperation to avoid climate culnerable sites. - Engage with local communities and indigenous groups from the outset of a project, and establishing mechanisms for ongoing communication and consultation throughout the project lifecycle - Include local and indigenous communities in the assessment of climate risks in the area to incorporate the needs of all citizens for climate adapted infrastructure | - For renewable energy projects, local and indigenous knowledge is important to incorporate in the decision-making process about land use decisions. Local communities attain valuable knowledge to complement the scientific decision basis.
4 | Policy and Legal Framework Assessment | TRUE | TRUE | TRUE | Infrastructure Planning | Robust policies and regulatory legal frameworks for climate adaptation can enhance resilience and reduce vulnerability in an infrastructure project. Identification and compliance to legal frameworks underpins effective delivery of infrastructure. Practitioners have an important role to align projects to long-term climate resilient development strategies. | - Understand and document the legal and policy framework for climate adaptation and infrastructure planning in the country. - Set the project in context of national climate visions and identify the role of adaptation measures in infrastructure assets (e.g., NDCs, national sustainability goals when applicable) - Identify if the country of interest has developed a Climate Action Plan (CAP) or National Adaptation Plan (NAP) and identify criteria for strengthened resilience in infrastructure | - Assess specific energy related targets and policies for your country - Identify potential energy specific action plans for your country. E.g., National Energy and Climate Plan (NECP), Sustainable Energy Action Plan (SEAP) or Sustainable Energy Climate Action Plan (SECAP)
5 | Consider Interdependencies, Systems Planning and develop Cross-ministerial Cooperation | TRUE | TRUE | TRUE | Project Preparation | Analyze the plan, projects, or program as a component in the inter-sectoral infrastructure system and study the interdependencies, synergies and trade-offs between assets and sectors to make robust long-term decisions that ensures resilient infrastructure provisioning related to climate change impacts. Identifying potential trade-offs and goal conflict between assets or environmental impacts are important to reduce the risk of sub-optimization. To achieve a systems perspective, initiate collaborations between all parts of society and long-term planning for infrastructure security to ensure that adaptation measures are taken. | - Assess other sectors where there are possible interdependencies or goal conflicts that could hinder resilience. - Initiate cross-sectoral collaboration in early planning to benefit adaptation strategies. - Consider interdependencies and potentially breaching chains to strengthen disaster control mechanisms - Identify the infrastructure asset in relation to critical Infrastructure services and climate adaptation by using an analysis of systems-of-systems - Increase systems resilience through systems planning that ensures diverse systems (see separate action) | - Collaborate with other sectors to ensure accurate energy provision prioritization - Consider sector-specific nexuses and how adaptation actions in energy infrastructure can support other sectors, such the energy-gender nexus for provisioning of energy to marginalized groups - Understand goal conflicts between the energy and agricultural sectors. Consider the most urgent need for the local population to ensure accurate adaptation strategies in the form of securing energy and/or food supply. - Consider interdependencies between energy and water. Many energy generation projects have high water requirements which pose uncertainties in supply due to climate change. Benefits of renewable energy projects need to be weighed against future water stress and impacts on freshwater ecosystems.
6 | Strategic Environmental Assessment | TRUE | FALSE | FALSE | Strategic Planning | Conducting a Strategic Environmental Assessment (SEA) in early development or in the strategic planning stage of a plan, program or policy ensures environmental impact considerations in long-term infrastructure planning. Including climate change in the assessment assures increases the adaptive capacity by acknowledging impacts from climate change in the design and planning. Integration of climate change in the SEA leads to better informed infrastructure plans and programs with greater adaptation to climate change. | - Conduct a SEA in strategic planning with the means of evaluating how the plan or project will be affected by climate change impacts. - In the SEA, include an evaluation of the program, plan or policies' potential impacts on the climate - In the SEA, include an analysis of how the program, plan or policy is affected by climate change and its impacts - Use the SEA for decision-making by assessing multiple alternatives - Invest in profound stakeholder participation for successful realization of the SEA. | - Adaptive strategic planning for energy infrastructure should also include more vulnerable assets, such as transmission lines to ensure energy provision in case of climate hazards.
7 | Environmental Impact Assessment | TRUE | TRUE | FALSE | Infrastructure Planning & Project preperation | An Environmental Impact Assessment (EIA) should be conducted, even if it is not legally required. An EIA shall identify, describe, and assess the direct and indirect effects of a project on ecosystems and humans. Apart from evaluating other environmental impacts, the assessment should integrate climate adaptation factors, since climate change is directly linked to ecosystem degradation and pollution. This includes evaluation of potential short-term or long-term impacts of climate change on the surrounding environment and adapting to anticipated adverse environmental impacts. An EIA can therefore be useful in formulating appropriate measures to adapt to climate impacts. | - Assess the regulatory framework for EIA related to the project in your region with identification of requirements for climate change considerations for the EIA - Include an evaluation of the project's potential impacts on the climate - Include an analysis of how the project is affected by climate change and its impacts - Integrate climate change impacts into the EIA to ensure that spatial planning and project design is executed as to fit future climate conditions
9 | Diverse Systems for Resilient Infrastructure Systems | TRUE | FALSE | FALSE | Strategic planning, Project Preparation | Diversification and redundancy within a system underpins resilience. Studying the infrastructure asset as a part of the bigger system helps to identify vulnerability within the system to guide infrastructure planning towards a climate adapted system. Diverse systems reduce the risk of catastrophic failure in the face of climate-related stresses and can also enhance adaptation and increase resilience to climate change impacts, as they provide multiple options and pathways for recovery. | - Interdependencies and synergies between assets and artifacts within the sector should be studied to adopt opportunities for diversity. - Interdependencies across sectors should be identified to account for different sectors providing the same service for society. In those cases, systems could be planned for redundancy where another sector substitute the function during a disruption in operation to build systemic resilience - Diversify infrastructure systems via a mix of assets with different vulnerabilities - Diversify infrastructure systems by incorporating multiple types of infrastructure (e.g. green infrastructure, gray infrastructure, and hybrid systems). - Base the diverse systems on renewable energy generation for co-benefits between mitigation and adaptation | - A variety of energy generation creates resilience in the energy system. Plan for power generation with differentiated vulnerabilities. E.g. Solar and wind are vulnerable to strong winds while hydropower is vulnerable to drought, and nuclear and thermal plants are vulnerable to floods and heat waves. - Plan for redundancy in the energy system, where multiple assets can provide back-up energy generation during disruptions to secure energy supply. - Mini-grids and microgrids do not rely on long-distance transmission lines and can therefore provide useful backup generation in case of disruptions in electricity transmission and distribution. - Analyze the possibility of decentralized power production to reduce risks
11 | Disaster Screening and Vulnerability Assessment | TRUE | FALSE | FALSE | Project Preparation | Climate change and extreme weather events are increasingly threatening infrastructure. Identifying climate risks with consideration of future climate changes and possible extreme weather events is therefore crucial to achieve good infrastructure planning. The assessment should be conducted to inform decisions on project design and accurate site selection as well as to take appropriate adaptation measures and mainstreaming of climate resilience in projects. Identification of most expected short-term climate impacts (as EWEs) and long-term chronic climate risks are useful for effective asset management in later stages. | - Conduct a Climate and Disaster Risk Screening to consider short- and long-term climate and disaster risks in the planning processes. - Include assessment of local climate impacts in the risk assessments to understand current and future climate variability and identify vulnerable locations unsuitable for new infrastructure development by: i) Collecting historical climate data to identify threats to the facility ii) Including scenario analysis to study chronic climate risks. iii) Use results to inform strategic decisions regarding site selection as well as maintenance schemes and routines iv) Consider using Geographic Information Systems (GIS) for accurate site selection - Following the climate risk screening, conduct a Climate Risk and Vulnerability Assessment (CRVA) including: i) detailed risk screening by assessing risks at medium and high level and the sensitivity of the project to climate variables such as rainfall, drought etc. ii) quantify climate change risks on the project iii) development of adaptation measures in the project design iv) report on the CRVA - When the most expected climate impacts are identified, the risk assessment should be followed by a contingency plan for how to act in case of emergency (see separate action). | - Most energy shortages come from damage to transformers, transmission lines and grids rather than damages to energy generation infrastructure. Be sure to include all energy infrastructure in the climate risk assessment. - Conducting a risk assessment in relation to nuclear power is crucial due to high consequences in case of disaster.
12 | Disaggregated Socio-Economic Data for Inclusive Infrastructure Planning | TRUE | FALSE | FALSE | Project Preparation | Collecting, processing, and sharing disaggregated data can help identify vulnerable groups within communities facing adverse effects of climate change and be used to establish actions to address their needs. Infrastructure planning should be guided by accurate data about consumption patterns and needs so that those most vulnerable to climate impacts can be prioritized. Disaggregated data allows for detailed analysis of socio-economic patterns in society and leads to more inclusive infrastructure for climate adaptation purposes. | - Collect spatially detailed data disaggregated by household income, gender, age, sex, geographic remoteness, and other inclusion indicators. Ensure that these consider the diverse needs of different users, especially marginalized groups. - Collect statistical disaggregated data via; i) surveys ii) observations iii) measurements - Use the data with group-specific and intersectional needs analysis and spatially correlated with infrastructure needs assessments to inform the creation of inclusive infrastructure policies and programs. | - Collect energy data through household surveys, observations, or measurements - Disaggregate data of energy consumption to groups of household income, gender, age, sex, geographic remoteness, and other inclusion indicators. - Use the data to inform planners for better prioritization of energy accessibility and addressing people serviced by particularly vulnerable sections of the transmission network.
16 | Share and Promote Best Practices for Climate Action in Infrastructure | TRUE | TRUE | TRUE | Strategic Planning | Scaling up climate action in infrastructure requires strategic communication and outreach to ensure a transition towards a carbon neutral society. To most effectively achieve the transition, and speed up mainstreaming of climate action in infrastructure, project managers should document lessons learned and promote them to individuals and stakeholders replicating the process. Sharing climate adaptation practices can help trigger transformative change. | - Knowledge and awareness of climate adaptation practices in infrastructure development should be built through increased collaboration and exchange of experience across sectors, facilitated by governments, donors, civil society organisations and private sector actors. - Share development through case studies to show how progress can be achieved in different national contexts - Share local solutions to climate adaptation to increase knowledge sharing about best practices for infrastructure commissioning - Publish evaluations of projects to spread information about best practices, incorporating communication about how the project aligned to national and international targets for climate action. - Share examples of innovative funding to facilitate mainstreaming of climate actions in infrastructure - Cover communication and cooperation of information spreading in a broad dimension of platforms, from research, newspapers, non-academic publications, municipal platforms, international forums etc. - Cover communication and publications with inclusion of all stakeholders including national ministries, municipal governments, private sector platforms, NGOs, historically marginalised populations and international development partners. | - Share best practices of resilience in energy systems, both transmission and generation - Small-scale adaptation measures in design of energy infrastructure can be more easy generalised across regions and best practices of low-cost adaptation designs should be promoted
18 | Climate Resilient Public Private Partnerships | FALSE | TRUE | FALSE | Procurement | To ensure climate action is integrated throughout a project, the different lifecycle stages should be addressed early in planning to ensure value in the procurement. Public-private partnerships (PPP) is a model where an entire project is contracted to a private company, meaning that the company will obtain the responsability of the quality of the asset throughout the lifecycle of the project, including operations and maintenance. This will result in longer contracts where planning for adaptation strategies can be included in the delivery phase as well as maintenance and operations. Risk allocation is crucial to consider initially in the partnership to prepare for climate risks and ensure realization of preventative and reactive measures in case of a climate hazard. | - Include climate risk and climate vulnerability in the PPP criteria - Embed climate resilience in all four stages of PPP: i) Project identification ii) Business Case iii) Transaction iv) Contract Management - The PPP should result in coordinated adaptation actions and resilient infrastructure by having a lifecycle perspective and a better overview and transparency of the project. | - Contract an energy company for the whole lifecycle of a project to ensure adaptation strategies are incorporated throughout all the lifecylce stages. - Embed Climate Resilience in PPP for the Power Project Procurement.
19 | Performance Based Contracting for Risk Allocation | FALSE | TRUE | FALSE | Procurement | Performance-based contracting (PBC) is an approach to project contracting where the performance of the infrastructure is prioritized over the methods used to complete the work. This method can foster innovation in sustainability and climate resilience. Climate change can present challenges for the maintenance and operation of infrastructure assets. Therefore, the goal of PBC is to establish effective communication among stakeholders to determine responsibilities when climate change affects the infrastructure. In a PBC, the focus should be on risk allocation, ensuring that climate risks related to the project are identified and managed, leading to a reduction of economic and social climate impacts. | - Ensure that the infrastructure asset meets performance requirements - Include climate risks in the performance contracting, including; i) Identification of climate risks ii) Valuation of the identified risks iii) Allocation of responsability between the contractor and the owner. - Assign the contact to the application best equipped to manage the climate risks - Integrate adaptation measures into the contracting terms to reduce collective risk and increase climate resilience. | - Performance based contracts have mainly been implemented in the road transport and water sector but can also be implemented for example when building transmission lines or other energy projects where the maintenance of the asset is not clearly falling to one stakeholder. - Implement PBC to energy projects to enhance the adaptive performance of the infrastructure asset. - Acknowledge energy generation as provider of energy for vital societal functions such as hospitals, water treatment facilities, and schools. - Adopt a holistic approach for energy projects in PBC to include vulnerable components of the energy systems, such as transmission lines.
21 | Resilient and Flexible Design | FALSE | TRUE | FALSE | Design | To ensure that infrastructure is resilient to climate risks, it is important to incorporate adaptation measures into the design process. This includes designing the asset and surrounding site to be adaptable in the face of changing climate conditions. By integrating resilience into the design, natural shocks can be managed effectively, while also improving the cost-effectiveness and overall quality of the infrastructure. Additionally, designing for flexibility and modularity allows for efficient maintenance and upgrades to handle any future breaches. It is important to consider that infrastructure can be impacted by climate change in multiple ways, including both direct climate risks and changing user needs and demands due to climate impacts. Therefore, a holistic approach to design and construction is necessary to ensure that infrastructure is resilient to both current and future climate conditions. | - Design the infrastructure with stability and robustness in mind to ensure it can withstand extreme weather events and other climate-related hazards. This can be achieved by reinforcing structures and foundations and using resilient materials and construction techniques. - Incorporate climate projections into the design process to ensure that the asset can adapt to future changes in the local climate. By doing so, the infrastructure will be better prepared for the expected changes in temperature, precipitation, and other environmental factors. - Design the asset with modular components that can be easily replaced or upgraded to accommodate changing needs and demands. This approach will make the infrastructure more flexible and adaptable to evolving requirements, allowing it to better respond to future changes and challenges. - Use green infrastructure and nature-based solutions to enhance the resilience of the asset and surrounding site to climate impacts. These solutions can include a range of measures such as green roofs, rain gardens, and permeable pavements that help to manage stormwater runoff and reduce the risk of flooding. | - Design off-grid and mini-grids renewable energy systems that can be easily and cost-effectively scaled up to meet the changing energy demand due to climate change impacts. - Design and implement resilient cooling systems for power plants (thermal, solar, nuclear, biofuels, WTE, and fossil) by considering options such as reusing cooling water or adopting dry cooling systems. This will ensure energy security in case of water shortages.
23 | Implement Nature-Based Solutions for Increased Resilience | FALSE | TRUE | FALSE | Design | Nature-based solutions (NBS) and green infrastructure can be implemented to enhance resilience by increasing biodiversity through the protection and restoration of ecosystems, as well as through improved land management practices that enhance the natural environment. Even small-scale implementation of these solutions in infrastructure components can deliver a positive climate impact. Examples of NBS for climate mitigation purposes include green roofs and walls, rainwater harvesting systems, and bio-retention systems. NBS strategies also include conserving or restoring natural ecosystems adjacent to the infrastructure site while building new infrastructure. | - Conduct one (or multiple) of three different types of nature-based solution for climate adaptation: i) Protect ecosystems ii) Manage ecosystems iii) Restore ecosystems. - Depending on the results from the Climate Risk Assessment and the geographic area of the infrastructure, consider suitable nature-based solutions as a defense system of the infrastructure asset. For example, mangroves and wetlands can be used for flooding protection. - Investigate the potential for integration of nature-based solutions to the project in relation to local, site-specific socioeconomic, ecological and institutional context, so that the NBS is adapted to local conditions and challenges to ensure resilience and reduce unintended consequences. - Investigate the potential for implementing green infrastructure in design in smaller parts of the detail plan, for example as green rooftops as a natural precipitation mechanism. | - Implementing nature-based solutions adjacent to energy infrastructure can help increase the resilience and biodiversity in that area as well as making the infrastructure asset less vulnerable to climate shocks. - If the energy asset and/or facility is in a coastal or frequently flooded area, implementation of nature-based Solutions can protect the asset/facility. - For bioenergy projects conduct ecosystem restoration and management of forests.
28 | Include Environmental Management in Operations and Maintenance | FALSE | FALSE | TRUE | Operations & Maintenance | Developing an environmental management system facilitates mainstreaming of climate adaptation actions throughout the project. Adhering to international conducts and standardization agreements for environmental management advances transparency and accuracy in the project and incorporates climate adaptation measures to the fullest potential. Environmental management and efficient use of resources, leads to less vulnerable infrastructure, thus increasing the potential for climate adapted infrastructure. | - Consider using and following standardization within the ISO 14000-family and other ISO-standards for climate adaptation strategies in environmental management, especially the ISO 14090-series for adaptation. - Follow the International Electrotechnical Community (IEC) for standards regarding management of the technological components used in the asset. | - Consider using and following ISO 5001 For Energy Management Standards - Follow specific standardizations and guidelines on renewable energy by the IEC regarding management of technological components used for electricity generation, distribution, and transmission.
30 | Retrofitting for Increased Resilience | FALSE | FALSE | TRUE | Retrofitting | Infrastructure assets can be adapted to new situations and evolving societal needs through the incorporation of new technologies or repurposing the services they provide. Retrofitting can be used to modify the design of infrastructure assets, increasing their resilience and strength against the impacts of climate change and extreme weather events. By doing so, infrastructure assets can have an extended lifespan, operate more efficiently, and result in more secure provisioning of the infrastructure service. | - Retrofit by upgrading technological components to be more robust and endure direct future climate impacts as extreme weather events. - Retrofit by upgrading technological components to ensure they can withstand changes in demand or by indirect climate change impacts. Eg water shortages or higher demand for the service. - Use retrofitting to incorporate green infrastructure into existing design of the asset, for example by incorporation of green roofs for biodiversity. | - Retrofitting energy infrastructure can consist of increasing the resilience of the production site via retrofitting for the facility to be less vulnerable and withstand external climate shocks. - Retrofit cooling systems to not be dependant on large amounts of water for bio-, nuclear-, solar-, fossil-, and waste-to-energy plants. Implement dry or hybrid wet cooling systems. - Seismic retrofitting is especially crusial for nuclear power plants due to high consequences in case of disaster.
32 | Asset Management for Climate Risk Reduction | FALSE | FALSE | TRUE | Operations & Maintenance | Due to the increasing frequency and intensity of external disruptions caused by climate change, it is crucial to integrate reactive management of built infrastructure with consideration of future climate risks. By inspecting and assessing expected climate risks, the design and operation of the infrastructure can be modified to enhance resilience. Adopting a flexible and reactive approach to asset management that accounts for climate change can result in the development of resilient infrastructure over time. Asset management also includes proactive maintenance to ensure safe and efficient operation. | - Develop Climate-Resilient Asset Management with consideration of climate shocks by: i) Identifying climate hazards and connected vulnerabilities to the infrastructure asset. ii) Assessing the likelihood and consequences of the climate impact to determine the risk. iii) Devising a response strategy: Determine what policies, operations and maintenance changes, retrofits, or new infrastructure could be used to reduce the risk posed by the climate impact. iv) Assessing the response strategies by their cost and effectiveness. - Conduct consistent and proactive maintenance to ensure the asset remains within the safety margins | - Conduct frequent inspections and audits of technological components such as electrical connections, inverters, panels, turbines, and batteries to allow for component maintenance and disaster reduction for better adaptation capacity. - Secure energy for vital societal functions such as hospitals, water treatment facilities, and schools. This can be achieved, for example, by securing emergency power supplies. - Ensure the security of emergency power supplies.
33 | Contingency Plan for Climate Risks | FALSE | FALSE | TRUE | Operations & Maintenance | Climate change is causing more frequent and severe external disruptions, making it crucial to integrate reactive responses to breaches in the management of infrastructure assets. This includes developing a comprehensive contingency plan for climate risks to ensure timely and well-informed responses to unexpected failures. A clear contingency plan can reduce recovery time after disruptions and should consider future climate impacts and extreme weather events. Strong governance and clear assignment of responsibilities are essential to provide possibility for reactive and effective management. | - Develop a climate risk contingency plan that follows key principles in relation to climate change: i) Base the plan on a climate risk assessment for accurate emergency response. ii) If a climate risk can be foreseen, include a management plan to adapt operation for minimum disruptions on the demand side (risk prevention). iii) Include management guidelines in the contingency plan on how to recover from failure. iv) Create a tier-list of key nodes of the infrastructure system to be reconstructed first to secure vital societal functions. v) Ensure that the contingency plan states that disaster recovery staff and spare parts should be available at all times to react and respond to the disruption. - When developing the contingency plan, inspect the infrastructure project in relation to the Sendai Framework's priority action 4: "Enhancing disaster preparedness for effective response and to 'Build Back Better' in recovery, rehabilitation, and reconstruction | - Include risk assessment of services reliant on energy provisioning - Provide back-up energy generation to allow for reparation with general power outage - For a flexible demand-side management of energy system, predetermined loads can be disconnected to avoid loss of grid stability and avert possible widespread energy outages - Emergency resource planning for energy infrastructure, including transmission lines as they are extra vulnerable to climate shocks.
35 | Restore the Natural Environment after Infrastructure Decommissioning | FALSE | FALSE | TRUE | Decommisioning | Take action at the end-of-life stage of infrastructure assets to ensure that after decommissioning, the site should be reinstated to its original state as much as feasible. The restoration should support the maintenance of healthy and productive ecosystems to sustain ecosystem services and increase resilience in the environment. If there is no option to restore the natural environment, the brownfield area can be repurposed. | - Identify areas of soil or groundwater contamination, toxic wastes, and pollutants. - Treat the polluted areas and restore the site to support wildlife and ecosystem functions. Doing this will ensure biodiversity and resilience on site. - Restore the original vegetation by using indigenous and non-invasive species to ensure biodiversity. - Investigate if leaving the infrastructure could be beneficial for certain species. | - When a power plant is decommissioned, environmental remediation should be conducted to restore the area for resilience purposes. - For land-based energy production, separately retain and store topsoil and subsoil stripped from the construction areas for later use during reinstatement. - Investigate the benefits of leaving off-shore wind foundation as man-made coral reefs.