## Mitigation
No. | Activity Name | Lifecycle stage |  |  | Project stage(s) | Description of Activity | Implementation of Activity (general) | Implementation of Activity (energy specific)
|  | Planning | Delivery | Management
1 | Stakeholder Mapping and Engagement | TRUE | FALSE | FALSE | Project Preparation | Conducting an inclusive stakeholder mapping can identify all parties affected by the infrastructure project and its climate impacts. Identifying a broad spectrum of stakeholders is pivotal for contextualizing the project and ensuring that all parties with an ambition to contribute to lower emissions are involved. This can lead to more informed decision-making and better project outcomes, including more effective climate mitigation strategies. Additionally, planners and project managers should undertake continuous engagement-building exercises among stakeholders to increase communication, collaboration, and trust, and facilitate wide acceptance of the project. This can lead to improved environmental and social sustainability. | - Identify the users of the infrastructure asset and its associated services. - Identify stakeholders who would be directly and indirectly affected by climate impacts related to the project, such as decision makers, local communities, and civil society organizations. - Understand which actors have the power to influence and make decisions regarding the local environment. - Consider the willingness and capacity of local stakeholders to participate in a project over the long term. - Identify the skills and resources that different stakeholders can provide that will be beneficial to the project. - Understand the role of different stakeholders to minimize the risk of marginalizing or negatively impacting any particular group. | - Map stakeholders in the energy sector, including manufacturers, retailers, operators, local governments, local populations, landowners, energy users, and energy companies, to achieve effective energy projects that realize the full climate mitigation potential of the project. - Investigate potential land-use conflicts for some renewable energy projects, where stakeholder mapping should address interests in competing land-uses. - In the stakeholder mapping, include communities and connected civil society organizations that live and use existing natural resources within the target area, and downstream of planned interventions where systemic impacts may occur.
2 | Inclusive Public Participation for Climate Justice | TRUE | FALSE | FALSE | Project Preparation | Local communities and civil society organizations should be included in the decision-making process. Engagement of marginalized groups of society, including women and indigenous people, should be prioritized to ensure that project process and outcomes support climate justice. Increased acceptance of the project, identification of goal conflicts, and trade-offs between environmental and social factors are all supported by inclusive public participation. | - Increase public participation and prioritize information distribution about the project to enhance the quality of decision-making, incentivized by the Aarhus Convention. - Conduct inclusive participatory stakeholder consultation with diverse participatory methods. - Implement public participation in the EIA or SEA. - Conduct participatory pre-feasibility and feasibility studies to ensure uptake of social and environmental implications and trade-offs of the project. | - Public participation and inclusion of local citizens and civil society organizations are extra important for land-use decisions for renewable energy projects where spatial claims need to be made. - The transition towards a sustainable and renewable energy system benefits from involving the public, and strong democracies are important to support a political climate where society can influence the transition. - In the transition towards a renewable energy system, take consideration of communities dependent on fossil fuel extraction with social and economic consequences.
3 | Use of Indigenous and Local Knowledge | TRUE | FALSE | FALSE | Project Preparation | Indigenous and local knowledge (ILK) are skills and information that has developed through historical observations of local surroundings and are an asset for informed land-use decisions in an infrastructure project. ILK brings contextualization of the natural surroundings to the site of interest for exploitation and can provide valuable information of effective land use decisions and identification of long-term climate changes. When formal data collection is unavailable, ILK can be a complement to the scientific knowledge and should be used in the decision-making process to acquire full climate mitigation potential of the project. | - Use contextualized ILK in the decision-making process for better decision basis about the local area to complement the scientific data and project approaches in the project preperation. - Engage with local communities and indigenous groups from the outset of a project, and establishing mechanisms for ongoing communication and consultation throughout the project lifecycle | - For renewable energy projects, local and indigenous knowledge is important to incorporate in the decision-making process about land use decisions. Local communities attain valuable knowledge to complement the scientific decision basis.
4 | Policy and Legal Framework Assessment | TRUE | FALSE | FALSE | Infrastructure Planning | Robust policies and regulatory legal frameworks underpin effective delivery of infrastructure. The project lifecycle should include and comply with legal frameworks for climate mitigation and emission targets. Infrastructure practitioners have an important role to align projects to long-term decarbonization goals to shift investments to low-emission infrastructure. | - Understand and document the legal and policy framework for climate action and infrastructure planning in the country. - Act towards compliance with relevant emission targets and emission limits for the specific sector or area - Set the project in context of climate mitigation policies in the country by assessing national climate visions (e.g., NDCs or national sustainability goals when applicable) - Identify if the country of interest has developed a Climate Action Plan (CAP) or Nationally Appropriate Mitigation Actions (NAMAs) and adhere guidelines to engage in communal attempts to fulfill international targets for climate mitigation. | - Assess specific energy related targets and policies for your country - Identify potential energy specific action plans for your country. E.g., National Energy and Climate Plan (NECP), Sustainable Energy Action Plan (SEAP) or Sustainable Energy and Climate Action Plan (SECAP)
5 | Consider Interdependencies, Systems Planning and develop Cross-ministerial Cooperation | TRUE | FALSE | FALSE | Project Preparation | Analyze the plan, projects, or program as a component in the inter-sectoral infrastructure system and study the interdependencies between assets and sectors. Synergies for emission reduction and energy efficiency should be identified and exploited. Identifying potential trade-offs and goal conflict between assets or environmental impacts are important to reduce the risk of sub-optimization. To achieve a systems perspective, initiate collaborations between ministries for long-term planning of infrastructure to engage in wide-spread climate action. | - Assess connections and collaboration with other infrastructure sectors for identification of possible interdependencies. - Initiate cross-sectoral collaboration in early planning for mitigation benefits. - Undertake a systems-of-systems approach to critical infrastructure planning that exploits emission efficiencies for all connected assets and identify interdependencies and trade-offs. - Examine opportunities for industrial symbiosis. | - Collaborate with other sectors to support synergies and create a demand for clean and renewable energy. Undertake a systems perspective to energy systems planning where electricity production is connected to societal institutions, e.g., use of solar power for desalination plants. - The energy sector provides potential for electrification and decarbonasation of other sectors, such as electrification of the transport sector, where interdependet system planning is needed. - Consider sector-specific nexuses and how mitigation actions in energy infrastructure can support other sectors: i) WEF-nexus ii) Waste-to-energy nexus, E.g., usage of methane capture from landfill and waste heat from buildings and industrial processes
6 | Strategic Environmental Assessment | TRUE | FALSE | FALSE | Strategic Planning | Undertaking a Strategic Environmental Assessment (SEA) during the early stages of development or strategic planning of a plan, program, or policy ensures that environmental impact considerations are integrated into long-term infrastructure planning. Including climate change in the assessment ensures a comprehensive perspective on climate impacts, leading to better-informed plans and programs for infrastructure development related to climate mitigation. The SEA should be aligned with, and contribute to, the development of national climate action plans. By examining interlinkages with economic and social considerations, the SEA can provide a holistic perspective to enable well-informed infrastructure decisions that can withstand future societal and environmental changes | - Conduct a SEA in strategic planning with the ambition of evaluating how the plan or project performs in relation to strategies for climate mitigation. - Identify country specific GHG emission objectives and align the SEA accordingly (e.g. as specified in the NDC) - Consider the entire lifecycle of the energy program, from resource extraction to end-of-life disposal, to ensure a comprehensive assessment of the program's environmental impacts - Include indirect climate change impacts in the assessment - Use the SEA for decision-making by assessing multiple alternatives of the project with consideration of maximum performance of: i) energy consumption ii) energy efficiency iii) usage of renewable energy - Develop a monitoring and evaluation plan to ensure that mitigation measures are effectively implemented and to assess their effectiveness in reducing greenhouse gas emissions - Invest in profound stakeholder participation for successful realization of the SEA. | - Culmative climate mitigation effects can be captured through renewable energy generation programs on a significant dimensions to have an effect for regional or national climate action plans - Assess the potential environmental and social impacts in relation to climate change of the energy program, including potential effects on biodiversity, water resources, and human health
7 | Environmental Impact Assessment | FALSE | TRUE | FALSE | Infrastructure planning & Project preperation | An Environmental Impact Assessment (EIA) should be conducted, even if it is not legally required, and special focus on climate change should be integrated, apart from other environmental impacts. An EIA shall identify, describe and assess the direct and indirect effects of a project on ecosystems and humans. As climate change is directly linked to ecosystem degradation and pollution, climate impacts and GHG-emissions should also be covered in the EIA. The tool can be useful in formulating appropriate mitigation measures to reduce greenhouse gas emissions. | - Assess the regulatory framework for EIA related to the project in your region with identification of requirements for climate change considerations for the EIA - Country specific GHG emission objectives should be identified and used in the EIA (e.g., NDC) - Estimate the magnitude, composition, and intensity of GHG emissions from a lifecycle perspective in the EIA - Assess climate change impacts associated with the greenhouse gas emissions from infrastructure project. This could include impacts such as changes in temperature, precipitation, sea level rise, extreme weather events, and impacts on ecosystems. - Identify mitigation measures through the EIA to reduce GHG-emissions - Integrate climate mitigation strategies together with social, economic, and environmental issues posing threats to natural and human systems for thorough EIA delivery from a systems perspective
8 | Create Sustainable Path Dependence and Avoid Carbon Lock-ins | TRUE | FALSE | FALSE | Strategic Planning, Project Preparation | Infrastructure has a long lifetime and can therefore create lock-in effects. This means that unsustainable habits are cemented in society, which are hard to break, and the infrastructure continues to emit greenhouse gases for decades, even as the need to reduce emissions becomes more urgent. Investments in carbon-intensive infrastructure can limit the transition to low-carbon alternatives. It is therefore necessary to create a sustainable path dependence of infrastructure patterns to reduce emissions in line with internationally agreed goals on climate change. | - Analyze both the infrastructure asset and the service it provides to identify emission hotspots to understand where high-emitting lock-in effects can be created to steer prioritization of sustainable alternatives. - Incorporate flexibility and adaptability into design criteria to facilitate changes in design and operation due to changing conditions (e.g., fuel switching) to avoid carbon lock-in. | - The fossil fuel industry has social and economic path dependencies. Do not invest in unabated (without implementation of CCUS-technologies) fossil infrastructure, which creates a lock-in effect for the energy system. - Collaborate with other actors in the energy sector to create a demand for clean and renewable energy. International agreements and collaboration can help to break carbon lock-ins and create new, sustainable dependencies. For example, sign a Power Purchase Agreement (PPA), a long-term contract between the energy producer and the consumer. - Low-income countries that are dependent on fossil energy in the current system of low-carbon development must actively be steered by policies and subsidies towards a fossil-free energy transition. It is most crucial to remove subsidies for fossil energy
10 | Consideration of Land Use Efficiency in Planning | TRUE | FALSE | FALSE | Project Preparation | Climate change is directly linked to land use change, which disrupts the biogeochemical carbon cycle. Local considerations can have global implications. Quality land use management maximizes land-use efficiency and has quantitative impacts, as well as interlinkages to other sectors competing for land use. Therefore, thorough spatial planning, with a focus on land-use efficiency and accurate site selection, can minimize natural habitat disruption and reduce climate impacts. | - Consider the appropriate scale (e.g., in hectares) under management and the potential spatial scale of impacts. - Plan for infrastructure assets to be built around existing infrastructure or on brownfield sites to maximize efficiency and minimize land use change, with respect to other criteria for effective land use. Use for example the environmental system analysis tool Multi Criteria Decision Analysis (MCDA). - Optimize land use management to minimize the impact on surrounding ecosystems and mitigate climate change. - Consider the interactions within and between ecosystems, even for site-level or smaller scale projects, and measure the distribution of potential cumulative impacts (both positive and negative). | - To enhance the performance, cost-effectiveness and mitigation potential of renewable energy projects, planners should incorporate robust studies on resource potential to optimize energy efficiency. - Consider using Geographic Information Systems (GIS) to map site specific resource potential for: i) solar power project by analyzing irradiance maps ii) wind power project by analyzing wind speed maps iii) bioenergy project by analyzing potential for agroforestry and afforestation in combination to the project - Minimize exploitation of new land by planning renewable energy projects around already existing infrastructure, such as siting wind power turbines adjacent to roads and highways - Ensure that the infrastructure required for the renewable energy project, such as roads and transmission lines, is designed to minimize its impact on ecosystems and biodiversity, and to avoid sensitive areas.
13 | Set Quantitative Targets and Objectives for Compliance to International Climate Goals | TRUE | FALSE | FALSE | Infrastructure Planning | Specific and measurable project targets allows for transparency in the project and contributes to development of national mitigation pathways. Quantitative targets facilitate compliance to climate action policies and long-term targets such as the SDGs and the Paris Agreement. It is important that climate objectives are set for the entire life cycle of the project to mainstream climate action throughout the project. It is important that the targets are science-based and in line with international agreements and policies. | - Set limits for GHG-emissions for the project's lifecycle and make sure they are in line with climate mitigation policies and national objectives. Broaden the scope of emission reductions from Scope 1 and 2 (own and controlled sources and pruchased energy) to include scope 3 emissions (not directly owned by the organization) - The set targets should be in line with national objectives within the sector for uniform development of national mitigation pathways. - Consider the design of targets and how they are expressed (e.g., in absolute, percentage or output terms). | - Set targets for increased share of renewable energy generation to enhance incentives for investments in renewable energy projects. - Set targets for energy demand as it triggers improvement in efficiency and emission reductions from energy generation and supports efficiency in the use phase. Could be specific to different sectors of energy consumption, such as buildings, industry, transport. - Set targets for energy efficiency as it supports economic growth, reduces energy costs and is the best way to get the most out of existing resources.
14 | Set Quantitative Targets and Objectives for Climate Mitigation in Delivery | FALSE | TRUE | FALSE | Construction | Effective climate mitigation in infrastructure construction can benefit from setting clear and measurable quantitative targets for emissions reductions. These targets provide a roadmap for action and creates a framework for assessing progress in the project. By setting targets for renewable energy usage, embodied carbon reduction, waste minimization, and energy efficiency, infrastructure practitioners can significantly reduce emissions during the construction phase. Quantitative targets can also steers design choices and align the construction for a project in line with climate action. However, it is important to ensure that these targets are aligned with national policies and objectives, and that they are expressed in a clear and meaningful way. | - Set targets for renewable energy usage in construction. - Actively work for reduction of embodied carbon from construction material by working towards a set target for embodied carbon. This triggers efficiency improvments in sourcing of material by addressing emissions from raw material extraction, transportation of material, construction and end-of-life management. - Set targets for waste minimization at construction site - Set targets for energy efficiency in operation to facilitate mitigation strategies in delivery. Strict targets for efficiency attracts green technologies and mainstream usage of the most efficient appliances which can guide development of emission reduction technologies. - Make sure that the emission targets are in line with climate mitigation policies and national objectives. - Consider the design of targets and how they are expressed (e.g., in absolute, percentage or output terms). | - Set targets for energy efficiency as it supports economic growth, reduces energy costs and is the best way to get the most out of existing resources.
15 | Set, and Report to, Quantitative Targets and Objectives for Climate Mitigation in Operation | FALSE | FALSE | TRUE | Operations & Maintenance | Setting and reporting on quantitative targets and objectives for climate mitigation is crucial in the operation and management phase of infrastructure projects. By setting targets for emission reductions and quantifying emissions, the carbon footprint can significantly be reduced. It is important to update these targets throughout the project and adapt them to any changes, while ensuring that they are aligned with climate mitigation policies and national objectives. Consideration should also be given to the design of the targets and how they are expressed, to ensure they are clear, measurable, and achievable. Reporting according to global standards further communicates commitment to climate mitigation and can be effective to identify emission hotspots in operation to steer operation towards consistent improvements in efficiency. | - Quantify emissions to be aware of performance and the chances to meet the set emission targets. - Perform consistent emission reporting according to the Global Reporting Initiative to comply with the set targets in planning and operation phase. - Set targets for emission reductions in operation to constantly improve the climate performance of the infrastructure asset. - Update the targets throughout the project and adapt them to any changes. - Make sure that the emission targets are in line with climate mitigation policies and national objectives. - Consider the design of targets and how they are expressed (e.g., in absolute, percentage or output terms). | - Set targets for energy efficiency as it supports economic growth, reduces energy costs and is the best way to get the most out of existing resources.
16 | Share and Promote Best Practices for Climate Action in Infrastructure | TRUE | TRUE | TRUE | All project stages | Scaling up climate action in infrastructure requires strategic communication and outreach to ensure a transition towards a carbon neutral society. To most effectively achieve the transition, and speed up mainstreaming of climate action in infrastructure, lessons learned should be documented thoughout the project and be promoted them to stakeholders replicating the process. Sharing climate mitigation practices can help trigger transformative change. | - Knowledge and awareness of climate mitigation practices in infrastructure development should be built through increased collaboration and exchange of experience across sectors, facilitated by governments, donors, civil society organisations and private sector actors. - Share development through case studies to show how progress can be achieved in different national contexts - Share local solutions to climate mitigation to increase knowledge sharing about best practices for infrastructure commissioning - Publish evaluations of projects to spread information about best practices, incorporating communication about how the project aligned to national and international targets for climate action. - Share examples of innovative funding to facilitate mainstreaming of climate actions in infrastructure - Cover communication and cooperation of information spreading in a broad dimension of platforms, from research, newspapers, non-academic publications, municipal platforms, international forums etc. - Cover communication and publications with inclusion of all stakeholders including national ministries, municipal governments, private sector platforms, NGOs, historically marginalised populations and international development partners. | - New technologies for clean energy often emerge in developed economies and should be promoted to countries not involved in the initial technological development for direct clean energy transition - Promote best practices of energy infrastrucuture projects that adhere to, or fulfil, national/international targets for energy efficiency and emission standards
17 | Public Private Partnerships for Climate Action | FALSE | TRUE | FALSE | Procurement | To ensure climate action is integrated throughout a project, the different lifecycle stages should be addressed early in planning to ensure value in the procurement. Public-private partnerships (PPP) is a model where an entire project is contracted to a private company, meaning that the company will obtain the responsability of the quality of the asset throughout the lifecycle of the project, including operations and maintenance. This will result in longer contracts where planning for mitigation strategies can be included in the delivery phase as well as maintenance and operations. Considering climate change in PPPs will ensure that environmental performance is held under the entire infrastructure lifetime and will encourage innovation in sustainability and emission reduction. | - Include climate change and mitigation strategies in the PPP criteria - Embed climate mitigation in all four stages of PPP: i) Project identification ii) Business Case iii) Transaction iv) Contract Management - The PPP should result in coordinated mitigation actions and reduction of emissions by undertaking a lifecycle perspective for better overview and transparency of the project. Material flows can be addressed holistically and can therefore be used as a way to reduce emissions. | - Contract a specialized private partner from the energy sector for the whole lifecycle of a project to ensure mitigation strategies are incorporated throughout all the lifecycle stages. - Embed Climate Resilience in PPP for the Power Project Procurement.
20 | Green Public Procurement | TRUE | FALSE | FALSE | Procurement | When governments contract a company for an infrastructure project, green public procurement (GPP) can be implemented to ensure climate action is incorporated in the procurement criteria. This means that procurement should be coined with mitigation strategies as a criteria to ensure low environmental impact throughout the project lifecycle. Doing so, GPP has the potential to reduce GHG-emissions. Fundamental in GPP is to not only base the decision on the lowest cost, but rather the lifecycle costing, including externalities. Additionally, GPP demonstrates the importance of considering economic, social and environmental factors when determining best value. | - Set clear sustainability criteria for the GPP. Examples of criteria to be met by potential suppliers include: i) GHG-emissions ii) Energy efficiency iii) Share of renewable energy usage iv) Low embodied carbon of material - Enhance transparency in the project by specifying GHG-calculations in delivery and operation (e.g., via LCA or GHG reporting) - Encourage waste reduction and recycling in procurement specification - Value mitigation strategies on performance of GHG-emission reduction/USD for the most cost-effective mitigation strategies proposed in the procurement
22 | Implement Nature-Based Solutions for Climate Mitigation | FALSE | TRUE | FALSE | Design | Nature-based solutions (NBS) and green infrastructure can be implemented to increase carbon sequestration and mitigate climate change through the protection and restoration of ecosystems, as well as improved land management for enhancing the natural environment, resulting in natural cooling of the Earth. Even small-scale implementation of these solutions in infrastructure components can deliver a positive climate impact. Examples of NBS for climate mitigation purposes include green roofs and walls, rainwater harvesting systems, and bio-retention systems. NBS strategies also include conserving or restoring natural ecosystems adjacent to the infrastructure site while building new infrastructure. | - Conduct one (or multiple) of three different types of nature-based solution for climate mitigation: i) Protect ecosystems ii) Manage ecosystems iii) Restore ecosystems. - Focus on the type of nature-based solutions that enhances supporting ecosystem services and promotes carbon sequestration, for example restoring and conserving forests and coastal ecosystems. - Investigate the potential for integration of nature-based solutions to the project in relation to local, site-specific socioeconomic, ecological and institutional context, so that the NBS is adapted to local conditions and challenges to reduce unintended consequences. - Investigate the potential for implementing green infrastructure in design in smaller parts of the detail plan for enhanced carbon sinks and increased carbon sequestration. | - Consider implementation of nature-based solutions on production site buildings (e.g., roofs of power plants, watersheds for hydropower) or in combination with renewable energy constructions for coupled NBS-renewable energy systems. - Investigate the potential for nature-based solutions adjecent to and under transmission lines for ecosystem restoration and sustainable management purposes. - For bioenergy projects, conduct ecosystem restoration and implement NBS-techniques in management of forests.
24 | Implement Circular Economy Practices in Design | FALSE | TRUE | FALSE | Design | Implementation of circular economy practices can reduce emissions in the lifecycle of the infrastructure project. Pursuing circular material flows allows for a higher share of recycled material in construction, reduced material losses and ultimately lower material footprints and associated emissions. Additionally, designing for easy replacement of components allows for decoupling the lifetime of the asset from the lifetime of the component. This supports recycling and reuse of components, leading to reduced emissions. | - Consider implementation of recycled material in construction instead of virgin material (e.g. reuse of structural steel or concrete) - Investigate possibilities for Modularity in design or Design for easy Disassembly - Consider implementation of innovative material with incorporation of reused material - Proactively prepare components for decommissioning by designing them for easy deconstruction. - Study interdependencies with other sectors and infrastructure systems and investigate possibilities for industrial symbiosis | - Energy infrastructure can be designed for modularity and reuse. See example of utility-scale solar PV facilities can be repurposed and provide components for development of smaller-scale community or household use PV - Investigate waste and by-products, created by the energy system and other sectors, that could be used for energy generation. - Consider Industrial Symbiosis for bioenergy production
25 | Embodied Carbon and low-emission Sourcing of Materials | FALSE | TRUE | FALSE | Design & Contruction | Embodied carbon for a material is all the carbon emitted in the acquisition of raw materials, their processing, manufacturing, transportation to site, and construction throughout the whole life cycle. Embodied energy is, ergo, the energy used in the entire lifecycle of a material. Embodied carbon calculations incorporate the end-point emissions embedded in the materials. Since infrastructure assets require large amounts of construction materials it is important to consider the material choice with the least embodied carbon (or embodied energy) as a mitigation strategy. | - Calculate the embodied carbon and embodied energy for materials used in construction to guide low-emission material choices. Full calculation of embodied carbon includes emissions connected to the lifecycle of the material, including i) Excavation, refining and processing of raw material ii) Transport to site iii) The constructuion/assembly of material itself iv) End-of-life emissions from recycling of disposal of the material - Consider material swapping from material with high embodied carbon (steel, cement, and concrete) to lower carbon materials (biobased and recycled materials). - Identify risks of burden shifting of emissions to other parts of the infrastructure lifecycle due to material choices. For example, a material with lower embodied carbon might lead in lower enegy efficiency and result in increased emissions during operation. When there is a likelihood of burden shifting, consider conducting a Life Cycle Assessment (LCA) with focus on embodied carbon. | - Calculate embodied carbon of key materials for the energy infrastructure, such as the construction material for wind turbine blades and foundation, solar panels with mountaing and racking components and inverters, materials for dam and intake structure for hydropower - Include carbon emissions associated with raw material extraction, transportation, assembly and end-of-life management of the material for the energy project - For wind power project, the wind turbine blades generally embodies the most carbon out of all components. Material choices should be based on embodied carbon in construction, end-of-life emissions in relation to the electricity output. - Conduct calculations of embodied energy of supporting infrastructure, such as transmission and distrubution facilities
26 | Life Cycle Assessment in Construction | FALSE | TRUE | FALSE | Construction | Life Cycle Assessment (LCA) covers emissions from all life cycle stages and avoids burden shifting between lifecycle stages, as well as including upstreams and downstreams impacts. A LCA allows for identification of all environmental impacts and dependencies between GHG-emissions, pollution, radiative emissions, toxicity, water and soil contamination and more. Conducting a LCA for the construction phase of an infrastructure project captures potential emission hotspots in the construction to steer design choices to lower the climate and environmental impact. | - Conduct a LCA for construction and design planning to streamline emission efficiency in construction and delivery. Choose one out of the two following approaches: i) For a simplified method specifically developed for industry usage, use LCA tools such as OneClickLCA. ii) A detailed LCA requires specific LCA competence but gives a more thorough result, in that case, use full content tools such as OpenLCA, SimaPro or GaBi. - For efficient execution of the LCA, Follow ISO:14040 standards with extra caution payed to: i) Formulate a robust scope for the LCA that encaptures the entire lifecycle of the project and accounts for emissions with impact to climate change, not only GHG-emissions ii) Choose an appropriate functional unit that relates to the main function of the infrastructure project iii) Include all impact categories if possible for holistic assessment. If inevitable, make transparent descriptions for chosen impact categories. - Use results from LCA as a hotspot analysis to identify burdensome lifecycle stages and components in design, with broad analysis of alternative options for emission reduction possibilities - Make results from LCA transparent to investors in compliance to local laws and regulations in order to promote further green investments in infrastructure projects. | - LCA adapts a lifecycle perspective that avoids burden-shifting between lifecycle stages, which is especially relevant for renewable energy projects that often entail low emissions from the operation phase. It is though pivotal to address the entire lifecycle which includes heavy emissions from raw-material extraction and production - For fuel-based projects (fossil, nuclear and biomass), widen the scope to include the lifecycle of fuel supply to provide a robust LCA - Choose a functional unit that corresponds to the energy output and in compliance to other LCAs in the sector for easy comparison and transferability - Widen the impact categories from solely focusing on climate change as depletion of natural resources and toxicity is sensitive for energy projects with long lifetimes and indirectly connected to climate change.
27 | Life Cycle Assessment for Energy Efficient Management | FALSE | FALSE | TRUE | Operations & Maintenance | Life Cycle Assessment (LCA) covers emissions from all life cycle stages and avoids burden shifting between lifecycle stages, as well as including upstreams and downstreams impacts. A LCA allows for identification of all environmental impacts and dependencies between GHG-emissions, pollution, radiative emissions, toxicity, water and soil contamination and more. Conducting a LCA captures potential emission hotspots from the project to steer environmental management towards the most crucial activities for climate mitigation reasons and can be used to update operation. An LCA could also be used in communication about the project and contribute to mainstreaming of effective environmental management of infrastructure assets. | - Conduct a LCA after commission, during operation, to streamline emission reduction in management of the infrastructure asset. Choose one out of the two following approaches: i) For a simplified method specifically developed for industry, use LCA tools such as OneClickLCA. ii) A detailed LCA requires specific LCA competence but gives a more thorough result, in that case, use full content tools such as OpenLCA, SimaPro or GaBi. - For efficient execution of the LCA, Follow ISO:14040 standards with extra caution payed to: i) Formulate a robust scope for the LCA that encaptures the entire lifecycle of the project and accounts for emissions with impact to climate change, not only GHG-emissions ii) Choose an appropriate functional unit that relates to the main function of the infrastructure project iii) Include all impact categories if possible for holistic assessment. If inevitable, make transparent descriptions for chosen impact categories - Use results from LCA as hotspot analysis to identify burdensome operations with broad analysis of alternative procedures and alternative material usages in operation. - Make results from LCA transparent to investors in compliance to local laws and regulations in order to promote further green investments in infrastructure projects. - Use the results for increased communication of mainstreaming climate friendly environmental management of infrastructure assets | - LCA adapts a lifecycle perspective that avoids burden-shifting between lifecycle stages, which is especially relevant for renewable energy projects that often entail low emissions from the operation phase. It is though pivotal to address the entire lifecycle which includes heavy emissions from raw-material extraction and production as well as fuels used for transportation in the operations phase. - For fuel-based projects (fossil, nuclear and biomass), widen the scope to include the lifecycle of fuel supply to provide a robust LCA - Choose a functional unit that corresponds to the energy output and in compliance to other LCAs in the sector for easy comparison and transferability - Widen the impact categories from solely focusing on climate change as depletion of natural resources and toxicity is sensitive for energy projects with long lifetimes and indirectly connected to climate change.
28 | Include Environmental Management in Operations and Maintenance | FALSE | FALSE | TRUE | Operations & Maintenance | Developing an environmental management system in facilitates mainstreaming climate mitigation actions throughout the project. Adhering to international conducts and standardization agreements for environmental management advances transparency and accuracy in the project and incorporates climate mitigation measures to the fullest potential. Environmental management and efficient use of resources, as well as emission efficiency in operation leads to more effective infrastructure, thus lowering life cycle emissions from the project. | - Consider using and following standardizations within the ISO 14000-family and other ISO-standards for climate mitigation strategies in environmental management. - Follow the International Electrotechnical Community (IEC) for standards regarding management of the technological components used in the asset. | - Consider using and following ISO 5001 For Energy Management Standards - Follow specific standardizations and guidelines on renewable energy by the IEC regarding management of technological components used for electricity generation, distribution, and transmission.
29 | Retrofitting for Climate Mitigation | FALSE | FALSE | TRUE | Retrofitting | Retrofitting of an infrastructure asset can significantly enhance the lifetime and operational efficiency of the asset by continually upgrading its technology. This approach enables infrastructure assets to reduce its emissions or to repurposed to meet changing societal needs and utilized in new situations, ultimately resulting in a reduction of lifecycle GHG emissions. | - For compliance to societal ambition for fossil fuel phase out, retrofit or repurpose fossil fuel infrastructure to reduce emissions instead of early retiring - Retrofit by incorporation of Carbon Capture, Utilization and Storage (CCUS). - Make use of retrofitting for efficient asset management to increase energy efficiency, for example by incorporation of new technology or upgrading existing components. - Use retrofitting to incorporate green infrastructure into existing design of the asset, for example by incorporation of green roofs. - Lock-in infrastructure can be repurposed by retrofitting. - At end-of-life, repurpose the asset to another sector to omit emissions from new construction in another infrastructure lifecycle. | - Retrofit existing coal- and gas-fired plants to co‐fire with hydrogen. - Fossil fuel power plants can be retrofitted for carbon capture storage (CCS). - Retrofitting by altering and redesigning cooling systems to use recovered heat in bio-, nuclear-, solar-, fossil-, and waste-to-energy plants can decrease emissions. - Investigate the possibility to increase recycling of cooling-water - Repurpose fossil energy infrastructure at end-of-life to support other services and make use of existing building stock (e.g coal power plant repurposed for nuclear energy with SMR or for energy storage).
31 | Proactive Maintenance | FALSE | FALSE | TRUE | Operations & Maintenance | A proactive approach to asset maintenance involves monitoring and inspecting components and replacing exhausted ones early. Proactive maintenance provides less margin for error before drastic management measures need to be implemented, extending the lifespan of the infrastructure asset and leading to reduced emissions associated with new or additional construction. It also decouples the infrastructure lifetime from the lifetime of certain components | - Conduct regular audits and inspection schemes to identify potential breaches in operation before they need to be replaced. This ensures a longer lifetime for components and the entire infrastructure asset. - Develop a maintenance schedule according to ISO standards. - Have an Asset Management Plan with a focus on reducing emissions. For example, prioritize assets with the biggest material footprint. - Train and empower staff. Ensure that staff are trained and empowered to conduct proactive maintenance tasks, and that they understand the importance of identifying and addressing potential issues before they become major problems. | - Conduct frequent inspections and audits of technological components such as electrical connections, inverters, panels, turbines, and batteries to allow for component maintenance rather than system-wide replacement. This can reduce the material footprint and, thereby, GHG emissions.
34 | Decommisioning with Circular Economy Practices | FALSE | FALSE | TRUE | Decommisioning | Implementation of circular economy practices can reduce emissions in the end-of-life stage of the infrastructure. Decommissioning with focus on circular material flows allows for reduced material losses and therefore reduced GHG emissions. Increased material separation at decommissioning results in lower needs for raw material extractions in the next cycle and reduces the need for landfilling. A detailed material recovery at end-of-life management should be considered to increase resource efficiency and reduce the material footprint. | - Have a decommissioning plan that embeds circularity. - Incorporate circular economy principles in the decommissioning by: i) Considering reusing or repurposing the asset and/or brownfield area by retrofitting. ii) Investigating the opportunity for components and materials to be reused or repurposed for another asset lifecycle. iii) Investigating the opportunity for components and materials to be separated and recycled. - Address the challenges of material recovery by including material separation for reuse and recycling of components and/or construction material | - Repurpose fossil energy infrastructure at end-of-life to support other services and make use of existing building stock (e.g., coal power plant can be repurposed for nuclear energy with SMR or for energy storage). - Separate materials to sub-components to simplify material recovery and recycling. For example, most parts of solar PVs can be recycled (glass, aluminium, plastic etc.) - Follow the waste hierarchy for guidance on how to minimiza waste and incentivise re-use and reycling of material (Prevent, re-use, recycling, recovering, disposal)