Additional File 5

Appendix 5: Feedback Loops Documentation Tool

| Intervention Component | Barriers | Facilitators | Proposed MicroTweak Description | Justification/Rationale | Decision-Making Process Notes |
| --- | --- | --- | --- | --- | --- |
| HemoDemo | Women aren't staying until the end of the HemoDemo sessions to review group-level reports after receiving their own. | NA | Individual reports will now be provided at the enf of each session so that women stay for the group-level reports. | This change in operational efforts allows us to incorporate the normative implementation activity necessary to demonstrate to our study participants how anemia is an issue among women of reproductive age in their villages. | MicroTweak was implemented upon identification at the discretion of the State Implementation Mgr |
| HemoDemo |  | Demand for Hg testing is beyond anticipated levels especially this early in the implementation phase. | Wait-lists have been started in implementation areas with high demand for Hg testing. | Ethically we must accommodate women who request testing as our resources permit. We will continue to monitor the demand levels and consider macro tweaks, if necessary. | MicroTweak was implemented upon identification at the discretion of the State Implementation Mgr |