Additional File 1

Appendix 1: Sample Template for RANI’s Monitoring and Evaluation Framework

| T4 SESSIONS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EQ1. To what extent was fidelity to implementation maintained during the implementation of the T4 sessions in the RANI project? - What were the total number of T4 sessions conducted per village? |  |  |  |  |  |  |  |  |
| OUTPUT | DATA TOOL | ITEMS | RESPONSIBLE PARTY | DATA ENTRY FREQUENCY | INDICATORS | REPORTING FREQUENCY | VISUALIZATION | HOW WILL WE USE THIS INFORMATION? |
| Fidelity to implementation – Dose & Coverage | CFIF | Section 2 2-6 | Community Facilitator | Within 4 days post activity completion | - Total number of T4 sessions conducted by village | Monthly | - Heat map with frequencies | - IPE Global and DC team will be able to track the roll-out of T4 sessions on the ground |