Supplementary material

# Implementation Guide: A practical 10-item checklist

These operational steps are presented in a logical order, but not every rollout will follow this precisely as a range of factors will influence. First, or at least very early on, the implementing organisation (eg District Health Board or Primary Health Organisation) should identify a YouthCHAT Organisational Administrator(s), who will take on some, if not all, of the below tasks.

| 1 | State problem or goal (eg a need to increase screening rates in a region) |  |
| --- | --- | --- |
| 2 | Identify stakeholders – those who will be affected by the implementation (e.g. end users and local community) – for communication and consultation purposes |  |
| 3 | Assess (and document) current screening practices and relevant workflows |  |
| 4 | Identify barriers and challenges to both acceptance and uptake |  |
| 5 | Establish (and communicate) clear criteria for screening, as well as specific targets |  |
| 6 | Check IT or resource requirements (e.g. update Wi-Fi or buy e-tablet) |  |
| 7 | Conduct initial training and provide users with logins and support materials |  |
| 8 | Establish a screening protocol that is integrated with existing workflow |  |
| 9 | Determine the YouthCHAT settings for the clinic (e.g., introduction, language, modules switched on/off) |  |
| 10 | Follow-up with users to see if more training or barrier resolution is needed, and review goals/targets, criteria and procedures |  |