Logic Model  - Peer Health Equity Navigator (PEN) Intervention

| Main Goal | - To improve vaccine and health literacy and reduce barriers to health care among ACB communities in Ottawa |  |  |  |
| --- | --- | --- | --- | --- |
| Sub Goals | - To develop and implement a PEN training program and intervention - To implement PENs in partner health organizations / ACB community - To generate evidence re: PEN model and integrate PEN model into partner and health organizations |  |  |  |
| Components | Recruitment & Selection | Training | PEN Community Engagement | Research and KT |
| Activities – Inputs | Outreach, awareness, and recruitment of PENs | Blended learning program Practica in partner (and other health) agencies | Community engagement events | KT and information-sharing activities |
| Target Population | - ACB community members in Ottawa | - PEN students/trainees - Partner and health organizations | - ACB clients/community members | - Partner organizations - Health organizations - Health policy planners |
| Implementation Objectives | - To share info about the PEN program in ACB communities - To receive a minimum of 20 applications / cohort - To select a minimum of 6 – 10 PENs / cohort | - To develop 12 training modules - To provide online training events over an 8-week period - To have 6-10 PENs complete training per cohort - To have PENs complete an 8-week practicum with a partner organization | - To have PENs host a minimum of 10-12 educational events/practicum / cohort | - To share research and evaluation findings re: PEN intervention with key stakeholders |
| Outputs (Process Indicators) | - #/type of applicants / cohort - #/type of PENS selected / cohort | - # of modules completed/student - # of students completing the training / cohort - # of certificates awarded per cohort - # of PEN graduates who complete a practicum with a partner agency / cohort | - # of educational events hosted per PEN/ practicum - # of ACB attendees per event | - # of research reports / policy briefs developed from the research |
| Short-Term Objectives | - To increase awareness of the PEN program among individuals and organizations - To recruit and train additional PEN cohorts - To increase # of PEN applications per cohort | - To obtain positive feedback from students on program content and format - To reduce the # of students who dropout of the program - To increase students’ knowledge, confidence, and skills in vaccine and health promotion - To obtain positive feedback from preceptors/agency leads on PEN activities | - To increase access and information to vaccine and health information in ACB communities | - To have PEN model adopted by partner and health organizations |
| Short-Term Indicators1 | - % increase in # of applications per cohort | - % of students who report satisfaction with content and format of the program - % of students who report increased knowledge, confidence and skills in vaccine and health promotion - % of preceptors/ agency leads who report satisfaction with the practica - % of preceptors/agency leads who report positive impacts of PENs in ACB communities | - % of attendees reporting increased knowledge and literacy in making decisions about vaccines and health | - %/type of partner and health organizations who adopt PEN intervention - Funding |
| Long-Term Objectives | - To increase # of organizations with trained PENs | - To continuously review student perspectives on PEN training program - To continuously review preceptor/agency lead perspectives on PEN training program and practica - To integrate PENs into partner and other health agencies to address ACB health inequities - To continue to engage PEN trainees in health promotion activities | - To continuously engage with ACB community members to promote vaccines and health | - To continue to conduct KT activities and promote PEN model in health organizations working with ACB communities |
| Long-Term Indicators | - % increase in # of organizations who engage/hire/retain PENs | - %/type of trainees/preceptors/agency leads who provide positive program feedback - % of preceptors/agency leads who report changes in organizational practice - %/type of PEN trainees who report continuous engagement in health promotion activities | - %/type of partner and health agencies reporting positive long-term impacts of PENs on ACB health inequities |  |