Appendix Table 3. Guideline Adaptation Working Plan

| Timeline | Corresponding Modules | Assigned to | Tasks | CPG Phase |  |
| --- | --- | --- | --- | --- | --- |
| January 2017 | Preparation Module | CPG Adaptation Group (GAG) | Prepare for the Adaptation Process - Decide on health topic area - Assess feasibility of adaptation - Identify needed resources - Establish multidisciplinary panel (adaptation working group) - Write/ submit protocol - Identify endorsing body - Discuss authorship and accountability - Discuss dissemination and implementation | Meeting 1 | Set Up Phase |
| February 2017 | Preparation Module | GAG | - Decide on terms of reference/consensus process - Establish CPG inclusion/exclusion criteria - Help identify key search terms - Help identify key documents/ sources - Capacity building for CPG adaptation methodology (KSU-Modified-ADAPTE) | Meeting 2 | Adaptation Phase |
|  | Scope and Purpose Module | GAG | Define Health Questions Refine topic area |  |  |
| March 2017 April 2017 April 2017 | Search and Screen Module Assessment Module | GAG | Search & Screen CPGs - Complete CPG Search - Narrow list of CPGs (if needed) by inclusion/ exclusion criteria Assess CPGs - Complete AGREE II appraisal - Assess CPG currency - Complete evaluations (literature search and evidence, consistency of evidence and conclusions, conclusions and recommendations) for all recommendations (optional) - Prepare recommendations matrix - Assess acceptability | Meetings3-5 |  |
| July 2017 | Decision and Selection Module | GAG | Decide & Select - Review all data - Decide on recommendations for adapted CPG | Meeting 6 |  |
| March 2018 | Customization Module | GA | Draft CPG Report Write first draft of CPG and/or report on process | Online communication | Finalization Phase |
| July 2018 |  | GAG | Approve first draft by CGC-s (Clinical content and Methodology) | Online Communication |  |
| December 2018 – February 2019 | External Review Module | External Review Panel for clinical content and methodology | External Review - Send for external review and consultation (Clinical content and Methodology) - Get formal endorsement |  |  |
| April-May 2019 December 2019 | Aftercare planning Module | GAG | Discuss feedback Review and consultation | Meetings 7-10 |  |
|  |  | GAG | Plan for Future review & update Decide on update process |  |  |
|  | Final Production Module | GAG | Produce Final CPG Create final adapted CPG Including Implementation tool(s) and Performance Measures | Meeting 11 |  |
| July 2020 |  | GAG | Consider implementation issues and strategies based on the Implementation tools and performance measures. | Online communication | Implementation Phase |

Appendix Table 4. Assessment of Currency of the Selected Source CPG

Currency Survey of the CPG Developer

Source CPG: Attention deficit hyperactivity disorder: diagnosis and management. NICE guideline [NG87]. Published date: 14th of March 2018

- Are you aware of any new evidence relevant to this CPG statement? No

- Is there any new evidence to invalidate any of the recommendations comprising the CPG? No

- Are there any plans to update the CPG in the near future? No

- When the CPG was last updated? 13th of September 2019 What is the citation for the latest version? https://www.nice.org.uk/guidance/ng87

Appendix Table 5. Decision support record for the ADHD CPG adaptation group (GAG) using the KSU-Modified-ADAPTE methodology

| PHASE | MODULE | STEP | TOOL | DECISION |  | REASON (if not utilized) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Utilized | Not utilized |  |
| ONE: SET-UP | - Preparation | 1 | 1 | √ |  |  |
|  |  |  | 2 | √ |  |  |
|  |  | 2 |  | √ |  |  |
|  |  | 3 |  | √ |  |  |
|  |  | 4 |  | √ |  |  |
|  |  | 5 | 3 | √ |  |  |
|  |  |  | 4 | √ |  |  |
|  |  |  | 1 | √ |  |  |
|  |  | 6 | 5 | √ |  |  |
| TWO: ADAPTATION | 2.1. Scope and Purpose | 7 | 6 | √ |  |  |
|  | 2.2. Search and Screen | 8 | 2 | √ |  |  |
|  |  |  | 7 | √ |  |  |
|  |  | 9 | 8 | √ |  |  |
|  |  | 10 | 9 |  | √ | Not utilized. The GAG decided to rely on inclusion/ exclusion criteria and PIPOH compatibility |
|  |  |  | 10 |  | √ |  |
|  | 2.3. Assessment | 11 | 9 | √ |  |  |
|  |  |  | 10 | √ |  |  |
|  |  | 12 | 11 | √ |  |  |
|  |  | 13 | 12 |  | √ | Not utilized. The GAG decided to select and adopt all the recommendations from one Source CPG: NICE NG87 |
|  |  | 14 | 13 |  | √ | The GAG decided to rely on Domain 3 scores of the AGREE II appraisal |
|  |  |  | 14 |  | √ |  |
|  |  | 15 | 15 |  | √ | The GAG decided to rely on Domains 2 and 5 scores of the AGREE II appraisal |
|  | 2.4. Decision and Selection | 16 |  | √ |  |  |
|  |  | 17 |  | √ |  | Decision making and selection (5 options). The GAG adopted the recommendations with their evidence. |
|  | 2.5. Customization | 18 | 16 | √ |  |  |
| THRE: FINALIZATION | 3.1. External Review and Acknowledgment Module | 19 | 17 | √ |  |  |
|  |  | 20 |  | √ |  |  |
|  |  | 21 |  | √ |  |  |
|  |  | 22 |  | √ |  |  |
|  | 3.2. Aftercare Planning | 23 | 18 | √ |  |  |
|  | 3.3. Final Production | 24 |  | √ |  |  |