## Template 1
Strategy | Activities | Resources
Audit and feedback | Meet with stakeholders to identify outcomes | Project officer
| Retrieve and analyse data on outcomes | Team leader A
| Present data to stakeholders | Team leader B
Clinical team A - champion
Clinical team B - champion
Involve existing governing structures | Meet with executives | Project officer
| Meet with clinical team/s | Executive A
Executive B
Team leader A
Team leader B
Identify and prepare champions | Engage with stakeholders to identify potential champions | Project officer
| Engage (meetings or emails) with possible champions | Team leader A
| Ongoing support for champions | Team leader B
Clinical team A - champion
Clinical team B - champion
Train-the-trainer | Adapt training with stakeholders | Project officer
| Train the champions to be trainers | Team leader A
| Create opportunities for the trainers to train others | Team leader B
| Monitor training progress | Clinical team A - champion
Clinical team B - champion
Training material
Training room

## Template 2A
Index | Activity | Purpose | Strategy | Role | Hourly wage rate | Number of personnel involved | Time spent per person (mins) | Total person minutes | Labour ($) | Notes
1 | Meet with executives | present intervention aims and outcomes | Involve existing governing structures | Project officer | 85.21 | 1 | 30 | 30 | 42.605
1 | Meet with executives | present intervention aims and outcomes | Involve existing governing structures | Executive A | 134.0765 | 1 | 30 | 30 | 67.0383
1 | Meet with executives | present intervention aims and outcomes | Involve existing governing structures | Executive B | 150.4776 | 1 | 30 | 30 | 75.2388
2 | Meet with clinical team/s | present intervention aims and outcomes | Involve existing governing structures | Project officer | 85.21 | 1 | 30 | 30 | 42.605
2 | Meet with clinical team/s | present intervention aims and outcomes | Involve existing governing structures | Team leader A | 97.2914 | 1 | 30 | 30 | 48.6457
2 | Meet with clinical team/s | present intervention aims and outcomes | Involve existing governing structures | Team leader B | 115.62 | 1 | 30 | 30 | 57.81
3 | Meet with stakeholders to identify outcomes | meeting to identify what needs to be audited and how to feed it back | Audit and feedback | Project officer | 85.21 | 1 | 60 | 60 | 85.21
3 | Meet with stakeholders to identify outcomes | meeting to identify what needs to be audited and how to feed it back | Audit and feedback | Team leader A | 97.2914 | 1 | 60 | 60 | 97.2914
3 | Meet with stakeholders to identify outcomes | meeting to identify what needs to be audited and how to feed it back | Audit and feedback | Team leader B | 115.62 | 1 | 60 | 60 | 115.62
4 | Engage with stakeholders to identify potential champions | email asking for champion suggestions | Identify and prepare champions | Project officer | 85.21 | 1 | 10 | 10 | 14.2017
4 | Engage with stakeholders to identify potential champions | champion suggested via email | Identify and prepare champions | Team leader A | 97.2914 | 1 | 10 | 10 | 16.2152
4 | Engage with stakeholders to identify potential champions | champion suggested via email | Identify and prepare champions | Team leader B | 115.62 | 1 | 10 | 10 | 19.27
5 | Engage (meetings or emails) with possible champions | met with clinical team A champion | Identify and prepare champions | Project officer | 85.21 | 1 | 30 | 30 | 42.605
5 | Engage (meetings or emails) with possible champions | met with clinical team A champion | Identify and prepare champions | Clinical team A - champion | 78.8025 | 1 | 30 | 30 | 39.4012
6 | Engage (meetings or emails) with possible champions | met with clinical team B champion | Identify and prepare champions | Project officer | 85.21 | 1 | 30 | 30 | 42.605
6 | Engage (meetings or emails) with possible champions | met with clinical team B champion | Identify and prepare champions | Clinical team B - champion | 56.873 | 1 | 30 | 30 | 28.4365
7 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | Project officer | 85.21 | 1 | 60 | 60 | 85.21
7 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | Team leader A | 97.2914 | 1 | 60 | 60 | 97.2914
7 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | Team leader B | 115.62 | 1 | 60 | 60 | 115.62
7 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | Clinical team A - champion | 78.8025 | 1 | 60 | 60 | 78.8025
7 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | Clinical team B - champion | 56.873 | 1 | 60 | 60 | 56.873
8 | Adapt training with stakeholders | Incorporate adaptations to training | Train-the-trainer | Project officer | 85.21 | 1 | 60 | 60 | 85.21
9 | Train the champions to be trainers | same as activity | Train-the-trainer | Project officer | 85.21 | 1 | 60 | 60 | 85.21
9 | Train the champions to be trainers | same as activity | Train-the-trainer | Clinical team A - champion | 78.8025 | 1 | 60 | 60 | 78.8025
9 | Train the champions to be trainers | same as activity | Train-the-trainer | Clinical team B - champion | 56.873 | 1 | 60 | 60 | 56.873
10 | Create opportunities for the trainers to train others | book meeting room for monthly training sessions for champions to train | Train-the-trainer | Project officer | 85.21 | 1 | 15 | 15 | 21.3025
11 | Ongoing support for champions | check in with champions | Identify and prepare champions | Project officer | 85.21 | 1 | 30 | 30 | 42.605
12 | Monitor training progress | request current training numbers | Train-the-trainer | Project officer | 85.21 | 1 | 10 | 10 | 14.2017
13 | Retrieve and analyse data on outcomes | same as activity | Audit and feedback | Project officer | 85.21 | 1 | 30 | 30 | 42.605
14 | Ongoing support for champions | check in with champions | Identify and prepare champions | Project officer | 85.21 | 1 | 30 | 30 | 42.605
15 | Monitor training progress | request current training numbers | Train-the-trainer | Project officer | 85.21 | 1 | 10 | 10 | 14.2017
16 | Retrieve and analyse data on outcomes | same as activity | Audit and feedback | Project officer | 85.21 | 1 | 30 | 30 | 42.605
17 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | Project officer | 85.21 | 1 | 30 | 30 | 42.605
17 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | Clinical team A - champion | 78.8025 | 1 | 30 | 30 | 39.4012
17 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | Clinical team B - champion | 56.873 | 1 | 30 | 30 | 28.4365
17 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | Team leader A | 97.2914 | 1 | 30 | 30 | 48.6457
17 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | Team leader B | 115.62 | 1 | 30 | 30 | 57.81

## Template 2B
Non-labour resource | Strategy | Monetary or opportunity cost? | Unit description | Amount of resource | Cost per unit of resource ($) | Cost source | Cost year | Total ($)
Training material | Train-the-trainer | monetary | Printed training booklet | 50 | 5 | Invoice | 2023 | 250
Training room | Train-the-trainer | opportunity | Meeting room in hospital | 1 | n/a | Market value | 2023 | 900

## Summary table
Roles |  | Train-the-trainer | Audit and feedback | Involve existing governing structures | Identify and prepare champions | Total | Roles |  | Train-the-trainer | Audit and feedback | Involve existing governing structures | Identify and prepare champions | Total
Project officer | Project officer ($788) | 305.3358 | 213.025 | 85.21 | 184.6217 | 788.1925 | Labour | Labour ($2012) | 789.5982 | 600.2299 | 333.9427 | 287.9447 | 2011.7155
Team leader B | Team leader B ($366) | 115.62 | 173.43 | 57.81 | 19.27 | 366.13 | Non-Labour | Non-Labour ($1150) | 1150 | 0 | 0 | 0 | 1150
Team leader A | Team leader A ($308) | 97.2914 | 145.9371 | 48.6457 | 16.2152 | 308.0894 | Total |  | 1939.5982 | 600.2299 | 333.9427 | 287.9447 | 3161.7155
Clinical team A - champion | Clinical team A - champion ($236) | 157.605 | 39.4012 | 0 | 39.4012 | 236.4075
Clinical team B - champion | Clinical team B - champion ($171) | 113.746 | 28.4365 | 0 | 28.4365 | 170.619
Executive B | Executive B ($75) | 0 | 0 | 75.2388 | 0 | 75.2388
Executive A | Executive A ($67) | 0 | 0 | 67.0383 | 0 | 67.0383
Total |  | 789.5982 | 600.2299 | 333.9427 | 287.9447 | 2011.7155