Table: MRC framework phase-specific implementation strategies and considerations

| ERIC strategy | Single service | ERIC strategy | Regional service innovation |
| --- | --- | --- | --- |
| Identification and Adaptation phase |  |  |  |
| Build a coalition | Leveraging existing clinical-academic relationships and charity partnerships the concept of NROL within the NHS was cultivated. | Build a coalition | Involvement was extended to include leaders at NHS Trusts across the region who provide community-based stroke and/or neurorehabilitation services (i.e. partnered NHS Trusts), and management with overarching responsibility within the regional integrated care system. |
| Conduct local needs assessment | Identified that NROL aligned with local and national strategic priorities (1-5) and provided scope to help meet clinical guidelines (6). Understanding gained of pilot context compared to local single service NHS context. | Conduct local needs assessment | Understanding gained of partnered NHS Trusts service/s contexts (e.g. multi-service) given differences in service structure, remit and provision. |
| Assess readiness and identify barriers | Need for local information governance and data protection approvals. Technology assistance deemed essential but role not standard within service. | Assess readiness and identify barriers | Need for regional information governance and data protection approvals. |
| Create a learning collaborative | A learning collaborative was established and evolved over time as NROL was expanded. It involved diverse stakeholders such as patients, healthcare system staff (therapy staff, management, administrative and decision-makers), clinical-academic and academic staff, third sector organisations and the original intervention developers). | Create a learning collaborative | The learning collaborative was extended to ensure representation across the region. |
| Develop an implementation blueprint | An Implementation Research Logic Model, and NROL Standard Operating Procedure (SOP) and materials were co-produced and revised periodically across phases. | Develop an implementation blueprint | A new iteration of the Implementation Research Logic Model was co-produced for regional delivery. NROL SOP and materials revised for multi-service approach e.g. Change in referral process, staffing etc. |
| Feasibility, Implementation and Evaluation phase |  |  |  |
| Implementation facilitation | Facilitated local information governance and data protection approvals. | Implementation facilitation | Sought support from regional stakeholders to obtain information regional governance and data protection approvals |
| Access new funding | Charity funding for key NROL technical, operational and evaluation roles. | Access new funding | Charity and NHS England funding for expanding in regional services and on-going technical, operational and evaluation roles |
| Recruit, designate and train | Recruit/designate therapy staff to deliver groups, including new technical role. | Recruit, designate and train | Transition of NROL technical and operational roles to healthcare system integrated roles, train therapy staff from partnered NHS Trusts. |
| Identify and prepare champion | Single-service champions developed organically from learning collaborative and those delivering therapy. | Identify and prepare champion | Champions identified from each service in the region involved in community-based stroke and/or neurorehabilitation delivery. |
| Provide local technical assistance | Technical assistance for patients and staff. | Provide local technical assistance | Technical assistance for patients and staff |
| Conduct cyclical small tests of change | Feasibility of the adapted NROL was determined through an initial trial (single group, small cohort), and then sequential implementation (broader range of multidisciplinary therapy groups, increasing patient cohort) and evaluation at a single service. NROL was refined iteratively e.g. adding/trialling new groups. | Staged implementation scale-up | Sequential onboarding of regional community-based stroke and neurorehabilitation services. Feasibility was determined through concurrent implementation and evaluation at a multi-service systems level. |
| Capture and share local knowledge | Collected and collated quantitative and qualitative patient, staff and service data. Shared with learning collaborative, champions and wider stakeholders at regular meetings. | Capture and share local knowledge | Collected and collated quantitative and qualitative patient, staff and service data. Focus on further understanding efficiencies. Shared with learning collaborative, champions and wider stakeholders at regular meetings. |
| Conduct ongoing training | Observations enabled therapists and other staff to gain understanding of NROL, and experience groups. This could be for insight or experiential learning before facilitating groups. | Conduct ongoing training | Observations enabled therapists and other staff to gain understanding of NROL, and experience groups. This could be for insight or experiential learning before facilitating groups. |
| Conduct local consensus discussions | Implementation outcomes were discussed, and consensus reached on patient, staff and service acceptability, and appropriateness of NROL within the service. | Conduct local consensus discussions | At a regional level, consensus was reached regarding system adoption and acceptability. |
| Sustainment phase |  |  |  |
| Stakeholder communication on the continued impact of the evidence-based practice | Continued engagement with local clinical, service and regional leads for championing NROL and communicating evaluation findings. The coalition and champions were key in strategic alignment and highlighting opportunities for visibility and impact. | Stakeholder communication on the continued impact of the evidence-based practice | Continued engagement with regional clinical, service and regional leads for championing NROL and communicating evaluation findings. The coalition and champions were key in strategic alignment and highlighting opportunities for visibility and impact. |
| Fund and contract for clinical innovation | Identified advantages in terms of staff and patient resources, barriers and facilitators identified. | Fund and contract for clinical innovation | Developed business case for commissioners with advantages identified in terms of staff and patient resources, barriers and facilitators identified. |
| Involve executive boards | Potential value proposition of local versus regional delivery discussed with decision-makers, outlining outcomes and resources required and tailoring to strategic priorities. | Involve executive boards | Value proposition shared with decision-makers, outlining outcomes and resources required and tailoring to strategic priorities. |

References

- NHS Lancashire and South Cumbria Integrated Care Board. Lancashire and South Cumbria Integrated Care System: Our NHS Joint Forward Plan from 2023 onwards. 2023 [Available from: https://www.healthierlsc.co.uk/application/files/7416/8977/5384/LSC_ICB_Joint_Forward_Plan_2023.pdf.

- NHS England. 2022/23 priorities and operational planning guidance. 2022 [Available from: https://www.england.nhs.uk/wp-content/uploads/2022/02/20211223-B1160-2022-23-priorities-and-operational-planning-guidance-v3.2.pdf.

- NHS England. 2023/24 priorities and operational planning guidance 2023 [Available from: https://www.england.nhs.uk/wp-content/uploads/2022/12/PRN00021-23-24-priorities-and-operational-planning-guidance-v1.1.pdf.

- NHS England. The NHS Long Term Plan. 2019 [Available from: https://www.england.nhs.uk/wp-content/uploads/2022/07/nhs-long-term-plan-version-1.2.pdf.

- NHS England. NHS Long Term Workforce Plan. 2023 [Available from: https://www.england.nhs.uk/wp-content/uploads/2023/06/nhs-long-term-workforce-plan-v1.21.pdf.

- Royal College of Physicians. National Clinical Guideline for the Stroke for the United Kingdom and Ireland. 2023 [Available from: https://www.strokeguideline.org/app/uploads/2023/04/National-Clinical-Guideline-for-Stroke-2023.pdf.