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	Region 
	Topic 
	Challenges/projects
	Reported results (Aug 2017–Sept 2018)

	Amhara 
	Woreda standards  
	June 2018: increase woreda management standards met from 53% to 75%. (HSS project, #21).
	Increased woreda management standards met from 53% to 96%. 

	
	ANC4+ service uptake 
	June 2018: increase ANC4+ service uptake coverage from 48% to 75%. (Maternal and neonatal health: ANC project, #60).
	Increased ANC4+ service uptake coverage from 48% to 58%. 

	
	Skilled delivery 
	June 2018: increase skilled delivery service uptake coverage from 64% to 70%. (Maternal and neonatal health: delivery project, #7).
	Increased skilled delivery service uptake coverage from 64% to 71%. 

	
	Immunization 
	Aug 2018: decrease Penta3 defaulter rate from 7% to 5%. (Child health- immunization, #69).
	Decreased Penta3 defaulter rate from 7% to 3%.

	
	Severe acute malnutrition 
	Aug 2018: decrease severe acute malnutrition (prevalence rate from 3.6% to 1%. (Nutrition project, #75)
	Decreased severe acute malnutrition prevalence rate from 3.6% to 1.3%. 

	Oromia 
	Disease Prevention  
	By end of Feb 2018, increase TB case detection rate from 40% to 60%. (Other: TB prevention and control project, #122)
	TB case detection rate remained 40% (did not meet the desired measurable result.) 

	
	Community-based health insurance  
	By end of Oct 2018, increase proportion of households enrolled in CBHI scheme from 8% to 75%. (CBHI project, #156)
	Increased the proportion of households enrolled in CBHI scheme from 8% to 25%. 

	
	Disease prevention  
	By end of July 2018, decrease the prevalence malaria positivity rate from 2.8% to 0.8%. (Other: malaria prevention and control project, #147)
	Decreased the prevalence malaria positivity from 2.8% to 0.7%. 

	SNNP
	Family Planning 
	By end of December 2017, increase modern contraceptive acceptance rate from 34% to 60%. (FP project, #215)
	Increased modern contraceptive acceptance rate from 34% to 67%. 

	
	Community-based health insurance  
	By end of June 2018, increase the proportion of households enrolled in CBHI scheme from 15% to 100%. (CBHI project, #241)
	Increased the proportion of households enrolled in CBHI scheme from 15% to 64%. 

	Tigray
	
Hospital Reform
	By end of Feb 2018, increase hospital services transformation guidelines standards met from 30% to 70%. (HSS project, #93)
	Increased hospital services transformation guidelines standards met from 30% to 69%. 




