|  |  |  |  |  | Preparatory phase |  |  | Trial duration |  |  |  |  |  |  |  |  |  | Analysis |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Procedures /à 6 months |  | 3 | 6 |  | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 |
| Chief monitor | Pre-trial visits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Check on compliance with GCP, ultrasound equipment, perinatal tertiary care center |  |  |  |  |  | X |  | X |  |  | X |  | X |  | X |  |  | X |
|  | Check on correct application of inclusion/ exclusion criteria, randomization procedure/ rate |  |  |  |  |  | X |  | X |  |  | X |  | X |  | X |  |  | X |
|  | Report regularly to PI and CI on deviation from protocol and on safety (AE/SAE) |  |  |  |  |  | X |  | X |  |  | X |  | X |  | X |  |  | X |
|  | Verify quality of data reported in CRF (including AE/SAE); address barriers with staff; seek solutions |  |  |  |  |  | X |  | X |  |  | X |  | X |  | X |  |  | X |
|  | Instruct and supervise assistant monitors |  |  |  |  |  | X |  | X |  |  | X |  | X |  | X |  |  | X |
|  | Clarify inconsistencies on CRF with staff if assistant monitors cannot resolve them, initial CRF changes |  |  |  |  |  | X |  | X |  |  | X |  | X |  | X |  |  | X |
|  | Check on documentation of withdrawals/ dropouts of enrolled participants according to SOP |  |  |  |  |  | X |  | X |  |  | X |  | X |  | X |  |  | X |
|  | Write monitoring report on study visits |  |  |  |  |  | X |  | X |  |  | X |  | X |  | X |  |  | X |
|  | Maintain Investigator's Brochure in centers |  |  |  |  |  | X |  | X |  |  | X |  | X |  | X |  |  | X |
| Assistant monitor | Verify data reported on CRF on-site; at least 100% of primary/secondary endpoints and safety variables; at least 80% of other endpoints/ data |  |  |  |  |  |  | X X | X X | X X | X X | X X | X X | X X | X X | X X | X X | X X | X X |
|  | Query and clarify discrepancies with staff on-site according to SOP, and report to chief monitor |  |  |  |  |  |  | X X | X X | X X | X X | X X | X X | X X | X X | X X | X X | X X | X X |
|  | Regularly collect filled in and verified CRF and transport/ship to KKS according to SOP |  |  |  |  |  |  |  | X |  | X |  | X |  | X |  | X |  |  |

Table 1: Time-points of visits and procedures every 6 months (X) and per month (XX)