Appendix 8 – STOP/GO criteria of internal pilot

(sections in bold specifying what was met in the pilot)

|  | RED | AMBER | GREEN * |
| --- | --- | --- | --- |
| Pilot recruitment/total study recruitment target by end of study month 21 | <10% | 10-20% | >20% |
| Mean recruitment rate/site/month (based on data to end of study month 21) | <0.2 | 0.2-0.3 | >0.3 |
| Number of sites opened by end of study month 18 | <19 | 20-23 | ≥24 |
| Total number of patients recruited by study month 18 | <37 | 37-47 | >47 |
| Proportion of those recruited by study month 18 retained to end of follow up* | <50% | 50%-60% | >60% |
| Percentage of LTADs removed due to peritonitis by end of study month 21* | >15% | 10%-15% | <10% |
| Proportion completing SFLDQoL questionnaire (except questions on sexual function) in those retained at time point, by end of month 18* Baseline Week 4 Week 8 Week 12 | <91% <85% <80% <75% | 91%-95% 85%-90% 80%-85% 75%-80% | >95% >90% >85% >80% |
| Checklist for LTAD insertion and post procedure monitoring % completed | <75% | 75%-85% | >85% |