Table 1: Time and Events Schedule

| Study Phase | Screening |  | Treatment Phasea |  |  |  |  |  |  |  | Follow-up Phase |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Week | Week 1 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 18 | Week 31 | End of study or in Case of Dropoutb |
| HPV and Pap smear screening for eligibility | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Histologic diagnosis of CIN 2/3 |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Inclusion and exclusion criteria |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Pregnancy testc |  | X |  |  |  |  |  |  |  |  |  |  |  |
| HIV, hepatitis A, B, and C screeningd |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Informed consent (ICF)e |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Sociodemographic, sexual and clinical information |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Randomization |  | X | X |  |  |  |  |  |  |  |  |  |  |
| LEEP treatment |  |  | X |  |  |  |  |  |  |  |  |  |  |
| 5-FU treatment visits |  |  | X |  | X |  | X |  | X |  |  |  |  |
| Imiquimod treatment visits |  |  |  | X |  | X |  | X |  | X |  |  |  |
| Follow-up evaluation visits |  |  |  | X |  | X |  | X |  | X |  | X | X |
| Assessment of test of curef |  |  |  |  |  |  |  |  |  |  | X |  | X |
| Assessment of CIN recurrencef |  |  |  |  |  |  |  |  |  |  |  | X | X |
| AE reviewg | Continuous review |  |  |  |  |  |  |  |  |  |  |  |  |

- There will be a minimum of 7-days between subsequent treatments for each treatment dosing in each participant.

- 14–26 weeks post first-dosing day (also applicable in case of dropout).

- Urine pregnancy test at screening, serum pregnancy test at enrolment and randomization.

- HIV-1 and HIV-2 test, and hepatitis A, B, and C test. If test otherwise performed within 3 months prior to the first treatment dosing, testing at screening is not required.

- Signing of the informed consent form (ICF) needs to be done before the first study-related activity.

- Screening to be followed by colposcopy and biopsy if positive

- Adverse events and concomitant medication will be monitored throughout the study from signing of the ICF onwards until the participant’s last study-related activity, or until the participant has been deemed lost to follow-up after demonstration of due diligence of follow-up effort

Table 2: Condensed timelines for research activities

| Proposed Activities | Year 1 |  |  |  |  | Year 2 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 | Q2 |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |
| Study preparation, IRB approvals |  |  |  |  |  |  |  |  |  |  |
| Participants’ enrolment |  |  |  |  |  |  |  |  |  |  |
| Data collection + follow-up |  |  |  |  |  |  |  |  |  |  |
| IRB renewal |  |  |  |  |  |  |  |  |  |  |
| Presentations |  |  |  |  |  |  |  |  |  |  |
| Project close-out |  |  |  |  |  |  |  |  |  |  |
| Statistical analysis |  |  |  |  |  |  |  |  |  |  |
| Dissemination of findings |  |  |  |  |  |  |  |  |  |  |

Abbreviations: IRB, institutional review board