Additional File 1: Flow diagram – Facilitating Return to work through Early Specialist Health-based interventions (FRESH) study Process evaluation

To describe participating sites (Months 1-23)

- Site feasibility questionnaire

- Telephone survey

Development of FRESH Intervention Training Package (manual, training and mentoring)

(Months 1-6)

Therapist Pre-training knowledge & confidence questionnaire

To understand OTs’ experiences of being trained and delivering intervention

(Months 12-14 & 32-34)

- Interviews with FRESH OTs.

Therapist Training

(Months 7-9)

Therapist Post-training

Knowledge & confidence questionnaire

To describe dose, content, adherence and barriers to delivery (implementation):

- Intervention CRF (session content) (Month 34-38)

- NHS therapy notes (Months 13-38)

- Fidelity checklists at 3-monthly monitoring visits (Months 13-38)

- Mentoring records (Monthly)

- Interviews with participants, therapists, employers & NHS staff (Months 15-34)

FRESH Intervention Delivery in 3 Sites (Months 9-34)

Manual-based FRESH delivered by a trained OT supported by monthly expert and peer mentoring

Refresher Training (sites 1-3)

(Month 13)

Usual Care Only

To describe content and delivery of Usual Care:

- Site level questionnaire

- Self-reported resource use data.

- Interviews with participants (n=15, 5 in each site)

To explore participants experiences of taking part in the intervention and perceptions and experiences of support to return to work (Months 22-34)

- Interviews with participants receiving VR and Usual Care (n=30, 5 in each site)

Understand the social and structural factors which support the implementation of the intervention (Months 16-38)

- Face to face semi-structured interviews with FRESH OT delivering the FRESH intervention at each site at the end of the study

- De-brief meetings within sites at the end of the trial

Synthesis of Process Evaluation Data with Trial outcome data (Months 12-38)

OT – occupational therapist