Additional File 2: Case and learning collaborative descriptions

Case A: Provincial ICU Delirium

The Provincial Intensive Care Unit (ICU) Delirium Initiative is a best practice implementation initiative led by Alberta Health Services (AHS) Critical Care Strategic Clinical Network (CC SCN). Province-wide implementation of the initiative occurred from September 2016 to March 2019. This initiative was implemented by operational and medical leaders and frontline teams in 17 adult and three pediatric ICUs across AHS. The ABCDEF (Assess, prevent and manage pain; Both Spontaneous Awakening Trials (SAT) and Spontaneous Breaking Trials (SBT); Choice of analgesia and sedation; Delirium: assess, prevent and manage; Early mobility and exercise; Family engagement and empowerment) care bundle of best practices to prevent and manage ICU delirium were implemented.

Case A used an AHS adaptation of the IHI Innovative Learning Collaborative (ILC) approach (1) to engage local teams in using measurement to drive clinical pathway practice changes and achieve system-wide improvements. These ILCs included learning sessions where interprofessional local teams, patients/families, and expert faculty exchange ideas. Action periods occurred between each session where local teams collected data and completed Plan Do Study Act (PDSA) cycles. Balanced Scorecards were used to organize key provincial and locally identified measures around quality dimensions. A total of five ILCs occurred during Provincial ICU Delirium Initiative implementation, involving an average of 173 multi-disciplinary participants from Alberta ICUs. Multi-disciplinary implementation teams comprised frontline health professionals and operational leaders. Each local ICU team was supported by Practice Leads as they implemented quality improvement activities that led to higher adoption rates and sustainable practices. Monthly audit and feedback reports were provided to frontline providers and unit leaders and quarterly reports were provided to Zone and site leadership.

Case B: Appropriate Use of Antipsychotics (AUA)

The Appropriate Use of Antipsychotics (AUA) in Supportive Living (SL) is a multi-phase initiative developed and implemented by the Alberta Health Services (AHS) Seniors Health Strategic Clinical Network (SCN). The AUA initiative focused on reducing the inappropriate use of antipsychotic medications for managing responsive behaviors associated with dementia. The AUA initiative was first implemented in 11 “early adopter” long term care (LTC) sites across Alberta in 2013-2014. The initiative supported enhanced implementation of the AUA Guideline and Toolkit of resources; Interprofessional Monthly Antipsychotic Medication reviews were the key interventions of the AUA initiative. Following the success of these early adopter sites in reducing antipsychotic use by 50%, the initiative was then implemented in all 170 LTC facilitates across Alberta in 2014-2015, followed by scaled implementation in 165 designated supportive living (DSL) facilities from 2016-2018.

After successful implementation of three learning collaboratives in 11 early adopter sites, a series of nine LCs (3 full-day sessions for each collaborative) occurred during provincial implementation in 2014-2015, engaging over 100 LTC sites with higher than provincial average baseline rates of resident antipsychotic medication use. Between 8-18 sites participated in each collaborative (one “change team” from each site). These “change-team” members were responsible for attending workshops, educating staff at their site, organizing and supporting practice change, and collecting data for the AUA initiative team. Seven of nine collaboratives occurred in person and two occurred virtually. The remaining LTC sites (approximately 60) were invited to one 2-hour educational session about the AUA toolkit and resources. These sites had lower than provincial average use of antipsychotics in their residents and received education only. In 2016-2018, with the spread to DSL, a series of 4 learning workshops engaged 156 DSL sites. Learning workshops occurred face-to-face, with some sites joining virtually. A total of 69 learning workshop sessions were held from 2016-2018. Additionally, the AUA initiative team provided 11 videoconferences, and monthly curbside consultations. Curbside consultations involved teleconference meetings to discuss case studies on responsive behaviors of residents with dementia. These additional meetings were opportunities for collaborative learning, problem solving, and support. In DSL sites, the AUA team used the AHS-adapted IHI Innovation Learning Collaborative (ILC) approach developed by SCNs in AHS (1). ILCs engage provincial teams in using measurement to drive clinical pathway practice changes and achieve system-wide improvements. ILC methods include learning sessions, action periods, balanced scorecards, measurement, results, and sustainability processes. The ILC method, tools and training are standardized to achieve: 1) care engagement; 2) focus on quality and 3) finish to sustainment (2).

Reference

1.	Institute for Healthcare Improvement. The Breakthrough Series: IHI’s collaborative model for achieving breakthrough improvement. 2003.

2.	Arain M, Charland P, Graham L, Memon A, Ahmad A. Appropriate Use of Antipsychotics in Designated Supportive Living 4/4D Evaluation: Final Report. Calgary, AB: Health Systems Evaluation and Evidence Alberta Health Services; 2018.