Appendix 1:  Summary of results

| Phase 1: Initial consideration for the host environment |  |  |  |
| --- | --- | --- | --- |
| Sub-dimensions | CSCom 1 | CSCom 2 |  |
| - Conduct a needs and resources assessment | Top down dominated by the health district |  |  |
| - Carry out an adequacy assessment | No assessment |  |  |
| - Carry out a readiness assessment | No assessment |  |  |
| - Possibility for adaptation | Multiple adaptation measures taken by the CSCom depending on the context |  |  |
| - Obtain explicit buy-in from key stakeholders and promote a favourable organisational climate | - Awareness-raising activities - Collaboration with influential community actors - Patient awareness during consultations - Door – to – door - Vaccinating staff to lead by example |  |  |
| - Strengthen general/organizational capacity | - Mobilisation of staff - Supply of assets by the Sanitary District |  |  |
|  | One-off financial contribution from CSCom |  | One-off financial contribution from ASACO |
| - Recruit and maintain staff | Recruitment of vaccinators from internal resources (staff, relays, trainees) |  |  |
| - Efficiently train staff prior to innovation | Cascading training: District Staff CSCom – vaccinators |  |  |
| Phase 2 |  |  |  |
| - Create implementation teams | 14 teams of five people during the first phase of vaccination | 20 teams of two people |  |
| - Develop an implementation plan | - Application of the micro-plan developed by the health district - Measuring the adjustment of vaccination strategies according to contexts |  |  |
| Phase 3 |  |  |  |
| - Assistance/coaching/supervision | - Cascading supervision (Health District – CSCom) - Low field presence of supervisors |  |  |
| - Evaluation of the process | Lack of process assessment activities |  |  |
| - Formative feedback mechanism | Informal feedback |  |  |
| Phase 4 |  |  |  |
| - Learn from experiences | - Need to raise awareness before vaccinating - Ensure availability of funds to pay for vaccinators’ premiums - Need to increase the duration of awareness raising |  |  |