Supplemetary Materials

A: Floor Plan Drawing of EPS Made Model Building

# B: Roof Plan Drawing of EPS Made Model Building

Roof plan

# C: EPS Made Model Building Panels View

# D: Results of a Monte Carlo Simulation

| Time | Probability | Number iterations out of 500 |
| --- | --- | --- |
| 79 | 0% | 0 |
| 80 | 0% | 0 |
| 81 | 0% | 0 |
| 82 | 0% | 0 |
| 83 | 0% | 0 |
| 84 | 0% | 0 |
| 85 | 0% | 0 |
| 86 | 0% | 0 |
| 87 | 0% | 0 |
| 88 | 0% | 0 |
| 89 | 0% | 0 |
| 90 | 0% | 0 |
| 91 | 0% | 0 |
| 92 | 0% | 0 |
| 93 | 0% | 0 |
| 94 | 0% | 0 |
| 95 | 0% | 0 |
| 96 | 0% | 0 |
| 97 | 0% | 0 |
| 98 | 0% | 0 |
| 99 | 1% | 5 |
| 100 | 1% | 6 |
| 101 | 3% | 13 |
| 102 | 4% | 20 |
| 103 | 6% | 29 |
| 104 | 8% | 39 |
| 105 | 10% | 49 |

| 106 | 12% | 60 |
| --- | --- | --- |
| 107 | 17% | 84 |
| 108 | 22% | 110 |
| 109 | 28% | 142 |
| 110 | 35% | 177 |
| 111 | 41% | 207 |
| 112 | 48% | 242 |
| 113 | 55% | 273 |
| 114 | 62% | 311 |
| 115 | 66% | 332 |
| 116 | 72% | 358 |
| 117 | 76% | 382 |
| 118 | 82% | 408 |
| 119 | 86% | 429 |
| 120 | 89% | 445 |
| 121 | 91% | 456 |
| 122 | 93% | 467 |
| 123 | 96% | 479 |
| 124 | 96% | 482 |
| 125 | 98% | 489 |
| 126 | 99% | 493 |
| 127 | 99% | 496 |
| 128 | 99% | 497 |
| 129 | 100% | 499 |
| 130 | 100% | 499 |
| 131 | 100% | 500 |
| 132 | 100% | 500 |
| 133 | 100% | 500 |
| 134 | 100% | 500 |
| 135 | 100% | 500 |

| 136 | 100% | 500 |
| --- | --- | --- |
| 137 | 100% | 500 |
| 138 | 100% | 500 |
| 139 | 100% | 500 |
| 140 | 100% | 500 |
| 141 | 100% | 500 |
| 142 | 100% | 500 |
| 143 | 100% | 500 |
| 144 | 100% | 500 |
| 145 | 100% | 500 |
| 146 | 100% | 500 |
| 147 | 100% | 500 |
| 148 | 100% | 500 |
| 149 | 100% | 500 |
| 150 | 100% | 500 |
| 151 | 100% | 500 |

# E: Flexural Strength Test Result Sample Graphs

Stress –strain of 15kg/m3 density panel	     Stress –strain of 18kg/m3 density panel

Load displacement of 15kg/m3 density	     Load displacement of 18kg/m3 density

# F: Duration Estimation

| Work item | Unit | Quanti- ty |  | Out- put per man / day |  | Min. worker (max.dur ation ) |  | Aver. Workers (aver. duration ) |  | Max. worker min. du- ration |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Earth work and exca- vation |  |  |  |  |  | 14.2 |  | 9.1 |  | 7.1 |
| Site clearance | m2 | 372.46 |  | 10 |  | 4.1 |  | 2.7 |  | 2.1 |
| Bulk excavation | m3 | 43.31 |  | 1.8 |  | 2.7 |  | 1.7 |  | 1.3 |
| Pit excavation | m3 | 32.2 |  | 1.7 |  | 2.1 |  | 1.4 |  | 1.1 |
| Trench excavation | m3 | 59.58 |  | 1.25 |  | 5.3 |  | 3.4 |  | 2.6 |
| Output per crew |  |  |  |  |  |  |  |  |  |  |
|  | Unit | Qua ntity | Out- put per crew / day |  | Min. worker (max.durat ion ) |  | Aver. Workers (aver. du- ration ) |  | Max.worker min.duration |  |
| 1. Sub structure Con- crete work |  |  |  |  | 28.6 |  | 24.0 |  | 17.3 |  |
| Masonry work | m3 | 65.5 | 5 |  | 1.5 |  | 0.4 |  | 0.4 |  |
| Pad concrete | m3 | 3.26 | 10 |  | 0.2 |  | 0.2 |  | 0.1 |  |
| Foundation column con- crete | m3 | 1.02 | 10 |  | 0.1 |  | 0.1 |  | 0.0 |  |
| Grade beam concrete | m3 | 7.55 | 10 |  | 0.4 |  | 0.4 |  | 0.3 |  |

| In 100 mm thick Ground slab | m3 | 23.3 | 10 | 1.2 | 1.2 | 0.8 |
| --- | --- | --- | --- | --- | --- | --- |
| ø10 mm def bars for ground slab mesh | kg | 1201 .51 | 100 | 4.0 | 3.0 | 3.0 |
| ø12 mm def bars for pad work | kg | 1123 .5 | 100 | 5.6 | 5.6 | 3.7 |
| Pad formwork | m2 | 15.1 4 | 6 | 1.3 | 1.3 | 0.8 |
| Foundation column form. | m2 | 32.2 | 5 | 3.2 | 3.2 | 2.1 |
| Grade beam form work | m2 | 48.1 2 | 5 | 4.8 | 4.8 | 3.2 |
| Hardcore | M2 | 232. 29 | 18 | 6.5 | 4.3 | 3.2 |
| 2. Super structure con- crete |  |  |  | 47.7 | 38.1 | 29.5 |
| Elevation column concrete | m3 | 3.12 | 6 | 0.3 | 0.2 | 0.1 |
| Stair case concrete | m3 | 3.16 | 8 | 0.2 | 0.1 | 0.1 |
| Intermediate beam concrete | m3 | 9.1 | 6 | 0.8 | 0.5 | 0.4 |
| First floor 70mm thick con- crete | m3 | 18.0 5 | 8 | 1.1 | 0.8 | 0.6 |
| Top tie beam concrete | m3 | 4.92 | 6 | 0.4 | 0.3 | 0.2 |
| elevation column form work | m2 | 110. 4 | 3 | 9.2 | 12.3 | 9.2 |
| Slab panel | m2 | 183. 07 | 5 | 9.2 | 6.1 | 4.6 |
| Intermediate beam form work | m2 | 63.8 4 | 3 | 10.6 | 7.1 | 5.3 |

| In Staircase form work | m2 | 18.5 | 3.5 | 2.6 | 1.8 | 1.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Top tie beams form works | m2 | 59.0 4 | 3 | 9.8 | 6.6 | 4.9 |
| Reinforcement |  |  |  | 12.6 | 8.5 | 7.3 |
| ø10 mm def bars for first floor slab mesh | kg | 1201 .51 | 100 | 1.3 | 0.9 | 0.7 |
| ø12 mm def bars for beams and column | kg | 2556 .2 | 100 | 2.8 | 1.8 | 1.4 |
| ø14 mm def bars for beams and column | kg | 3604 .3 | 100 | 4.0 | 2.6 | 2.0 |
| ø16 mm def bars for beams and column | kg | 395. 51 | 100 | 0.4 | 0.3 | 0.2 |
| 3. Block work |  |  |  | 8.3 | 5.8 | 4.6 |
| For external wall 20 cm thick | m2 | 295. 2 | 10 | 5.9 | 4.9 | 3.3 |
| For partion wall 10 cm thick | m2 | 96 | 8 | 2.4 | 0.9 | 1.3 |
| 4. CARPENTRY & JOINERY |  |  |  | 14.3 | 10.3 | 6.9 |
| Upper & Lower eucalyptus members. Size Dia.10- 12cm | ml | 359. 63 | 37 | 1.9 | 1.6 | 1.1 |
| Diagonal & vertical euca- lyptus members size Dia.8- 10cm | ml | 291. 87 | 23 | 2.5 | 2.1 | 1.4 |
| Purlin zigba 5*7 cm | ml | 750. 65 | 23 | 6.5 | 5.4 | 3.6 |
| Agro-stone doors in different sizes | no | 20.0 0 | 3 | 3.3 | 1.1 | 0.7 |

| 5. ROOFING | m2 |  |  | 5.0 | 4.0 | 2.9 |
| --- | --- | --- | --- | --- | --- | --- |
| G-28 Galvanized CIS roof- ing. | m2 | 257. 93 | 40 | 2.1 | 1.6 | 1.3 |
| Supply and fix G-28 Flash- ing(Copping) in flat metal sheet fix as shown detail drawing dev't length 33cm | ml | 180. 50 | 16 | 2.3 | 1.9 | 1.3 |
| Supply and fix G-28 flat sheet gutter dev't length 50cm as per the detail draw- ing | ml | 38.0 5 | 30 | 0.3 | 0.2 | 0.1 |
| Supply and fix G-28 flat sheet Valley gutter dev't length 90 cm as per the de- tail drawing | ml | 45.0 0 | 30 | 0.3 | 0.3 | 0.2 |
| 6. FINISHING WORK |  |  |  | 32.8 | 19.9 | 13.1 |
| Three coats of plastering for internal wall | m2 | 1189 .08 | 35 | 6.8 | 4.2 | 3.4 |
| Two coats of plastering for external wall ,columns &beams | m2 | 443. 98 | 35 | 4.2 | 2.5 | 1.6 |
| Apply three coats of plastic emulsion paint | m2 | 1189 .08 | 30 | 13.2 | 7.9 | 5.0 |
| Ceramics floor finish | m2 | 257. 00 | 10 | 8.6 | 5.1 | 3.2 |
| Total duration |  |  |  | 151 | 111 | 79 |