| Supplementary Table A1. Traffic light progression criteria |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Progression Criteria | Red (stop) | Amber (discuss & amend) | Green (go) | Finding | Status |
| - School recruitment (targeting n=6) | 1-2 schools recruited | 3-4 schools recruited | 6 schools recruited | 6 schools recruited (4 intervention, 2 control), >20 schools expressed an interest. | Green – proceed. |
| - Student recruitment (targeting n~810) | <20% of eligible students | 20-74% of eligible students | ≥75% of eligible students | 877 students recruited and participated in T1 survey. | Green – proceed. |
| - School staff training recruitment | ≤2 teachers per school | 3-6 teachers per school | ≥6 teachers per school | School 1: 10 School 3: 10 School 4: 18 School 6: 17 Average = 14 | Green – proceed. |
| - Suicide Prevention workshop delivery | <80% of scheduled workshops delivered | 80-99% of scheduled workshops delivered | 100% of scheduled workshops delivered | 100% of scheduled workshops delivered in intervention schools. | Green – proceed. |
| - Students screening at high-risk of suicide at T2 | <5 per school | 5-10 per school | 10-15 per school | School 1: 21 School 2: 18 School 3: 8 School 4: 20 School 5: 26 School 6: 12 Average = 18 | Green – proceed. |
| - Reframe IT-UK participation | <40% of eligible students engage with ≥75% of modules | 40-69% of eligible students engage with ≥75% of modules | ≥70% of eligible students engage with ≥75% of modules | 58 students eligible and 17 signed up for Reframe IT-UK (29.3%). Of those who enrolled, 71% completed ≥75% of modules. | Mixed red and green. Fewer students than targeted signed up (red), but those who signed up completed the desired number of modules (green). Qualitative feedback suggested that a future trial with Year 9 students would address concerns with sign-ups. |
| - Acceptability of intervention | <50% found MAPSS acceptable | 50-79% found MAPSS acceptable | ≥80% found MAPSS acceptable | Workshops: 89.9% found it somewhat or very useful, 86.3% would recommend to CYP. Reframe IT-UK: 72.7% agree or neither agree/disagree found it useful. 100% agree or neither agree/disagree found it easy to use. 90.9% would recommend to CYP. | Workshop: green – proceed. Reframe IT-UK: mixed green and amber. Targets were met for the proportion finding it easy to use and recommending it to another young person (green), but below target for proportion finding it useful (amber). Qualitative data suggested that adapting the topics of the modules could increase their usefulness. |
| - Outcome data collected at baseline | Data collected from <50% of students | Data collected from 50-79% of students | Data collected from ≥80% of students | Data collected from 92% of students. | Green – proceed. |
| - Follow-up outcome data attrition at T3 | >40% data attrition at T3 | 21-40% data attrition at T13 | ≤20% data attrition at T3 | School 1: 15.5% School 2: 67.7% School 3: 24.6% School 4: 1.5% School 5: 52.4% School 6: 8.7% Average = 26.7% | Amber – amend. Higher than targeted attrition in 3 schools. Qualitative data suggested beginning MAPSS delivery in September, with designated lead-in time in the academic year prior, would improve attrition. Implementing with Year 9 students instead would also help. |