## Ark1
Additional file 1. Timeline of strategies to facilitate implementation of the RCT
| 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
| Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Revision of trial design in collaboration with participating clinics
Development of protocol for control group
Monthly meetings with clinic management
Seminars for participating clinics and clinicians
Revision of questionnaire and software in collaboration with clinicians
Training of research coordinators, digitally and in seminars
Bi-weekly meetings with reserach coordinators
Project managment visits to participating clinics
Annual regional HIA-conferences
Information letter to all GPs in coverage area from project management
Intermittent visits from clinicians to GP offices in coverage area