## Data
Schedule durations and derived metrics — edit any blue cell
Method | Type | Improvement serial | Foundation serial | Improvement parallel (overlap) | Foundation parallel (remainder) | Super structure | T_cp (d) | Saving vs TPW (USD/m²)
Innovative (this study) | parallel | 0 | 0 | 7 | 7 | 60 | 74 | 636
Deep Foundation (piles) | parallel | 0 | 45 | 0 | 0 | 60 | 105 | 471.7
Dynamic Compaction | serial | 10 | 14 | 0 | 0 | 60 | 84 | 583
Lime Treatment | serial | 14 | 14 | 0 | 0 | 60 | 88 | 561.8
Stone Columns | serial | 21 | 14 | 0 | 0 | 60 | 95 | 524.7
Chemical Grouting | serial | 28 | 14 | 0 | 0 | 60 | 102 | 487.6
Traditional Pre-Wetting | serial | 120 | 14 | 0 | 0 | 60 | 194 | 0
Cost rates
Component | Symbol | Value | Units
Site overhead per delay-day | ω_OH | 1.8 | USD/m²/day
Revenue / opportunity loss per day | ω_RV | 3.5 | USD/m²/day
Combined rate (used in column I) | ω_OH+ω_RV | 5.3 | USD/m²/day

## Panel_a_Gantt
Panel a — Project schedule (Gantt-style stacked bars)
Each bar is the sum of: Imp_serial + Fnd_serial + Imp_overlap + Fnd_remainder + Sup_days. Coral = soil-improvement on the critical path; teal = improvement overlapped with foundation; blue = foundation; amber = superstructure.